## Slide 1: SNS 2016 AAC Outbrief
Rod Gerig Chair
February 18, 2016

## Slide 2: Topic: Operations
Since the last meeting the SNS team has achieved sustained operations with beam power ≥ 1.2 MW, including a return to 1.4 MW operations in December 2015. Availability was typically ≥ 90%, excluding one target failure, and neutron production targets for FY2015 were almost met.
The recommendation that SNS should consider prioritization of availability above the importance of 1.4 MW has clearly been addressed. This was endorsed by the BES Triennial Review.
It was good to hear that the requirement for 1.3 – 1.4 MW operations is now only driven by trying to achieve maximum scientific output for the facility, and that emphasis is being placed on the need to manage reliability more effectively in terms of impact on users.
The machine is clearly well understood, with lots of performance metrics and extensive analysis leading to continuous system improvements in order to tackle shorter downtimes.
Recommendation:
See Charge Questions 1 & 3.

## Slide 3: Topic: Shutdown Planning
SNS developed a risk prioritization process and used it to identify 15 priority activities for the Winter 2016 outage. It was reported that 14.5 of the 15 activities were completed during the scheduled outage period.
The RAD Director has described proposed strategies to improve outage work planning in preparation for the first long facility outage in January-April 2017 and the committee found them reasonable. Communication of and implementation of these strategies to mitigate schedule risk associated with the long outage seems to be only in its very early stages. The committee did not see evidence of documentation of these strategies.
There seems to be a history of schedule risk on receipt of the IRP from the vendor. There is a tight schedule for the authorization process for RFQ beam operations/testing prior to installation. The fates of these two activities are closely tied to each other because of the need to perform them both in a single long outage. Understanding the status of these two large activities both prior to and during installation and how they interact with other major activities such as plasma processing and routine maintenance activities will be critical.

## Slide 4: Topic: Ion Source, RFQ and ITSF
The ion source continues to run with good reliability, although this year there were several failures of the edump which turn out to have been related to a change in vendor for the alumina insulator. The problem now seems to be resolved by reverting to the original supplier plus increasing the insulator thickness in the weakest area. Through ongoing improvements, the source intensity continues to get better, although it is not yet to the point where one has a comfortable margin over the operational requirements (partly due to the still reduced RFQ transmission). Good progress in several areas - operation at reduced gas pressure, improvements on understanding and elimination of plasma outages, and operation with higher extraction voltage to reduce the emittance and improve the RFQ transmission.
Test Stand external antenna studies were resumed, with good results on long term stability. This external antenna source seems close to using for operations. For test stand studies of source performance variations and operation at higher extraction voltages, it would be good to get water cooling on the front slits so that source emittances can be made at full duty factor.
One expects that the source performance will continue to improve, since there is much activity worldwide on H- sources, and the SNS team are active participants in this community effort.
The RFQ is “hanging in there.” x-ray window installation has allowed the measurement of vane voltages. 15% low – as expected, since for reliability the RFQ has been operating at reduced power. This is part of the reason for the poor transmission.

## Slide 5: Topic: Ion Source, RFQ and ITSF (continued)
No LEBT valve yet on either ITSF or operational source. Committee still supports the installation of this valve in both locations at the appropriate time.
ITSF / 2nd RFQ - Disappointing that there has been no beam yet through linac. Clearly well behind the plan presented last year, making potential installation in January 2017 very tight. What remains to be done at this point is completion and approval of the safety documentation, which has now been given a very high priority so that beam testing can finally begin by June, 2016.
Almost all ITSF systems are ready, and essentially everything has been done short of the beam tests. The RFQ was tested (without beam) at full power and duty factor for several months. Hydrogen gas was flowed from the source while the RFQ was running and it was confirmed that there was no degradation in RFQ performance. There are few weeks of work remaining for completion of the protection system.
For a go/no go decision by September, one must quickly verify key performance parameters such as transmission, emittance, energy, energy spread, and reliable stable operation with beam. Assuming it’s ok, what will probably be sacrificed by this delay will be sufficient time for “shakedown,” which might lead to some extra downtime during the first run cycle with the new RFQ.
After the RFQ swap at the ITSF, there are good plans for future research there. Someone needs to be assigned as responsible person for the operation of the ITSF facility.

## Slide 6: Topic: Ion Source, RFQ and ITSF (continued)
Recommendations:
Begin beam testing of the RFQ as quickly as possible.
Carefully review the plan and schedule for all beam tests to make sure there is sufficient detail to prevent delays in testing once approvals are received, and that all items needed for the go/no go decision are included.
Once the new RFQ is installed, appoint a manager for the ITSF, who will be responsible for making it operational again with the old RFQ, and then for operation of the facility for the planned future research.

## Slide 7: Topic: Warm Linac
Operation of the warm linac
  There are no specified presentations on the warm linac.
  The committee appreciates stable operation of the warm linac for the delivery of beam power > 1.2 MW and availability > 90%.
Downtime and mitigation
  The warm linac mainly contributes the trips, which ranges from 20 minutes to 1 hour, and the number is about 0.8 time / day.
  There have been no big changes during past 5 years.
  An improvement effort, AIP-35 (Warm Linac Vacuum Upgrade), is carried out; Ion pumps are replaced with large Turbopumps. The DTL part has been completed and the CCL and MEBT part are underway.
  The committee supports the continuation of this improvement to mitigate the trips.
Recommendations
  None

## Slide 8: Topic: Linac Accelerator Physics and Software Tools
Software for Linac simulations and operations has been developed and implemented.
Linac RF tuning software, both for the warm linac and the cold linac, greatly effects to the reduction of tuning time.
  The committee appreciates the efforts of the accelerator physics team.
A new PIC code, PyORBIT, has been developing with addition of some linac models; lattice package, 3D space charge models, RF gap models, etc.
  The benchmarking result shows good agreement between the PARAMILA.
  But there are meaningful discrepancies between the measured results. The reason is not clear yet.
Recommendation
  Continue to develop the PyORBIT code to refine.

## Slide 9: Topic: Superconducting Linac / SRF
The reliability and availability of the superconducting linac has generally been good in for the past 5 years. The SNS team has developed methodologies to reduce the risk of cavity performance degradation.
The SNS team has recognized the need for SRF expertise and spare cryomodules to support the SNS mission.
The committee is impressed with the SRF capabilities and infrastructure that the SNS team has developed over the past few years. The recent developments in cavity inspection and cavity testing capabilities are seen by the committee as additional steps in the right direction.
No funding was available in the last year to implement on-site etching/electropolishing.
The SNS team has a plan to fabricate a spare medium-beta cryomodule. Progress has been made toward fabricating one 6-cell cavity. The committee sees this as a positive development. The SNS team did not provide funding for additional work on the spare cryomodule.
The SNS team has developed a plan to mitigate weak points in the high-beta cryomodule design for the PPU program. The committee views this as being a good approach.

## Slide 10: Topic: Superconducting Linac / SRF
The SNS team did not present a funding strategy or a schedule for further expansion of the on-site SRF infrastructure or producing cryomodules.
However, the committee's perception is that the recent decoupling of the STS and PPU upgrade programs is causing the SNS team to rethink their plans, priorities, and schedules.
Hence, the committee anticipates that the SNS team will have a new and refined plan for SRF infrastructure and cryomodule production at the time of the next AAC meeting.

## Slide 11: Topic: Superconducting Linac / SRF
Plasma Processing of SRF Cavities
The committee commends the SNS team on their impressive results with plasma processing of two high-beta cryomodules, including one done in-situ in the SNS tunnel. The committee is pleased to see that there is no evidence of significant cavity contamination with particulates associated with the plasma processing.
The committee agrees that it would be very beneficial to perform the majority of the in-situ plasma processing on high-beta cavities during the 4-month outage. However, the committee feels that there is a risk that there will be insufficient time and resources for the SNS team to complete the plasma processing in parallel with other critical work during this outage. In light of this, the proposed procurement and commissioning of one or more additional plasma processing carts is seen by the committee as a good investment.
Likewise, the committee would encourage the SNS team to use the Summer 2016 outage to gain more experience and make more headway with plasma processing, if possible.

## Slide 12: Topic: Superconducting Linac / SRF
Plasma Processing of SRF Cavities
The committee encourages the SNS team to plan carefully for in-situ plasma processing so that priorities, space, personnel, and resource allocations are clearly defined before the start of the outage periods.
Anticipating that there might not be enough time to plasma-process all of the high-beta cavities, and that plasma processing may not be completely free of risk, the committee suggests prioritizing plasma processing of cryomodules which have highest potential for performance improvement.
Additional comments and recommendation: see Charge Question 5

## Slide 13: Topic: Ring
The ring is meeting its requirements for reliable operation at 1.4 MW but the ongoing convoy electron collector damage rate, which increases at higher power, poses a risk to the operation and the PPU project. It warrants some effort on an improved design for electron collector.
Recommendation:
Consider adding the redesign of the electron catcher to the project prioritization planning.

## Slide 14: Topic: Target Systems (including IRP)
Overall Comments
  Excellent progress on all fronts
  Team is committed, talented, open to new ideas and criticism
IRP Replacement
  Step-by-step schedule for replacement has been created (50 days duration)
  Mock-up time overlaps summer 2016 shutdown (target, window replacement)
  IRP delivery, check-out, mock-up on the heels of the shutdown and just in time for go/no-go decision
  Critical to not rush mock-up & check-out process and/or over-work RH crews
  Recommendation:
  Consider ~1 month lagging start to IRP replacement during 4 month shutdown (or delay start of long shutdown)
Hot Cell Servo-Manipulator Replacement
  Inoperable servo-manipulator will result in almost complete halt of operations
  Concern: Not receiving high enough priority relative to other improvement projects
  Recommendation:
  Perform risk analysis to compare relative consequences of failure

## Slide 15: Topic: Target Systems (including IRP)
Target Reliability Strategy
  Record-setting target T12 was original design with repaired trapezoidal plate weld
  Other failures seem to be due to fatigue at stress concentrations caused by fabrication/design flaws
  Fabricating “perfect” targets may not be practical
  Reducing alternating stress and/or mean stress by identifying stress concentration areas and designing them out could be “hit-or-miss” and/or result in “chasing” stress concentrations to other locations
  The full analysis cycle for evaluating a design modification is ~5 months for ~3 FTE
  Reducing the loading “across-the-board” may be most effective strategy for near-term success
  Gas bubble injection promises to reduce the pressure wave loading in all downstream structures
  Small reductions in mean stress and/or alternating stress can mean big gains in lifetime (20% could result in 100 x’s increase in cycles to failure)
  Recommendation:
  Place more emphasis on an effective and stable gas bubble injection system.

## Slide 16: Topic: Target Systems (including IRP)
Gas Bubble Injection
  There appears to be no quantitative criteria for evaluating success or failure of a gas bubble injection system
  Recommendation:
  Use fatigue and stress analyses to set a quantitative minimum reduction in strain required to achieve satisfactory target vessel performance
  The small modifications suggested for the mercury loop to accommodate the short-term bubble injection scheme are probably not enough to ensure stable and safe operation. J-PARC experience and the recent testing at TTF indicate that more significant system modifications will be required. Efforts to raise the bar for the short-term scheme should be made to have a chance of stable, reliable operation at 1.4 MW within 19 months (more like a mid-term plan)
  Mitigation of cavitation-erosion damage using gas bubble injection has not been conclusively demonstrated
  Jet-flow has been shown to dramatically reduce the amount of cavitation-erosion damage
  Instrumentation (strain, temperature) of the target vessel is critical to evaluating gas bubble injection system effects and should be considered “part-and-parcel” to gas bubble injection development
  Recommendation:
  Raise the requirements of the short-term bubble injection system (including required changes to the mercury loop), incorporate with the jet-flow design, and instrument the target vessel to evaluate

## Slide 17: Topic: Pulsed Power and Electrical Systems
HVCM
  Focus on upgrades that deliver quantitative improvements to reliability and performance demonstrate “best practices”, e.g. AIP 34
  R&D prioritization follows similar methodology
    Oil circulation systems: significant reduction in component temperature – increases lifetime
    Alternative resonant capacitor: low reliability component – failure results in long downtime
    Alternative topology modulator: reduces component stress, especially resonant capacitor
Magnet Power Supplies, Kickers, and Choppers
  Power supply standardization (PS and controls interface) is a sound strategy to reduce maintenance costs, however this needs to part of a integrated prioritization process.
  Improving LEBT chopper modulator bandwidth to support “smart chopping” enhances utilization of machine capabilities
Radio Frequency Systems
  HPRF systems are starting to “show their age,” e.g. klystron and circulator failures
  Evolving stewardship philosophy to enhance component lifetime
  Identifying key R&D activities, e.g. DTL klystron 2nd cavity load, new source for DTL klystron

## Slide 18: Topic: Controls
Comments
Cyber Assessment and adoption of NIST standards are strengths and best practice
Actions taken as a result are necessary
Adoption of Code Management for Process PLCs is a strength
CSS-Boy scaling problems are an issue. Good progress and a good plan to address this. An important thing to do
Good to hear people added to process control team
PPS. An external review on priorities for rework was sensible
Excellent idea to remove power supplies from PPS

## Slide 19: Topic: Controls
Recommendations
Keep a focus on Cyber. Keep up with NIST standards. This is an ongoing and evolving battle – you are never done
Adopt Code Management for PPS PLC
Address CSS-Boy scaling problems
Think about succession planning for key staff

## Slide 20: Topic: Diagnostics
The committee heard a plan to upgrade several diagnostic systems including linac and ring BPM’s as well as BLM’s mainly because of hardware obsolescence. The plan called for AIP funds for the effort. Obsolescence is plausible but difficult for the committee to judge the risks from the evidence presented.
Recommendation:
The priority for this effort should be part of the overall priority scheme for the facility improvements.

## Slide 21: Topic: Proton Power Upgrade and Second Target Station
Significant progress made in plans to develop the Second Target Station. Very good work done in developing scientific case.
The SNS proton power upgrade portion of the project has been broken out as a separate DOE project.
Concerns are addressed in answer to charge question 6 and 10.

## Slide 22: 2016 SNS AAC Charge Context
All SNS accelerator and target-related activities over the next two years are aimed at two key objectives:
Achieve by the end of FY2017 sustainable and predictable routine operation at or near 1.4 MW to the First Target Station (FTS) with availability against published schedule of ≥ 90% while using ≤ 2 target vessels per year.
Achieve the vision of a three-source strategy for “Neutrons 2025” (including HFIR, FTS, Second Target Station [STS]) as articulated in the 2016 Strategic Science Plan for the Neutron Sciences Directorate. The accelerator and target-related aspects of this plan are identified as “SNS 2.8,” incorporating the steps necessary to double the machine power and to design a FTS target capable of accommodating beam power up to 2 MW while maintaining reasonable target lifetime.

## Slide 23: Charge Question 1: Has the performance of the accelerator complex and neutron source since the last meeting made suitable progress toward achieving Objective A?
Have moved significantly towards the specifications for Objective A, but whether this can be directly attributed as progress is difficult to quantify – this could just be down to good luck or statistics.
One of the key issues identified to achieve operational progress at the last meeting was testing and installation of the spare RFQ, but there has been little discernable movement (although good planning work has been done).
Target conditioning regimes and ‘target conservation mode’ seem to be somewhat empirical, but have proven effective so far.
Recommendation:
Keep doing what you are doing on gathering performance metrics, analysing data and underpinning operations by tackling shorter downtimes.
Keep doing everything possible to tackle long downtime events, primarily focusing on understanding and alleviating target failures.

## Slide 24: Charge Question 2: Are the SNS responses and ongoing actions to recommendations from the 2015 AAC meeting reasonable?
The committee appreciates the thorough and thoughtful responses to recommendations, and notes that in many cases SNS staff have made significant progress in the areas addressed.
Overall we emphasized two major areas in the recommendations of the 2015 meeting.
  The first was to develop a SNS wide prioritization process. Significant progress was made in this area, with scientific organizations developing a process to set priorities for instrument upgrades which were included in RAD prioritization, and an extensive and well defined process used within RAD to define outage work. We note this progress, and agree with SNS that more work needs to be done in this area.
  Secondly we strongly encouraged SNS to take the requisite steps to put beam through the new RFQ as quickly as possible. This did not happen for reasons that were explained. Furthermore, we were shown plans being ready to do this by June 1, 2016.

## Slide 25: Charge Question 2: Are the SNS responses and ongoing actions to recommendations from the 2015 AAC meeting reasonable?
We repeat these recommendations for 2016, noting that the development of a thorough, rigorous prioritization process takes time, and a change within the institutional culture.
Recommendation:
Continue the development of a quantitative prioritization process addressing outage work, AIPs other large tasks, and ultimately the two major project activities. At the next AAC meeting, present us with the output of this process showing how the approved projects met the criteria, and those not funded did not.
Ensure that the plans for putting beam through the RFQ are successfully implemented in defined time frame.

## Slide 26: Charge Question 3: Are the plans to achieve Objective A and associated risks reasonable
The accelerator today can get to 1.4 MW, but needs more operational margin to stay there reliably.
What needs to be done – achieving proper RFQ behaviour, smart chopping, plasma processing, modulator flattop, etc. – appears to be well understood, and is well integrated into the AIP program. However, lack of progress in testing of the spare RFQ, is a cause for concern.
A ‘power strategy’ has been developed for next year based on not exceeding the integrated power seen by the previous target, the upshot of which is that in FY2106 SNS seeks to demonstrate 2.5 months at 1.4 MW with the balance at lower powers to manage target lifetime.
Medium term efforts will seek to achieve reliable 1.4 MW operations by 2017, lay the foundation for 2.8 MW capability and maintain the potential to carry out the Proton Power Upgrade and Second Target Station (PPU/STS).
The instigation of an ‘incentivised performance reward’ system of bonuses for meeting operational challenges collectively is an interesting initiative.

## Slide 27: Charge Question 3: Are the plans to achieve Objective A and associated risks reasonable
The plans to achieve Objective A appear reasonable, but the associated risks have not been presented in any consistent fashion, making it difficult to understand or quantify them. The recommendation from the last meeting, encouraging project prioritization via risk analysis remains to be addressed.
Recommendation:
We encourage a rigorous approach to project prioritization, such as the use of risk analysis, and looking into best practice elsewhere.
Get spare RFQ tested and installed a soon as possible.
Sustainable performance requires investment - continue to fight for an adequate AIP budget (in the region of $4M/year).

## Slide 28: Charge Question 4: Is the scope of work identified for ongoing and future Accelerator Improvement Projects (AIP) appropriate and balanced between the competing interests building necessary margin for routine operation at 1.4 MW and addressing system obsolescence?
Comments
Building operating margin and addressing obsolescence are two aspects of ensuring reliable operation of the facility
The prima facie cases for the AIP projects that were presented to the committee seemed reasonable.
We didn’t see that common risk/reward criteria were used.
The committee endorses the policy of spending down AIP carry over.
Recommendation:
Acquire data to back up the argument that the desired amount of $4M/yr for AIP is needed for a facility of this size. E.g. What didn’t get done, what are the consequences of not doing projects?

## Slide 29: AIP
Addressing Obsolescence
Operating with obsolescent systems is not a desirable state in an ideal world.
We are not in an ideal world – Resources are finite
You have mitigation strategies in place - the most important of these being procuring sufficient spares.
With a known ‘burn rate’ of spares it should be possible to forecast the systems that need to be addressed and when
Have to make tough decisions e.g. can we manage with the current system until the upgrade?
Have to think of facility needs as a whole

## Slide 30: Charge Question 5: Are the proposed strategies to improve outage work planning in preparation for the first long facility outage in January-April 2017 reasonable?
Progress has been made in moving towards a quantitative risk prioritization process and the RAD Director laid out reasonable proposed strategies to improve outage work planning in preparation for the first long facility outage in January-April 2017. It is critical that implementation of these strategies proceed in a timely fashion.
The committee encourages the SNS team to plan carefully for in-situ plasma processing so that priorities, space, personnel, and resource allocations are clearly defined before the start of the outage periods.
Anticipating that there might not be enough time to plasma-process all of the high-beta cavities, and that plasma processing may not be completely free of risk, the committee suggests prioritizing plasma processing of cryomodules which have highest potential for performance improvement.

## Slide 31: Charge Question 5: Are the proposed strategies to improve outage work planning in preparation for the first long facility outage in January-April 2017 reasonable?
Recommendations:
We encourage quick dissemination of the planned outage work planning improvements to all impacted personnel. The schedule for doing this is already tight. Get the message out!
We encourage improvements to outage work planning proceed immediately and that the Summer 2016 outage be used as a beta test of the new process.
We view completing the authorization basis requirements for ITSF operations to be a critical path item and that it be treated accordingly in order to meet the proposed June 2016 start of RFQ beam operations.
Proceed with plasma processing during the 4-month outage, and take advantage of other opportunities in the schedule for plasma processing. Plan strategically to ensure that resources are available for this effort and prioritise cryomodules with the highest potential for improvement.

## Slide 32: Charge Question 6: Is the proposed strategy for the Proton Power Upgrade (PPU) project reasonable for an early project planning state, including the planned approach for the ring and transport systems?
The decision to break out the PPU from the Second Target Station (STS) project is very recent, and it is not clear to the committee that a strategy has been developed. However, it is clear that the PPU work may happen earlier with PPU installation work being done during normal SNS outages. Other facilities have demonstrated that this can be done, although it will be challenging. It is therefore essential that SNS develop the outage planning tools (e.g., using resource loaded scheduling during outages, and well developed prioritization) to be ready for PPU installation work.

## Slide 33: Charge Question 7: How might the target design & fabrication decisions that we are making now be improved for reaching the short-term 1.4 MW reliability goal?
Although the improvement work has been impressive, it is not clear that the current strategy will result in the reliability goal by the end of FY17
As discussed earlier, a strategy to reduce overall pressure wave effects, while still making some effort to reduce stress concentrations through design may be a more efficient use of resources
Recommendation:
To this end, along with previous applicable recommendations, a re-prioritization of activities should be considered:
  1) Gas bubble injection with jet flow
    Strain measurements on the target is an integral part of evaluating effects of gas bubble injection
  2) Continued PIE of spent targets
  3) Target design modifications to reduce stress concentrations and effects of fabrication flaws
  4) Fabrication improvements (QA, manufacturing methods, welding)

## Slide 34: Charge Question 8: What other areas of target development (besides gas injection) might have significant rewards for future target reliability?
The team has identified all the most promising areas for target development
  Gas wall could be pursued at a lower priority if jet-flow and gas bubble improvements do not result in satisfactory reduction of cavitation/erosion
  Additional and/or improved instrumentation methods would help evaluate design changes, gas bubble injection systems, “break-in” period phenomenon, target health…
PIE has been essential to target development and should be expanded if resources allow
  Possible to use CT scanning technology to image cavitation-erosion and leak areas?
Radiation Damage does not seem to be limiting factor for 1.4 MW operation
  May be an issue for 2+ MW, especially radiation damage effects coupled with fatigue performance (very difficult to assess!)
    Many SS foils from RaDIATE BLIP irradiation could be made available, if helpful

## Slide 35: Charge Question 9: How aggressively should SNS pursue implementation of gas injection for the short-term (1-year) and long-term plans? Are we using the right strategies?
As discussed earlier, to achieve goal A by end of FY17 (reliable operation at 1.4 MW with LTE 2 target replacements/yr), a more ambitious short-term gas injection system should be pursued aggressively
  Likely includes more significant mercury loop modifications to safely and stably handle gas loading
  The goal is not just to demonstrate effects on pressure wave mitigation, but to achieve reliable operation at 1.4 MW
The current short-term plan certainly would be helpful in perhaps demonstrating bubble injection effects and gaining experience with an injection system’s effects on mercury loop operation, but in our opinion, would not assure reliable target operation at 1.4 MW within the time frame of ~1.5 year
Long-term plans will always take a “back-seat” to achieving near-term goals, current operations and spare fabrication
  Should include only those improvements that are deemed likely necessary for higher power operations

## Slide 36: Charge Question 10: Is the proposed approach for the STS target systems reasonable for an early design stage, and in particular is the choice of a rotating target with vertical access for maintenance appropriate?
YES
  The safety implications of concentrated decay heat with a stationary target versus distributed decay heat with a rotating target are very compelling
Consider more deeply the replacement procedure (in-situ axle/wheel separation)
  Including the IRP replacement as it is more frequent.
The neutronics (prompt and residual dose rates analyses) should be completed ASAP to ensure proper radiological controls and shielding measures are in place to enable hands-on and RH procedures as currently envisioned
Hot Cell (Service Bay) is not included in the current layout
  Severely limits the autopsy and PIE capabilities
  Eliminates the capability for unexpected inspections or accident recovery
  Recommendation:
  Consider adding the conventional construction features for a hot cell that could be outfitted later, if necessary.

## Slide 37: Charge Question 11: Evaluate and comment on recent small-scale R&D projects conducted in collaboration with other organizations (U. Tenn.) and the readiness of the organization to pursue additional small-scale initiatives funded by other sources.
The Laser Assisted H- Stripping and the 6D Beam Dynamics Studies at ITFS are well planned R&D projects conducted in collaboration with other organizations and both projects are making good progress in achieving their goals.
The 10 microsecond H- stripping experiment is ready to take data and is on track to commence soon.
The 6D Beam Dynamics Studies could also be of direct benefit to improving the modeling efforts for SNS operations and development