## Slide 1: PPU and STS Overview
Presented at the
SNS Accelerator & Target
Advisory Committee Meeting
John Galambos, Director Proton Power Upgrade project
May 15, 2018

## Slide 2: PPU charges
Charge | Description | Presentations
 | Are the PPU pre-CD-2 activities properly focused? | 
 | Is the proposal for early use of the 2 MW PPU target in operations reasonable? | 
 | Do the benefits proposed from the PPU 2 MW target design changes outweigh additional potential complexities? | 
P4 - Galambos
A7-Kim
A9-Moss
A11-Anderson
Charge 10
T7 - Riemer
Charge 11
T1 - Wendel
T3 - Winder
T7 - Riemer

## Slide 3: SNS Upgrade Plans
Proton Power Upgrade project doubles accelerator power capability
  Near term, ~$240M
  Increases FTS capability+ capacity and provides accelerator basis for STS
Second Target Station provides new instrument hall with world class cold neutron brightness
  Delayed from PPU start, ~$1.5B
After PPU Upgrade
22 instrument slots, 8 initial instruments
24 instrument positions
19 instruments built
0.8 MW
2 MW
FTS
STS
Accelerator
Now
1.4 MW
24 instrument positions
19 instruments built
FTS
Accelerator
After STS Upgrade

## Slide 4: Second Target Station: world class cold neutron performance
STS will be the highest peak brightness long wavelength neutron source
(5 MW)
(1 MW)
(0.8 MW)
5 Å – long wavelength comparison

## Slide 5: STS project activities
Review on the initial instruments and general target/instrument hall choices in April 2017
  Rotating water cooled tungsten target concept chosen
  Instrument hall general layout
Technical parameter changes:
  15 Hz, 2 cold moderators
STS project activities suspended June 2017
  Focus resources on PPU

## Slide 6: PPU Technical Scope
RF:
Upgrade existing linac RF
RF for new cryomodules
SRF:
7 new cryomodules
Ring:
Injection / extraction regions
Target systems:
2 MW target vessel
Support system upgrades
Basis for WBS Structure
Conventional Facilities:
Tunnel stub
Klystron gallery

## Slide 7: PPU Guiding Principles
Minimize SNS operational impact
Target
  Leverage ongoing operations target improvements
Optimize built-in facility upgrade provisions and build on operational lessons
Accelerator
  Use existing technology where possible
  Utilize partnerships, sub-contract
  No equipment rework for STS following PPU

## Slide 8: PPU Parameters: power increase with energy and current
 | SNS 1.4 MW | PPU full upgrade capability | PPU FTS 60 Hz operation
Proton beam power capability (MW) | 1.4 | 2.8 | 2.0
Beam energy (GeV) | 0.97 | 1.3 | 1.3
RFQ output peak beam current (mA) | 33 | 46 | 46
Average linac chopping fraction (%) | 22 | 18 | 41
Average macropulse beam current (mA) | 25 | 38 | 27
Energy per pulse (kJ) | 23 | 47 | 33
Pulse repetition rate (Hz) | 60 | 60 | 60
Macro-pulse length (ms) | 1 | 1 | 1
FTS decoupled moderator brightness/pulse (AU) | 1 | 2.04 | 1.43
FTS coupled moderator brightness/pulse (AU) | 1 | 2.16 | 1.51
PPU delivers 2.8 MW capable accelerator
Prior to STS, accelerator will run at 2 MW to FTS
50% current increase
33% energy increase
No change

## Slide 9: Accelerator front-end is “STS ready”
Ion source output
  Operation production source has demonstrated required output
RFQ output
  Measured beam at RFQ output, 4/30/2018
STS Requirement
Beam current (A)
STS requirement
46 mA
Notes: STS – new facility

## Slide 10: PPU Activities: 2017 – 2018
CD-1 DOE reviews spring 2017
Target response summer fall 2017
CD-1 approval and funding spring 2018
Now we are preparing for CD-2
PM Cost Review
OPA CD-1 Review
April 2017
May
June
July
Aug
Sept
Oct
Nov
Dec
Jan 2018
Feb
Mar
April
PPU addressing target recommendations
Target gas injection
OPA recommendations closed
CD-1 Approved
$36M line item FY18
SRF partner selected (Jlab)

## Slide 11: PPU anticipated schedule: 2018 – 2019
Aim for a CD-2/3b review in ~ 1 year
  Baseline + preliminary design for entire project (CD-2)
  Final design for equipment already in use (CD-3b)
April 2018
May
June
July
Aug
Sept
Oct
Nov
Dec
Jan 2019
Feb
Mar
April
May
June
Complete baseline and preliminary design
Complete documentation
DOE reviews
ICE review
(Cost)
CD-2/3b review
Establish EVMS system
Director’s review
System reviews
AAC/TAC
OPA 3a/status review

## Slide 12: PPU Notional Funding Profile, Point Estimate
Cost range is $184M to $320M
The April 2017 “ICR team drilled down on >50% of direct costs; “there is a good basis of estimate.”
  Use of existing designs from SNS project and upgrades during operations.
WBS # | WBS Title | Total ($M)
Total Estimated Cost (TEC) |  | 158.5
P.01 | Project Management | 14.1
P.02 | Superconducting Linac Systems | 38.9
P.03 | RF Systems | 60.7
P.04 | Ring Systems | 10.5
P.05 | FTS Systems | 25.7
P.06 | Conventional Facilities | 8.6
Other Project Cost (OPC) |  | 14.6
P.07 | R&D | 4.6
P.08 | Pre-Ops | 2.7
P.09 | Pre-CD1 Activities | 7.3
Contingency (33%) |  | 57.1
Total Project Cost (TPC) |  | 230.2

## Slide 13: PPU Notional schedule
Holding 6-month outage/early finish firm
Include a pre-6 month outage PPU target demo, possibly at > 1.4 MW
CD3A
(TBD)
CD1
CD3
FY2018
FY2019
FY2020
FY2021
FY2022
FY2023
FY2024
FY2025
Early finish
(E)
CD4
(L)
CD2/3B
AE design of Klystron gallery
Civil construction Klystron gallery
Install RF equipment in gallery
Ring and target install
RTBT stub
6 month outage
Receive and install cryomodules
Assemble cryomodules
ARR and commis-sioning
Procure and receive RF equipment
FY2026
FY2027
KPP – 1250 hr Target ops time
Procure cavities and cryomodule hardware
30 mos. contingency
Clear Gallery, procure & install chase inserts
(SNS operations)
Prior
PPU target demo
Fabricate early PPU target
Final target design
Target development

## Slide 14: FY18 priorities
SRF / M. Howell
  Initiate cavity long lead procurements (Nb, cavity qualification equipment, cavities)
  With J-Lab, initiate cryo-module engineering baseline activities
Spare cryomodule in production since 2012 demonstrates PPU gradient
A7-Kim
Charge 6

## Slide 15: FY18 priorities
RF
  Finalize warm linac RF upgrade requirements (measurements driving RF into temporary loads for calibration)
  Test new HVCM at full power, initiate upgraded DTL klystron design and testing capability
Temporary load setup for CCL testing
3 MW resistive load
Charge A6
A9-Moss
A11-Anderson

## Slide 16: FY18 priorities
Target
  Target Test Facility gas wall injection testing
  PPU target conceptual design optimization
  Gas injection in operational targets
Charge A6
T1 – Wendel
T8 – Barbier
T7 – Riemer
T7 – Riemer
T3 – Winder
T8 – Barbier

## Slide 17: Target gas injection ramp-up: operations and PPU
Operational experience will feed into PPU target design up to mid 2020
Early PPU target demonstration is on critical path
T7 – Riemer

## Slide 18: FY18 priorities
Ring
  Extraction kicker approach
  Foil testing (Evans A5)
  Injection region magnet requirements
Conventional Facilities
  Award and initiate A/E firm design of klystron gallery work
  “BIM” design approach with RF and electrical equipment layouts incorporated
All
  Baseline scope
  Scrub schedule and cost estimates
  Draft Preliminary Design Report
Charge A6

## Slide 19: CF: Klystron gallery chase work complete
Nov 2017
Mar 2018
July 2017
Jan 2018
Stored equipment, water shop cleared out
Chases with incorrect cabling cleared
Inserts with RF waveguide / cable conduit installed
Cables re-routed
Ready for AE supported activities
Charge A6

## Slide 20: CF Activities: Klystron gallery near term
Layout of technical and conventional equipment will be combined into a single CAD model (“BIM” approach)
  Increased design scope for CF
  Will facilitate installation activities
  CF: cable trays, utilities, HVAC, …
  Include technical systems: HVCMs, RF, technical cooling skids
SOW is written, bidders oral presentations reviewed
  Aim to award this summer
Charge A6

## Slide 21: PPU-Ring extraction kicker system
Baseline: add 2 additional kickers
  Upgrade the existing 14 power supplies is preferred
Prototype extraction kicker resonant charging supply testing in progress
  Max voltage obtained to date is 39.8 kV with single pulse testing. Goal is 44 kV
Next steps: full voltage and full duty factor testing
Prototype resonant charging supply
One of the two sets of existing kicker magnets
Charge A6

## Slide 22: Ring injection dump septum and beam optics
Scope includes new injection dump septum magnet, quadrupole magnet and new beam instrumentation
  We need accurate beam optics model to achieve the best possible design
  Model benchmark with historical data:
  marginal agreement
Next steps:
  Acquire new, more complete benchmark data
  Improve the beam optics model
  Create physics specs for the new septum magnet
IDmp quad current
Beam size
Comparison of measured and model I-dump beam sizes
Charge A6

## Slide 23: PPU Key Performance Parameters
“1250 hr operation” KPP is part of the transition to operations
Key Performance Parameter | Thresholds (Performance Deliverable) | Objectives
Beam power on target | 1.7 MW at 1.25 GeV | 2.0 MW at 1.3GeV
Beam energy | 1.25 GeV | 1.3 GeV
Target operational time without failure | 1,250 hours at 1.7MW | 1,250 hours at 2.0MW
Stored beam intensity in ring | > 1.6x1014 protons at 1.25 GeV | > 2.24x1014 protons at 1.3 GeV *
Number of PPU installed cryomodules | 6 | 7
* corresponds to 2.8 MW at 60 Hz

## Slide 24: PPU Organization
FY2018 Changes
  Wayne Steffey: project controls lead
  John Moss: RF WBS level 2 lead
  Gary Bloom: CF WBS level 2 lead
Multiple positions are now open

## Slide 25: Risks / Concerns
Target performance at high power
  Timely operational experience and development activities will influence the design
Project ramp-up
  Matrix, subcontract, hire
Project mentality
  Last year’s reviews helped

## Slide 26: Summary
PPU is launched
Moving towards a baseline – fine tuning
Fleshing out the team