## Slide 1: SNS Operations Performance Metrics FY17 & FY18-Q1
Presented at the
SNS Accelerator & Target
Advisory Committee Meeting
Glen D. Johns
Accelerator Operations Manager
May 15-17, 2018

## Slide 2: Outline
FY17/18 Run Schedules
Review of SNS Commitments
Beam Power
FY17 and FY18-Q1 Performance
Downtime Overview
Summary

## Slide 3: FY17 schedule after adjustment due to IRP delivery delay Basically unchanged from last AAC

## Slide 4: FY18 schedule after extending 2017C outage due to gas injection implementation and extending 2018A by one month for IRP inspection results in a commitment of 2565 hours delivered of NP

## Slide 5: SNS Commitments
Year | Neutron Production Availability |  | Integrated Beam Power (MW-hrs) | 
 | Commitment | Actual | Commitment | Actual
FY2007 | 68.0% | 65.7% | 117 | 159
FY2008 | 74.0% | 72.0% | 877 | 945
FY2009 | 80.0% | 80.7% | 2031 | 2166
FY2010 | 85.0% | 85.6% | 3253 | 3455
FY2011 | 88.0% | 92.0% | NA | 4132
FY2012 | 90.0% | 90.0% | NA | 4368
FY2013 | 90.0% | 72.4% | NA | 3848
FY2014 | 90.0% | 83.7% | NA | 4798
FY2015 | 90.0% | 74.6% | NA | 4612
FY2016 | 90.0% | 86.4% | NA | 5348
FY2017 | 90.0% | 87.5% | NA | 5406
FY2018 (Q1) | 90.0% | 93.5% | NA | 1260
Year | Neutron Production Hours Delivered |  | Total Operating Hours Delivered | 
 | Commitment | Actual | Commitment | Actual
FY2007 | 1500 | 2078 | 3500 | 3779
FY2008 | 2700 | 2807 | 4000 | 4032
FY2009 | 3500 | 3553 | 4500 | 4916
FY2010 | 3900 | 4250 | 4800 | 5310
FY2011 | 4300 | 5002 | 5000 | 5941
FY2012 | 4500 | 4725 | 5000 | 5746
FY2013 | 4000 | 4202 | 5000 | 5120
FY2014 | 4230 | 4424 | 5000 | 5294
FY2015 | 4230 | 4441 | 5000 | 5278
FY2016 | 4230 | 4972 | 5000 | 5832
FY2017 | 4230 | 4807 | 5000 | 6079
FY2018 (Q1) | 2565 | 1040 | 5000 | 1421

## Slide 6: Beam power on target (60 sec average) – per Target Management Plan
1.0 MW for ~84 days
(T16)
2017A
Winter
Outage
2017C October
Outage
1.2 MW for ~73 days
(T17)
2017B Summer
Outage
1.2 MW for ~43 days
(T18)
IRP Leak
2018A Winter Outage

## Slide 7: IRP leak led to availability of 87.5% against schedule (94% excluding leak)
Chart: NP availability by week, FY17
| 42646 | 42653 | 42660 | 42667 | 42674 | 42681 | 42688 | 42695 | 42702 | 42709 | 42716 | 42723 | 42730 | 42737 | 42744 | 42751 | 42758 | 42765 | 42772 | 42779 | 42786 | 42793 | 42800 | 42807 | 42814 | 42821 | 42828 | 42835 | 42842 | 42849 | 42856 | 42863 | 42870 | 42877 | 42884 | 42891 | 42898 | 42905 | 42912 | 42919 | 42926 | 42933 | 42940 | 42947 | 42954 | 42961 | 42968 | 42975 | 42982 | 42989 | 42996 | 43003
Neutron Beam % Available | 0.93936 | 0.92341 | 0.84901 | 0.97619 | 0.983 | 0.88646 | 0.95226 | 0.91503 | 0.91571 | 0.94413 | 0.91154 | 0 | 0 | 0.50986 | 0.9744 | 0.9586 | 0.92998 | 0.87157 | 0.94485 | 0.83814 | 0.84643 | 0.96574 | 0.95231 | 0.9688 | 0.9253 | 0.88254 | 0.9 | 0.96702 | 0.95551 | 0.97556 | 0.97815 | 0.94145 | 0.98376 | 0.96176 | 0.93631 | 0.96812 | 0.90619 | 0.97694 | 0.97861 | 0
Commitment to DOE | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
FY running Avg. | 0.93646 | 0.92832 | 0.8982 | 0.91873 | 0.93036 | 0.92201 | 0.92676 | 0.92516 | 0.92404 | 0.92621 | 0.92596 | 0.84584 | 0.77673 | 0.75709 | 0.7745 | 0.78621 | 0.79595 | 0.80058 | 0.80786 | 0.80913 | 0.81123 | 0.81885 | 0.82417 | 0.82963 | 0.83392 | 0.83598 | 0.83763 | 0.84075 | 0.84526 | 0.85006 | 0.8541 | 0.85663 | 0.86101 | 0.86425 | 0.86624 | 0.86883 | 0.86997 | 0.87308 | 0.87523
Run Running Avg. | 0.93936 | 0.92933 | 0.89868 | 0.91915 | 0.93075 | 0.9223 | 0.92702 | 0.92538 | 0.92423 | 0.92638 | 0.92612 | 0 | 0 | 0.16837 | 0.39482 | 0.50331 | 0.58021 | 0.62323 | 0.65981 | 0.67583 | 0.69517 | 0.72075 | 0.73779 | 0.75342 | 0.76675 | 0.77499 | 0.7803 | 0.96702 | 0.95978 | 0.96578 | 0.96889 | 0.96362 | 0.96748 | 0.96659 | 0.96292 | 0.96345 | 0.95698 | 0.95896 | 0.96027
Ion source 13MHz breaker trips & source failure
IRP Leak
1.0 MW (T16)
1.2 MW (T15)
1.2 MW (T17)
2017A Winter
Outage
2017B Summer Outage

## Slide 8: FY18 continued with excellent performance (93.5%)
Chart: NP availability by week, FY18-1
| 43010 | 43017 | 43024 | 43031 | 43038 | 43045 | 43052 | 43059 | 43066 | 43073 | 43080 | 43087 | 43094 | 43101 | 43108 | 43115
Neutron Beam % Available | 0.90672 | 0.86726 | 0.97628 | 0.95831 | 0.94921 | 0.92766 | 0.94364 | 0.956 | 0
Commitment to DOE | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
FY running Avg. | 0.90672 | 0.8842 | 0.91736 | 0.92832 | 0.93271 | 0.93184 | 0.93359 | 0.9346
Run Running Avg. | 0.90672 | 0.8842 | 0.91736 | 0.92832 | 0.93271 | 0.93184 | 0.93359 | 0.9346
Feeder 2074 trip
1.2 MW (T18)
2017C Fall Outage
2018A Winter Outage

## Slide 9: Energy and power on target from October 2006
Delivered ~40.5 GW-hrs to IRP-01
FY13 – 3848 MW-hrs
FY14 – 4798 MW-hrs
FY15 – 4612 MW-hrs
FY16 – 5348 MW-hrs
FY17 – 5406 MW-hrs
FY18 – 1260 MW-hrs
IRP Changeout

## Slide 10: Long duration events dominate overall downtime numbers Less than 3 hour trips are ~3% of downtime
2017A Outage
FY17
Run 1
2017B Outage
2017C Outage & GIS COMMISSIONING
FY17
Run 2
FY17
Run 3
FY18
Run 1
SCHEDULED TARGET CHANGE
IRP water leak
Switchgear failure
Ion source
SCL CM17
HVCM
failure

## Slide 11: Short duration trip rate of ~2.5 trips/day in FY17 Individual cavity faults affect FY18-1 rate
2017A Outage
FY17
Run 1
2017B Outage
2017C Outage & GIS COMMISSIONING
FY17
Run 2
FY17
Run 3
FY18
Run 1
SCHEDULED TARGET CHANGE
IRP water leak
RFQ cavity instability
HVCM instabilities
HVCM instabilities

## Slide 12: Medium duration rates are fairly constant
2017A Outage
FY17
Run 1
2017B Outage
2017C Outage & GIS COMMISSIONING
FY17
Run 2
FY17
Run 3
FY18
Run 1
SCHEDULED TARGET CHANGE
IRP water leak
HVCM
Ion source

## Slide 13: Long duration trips for FY18 are excellent (so far) Strive for 1 trip every 2 weeks
2017A Outage
FY17
Run 1
2017B Outage
2017C Outage & GIS COMMISSIONING
FY17
Run 2
FY17
Run 3
FY18
Run 1
SCHEDULED TARGET CHANGE
IRP water leak
Multiple HVCM
failures
Ion source
SCL CM17

## Slide 14: Continue to monitor errant beam trips Individual equipment issues significantly affect trip rate
2017A Outage
FY17
Run 1
2017B Outage
2017C Outage & GIS COMMISSIONING
FY17
Run 2
FY17
Run 3
FY18
Run 1
SCHEDULED TARGET CHANGE
IRP water leak
DTL5 RF window arcing
Lightning induced MPS trips
Beam tuning

## Slide 15: Continue to make good progress on reducing number of short trips Also beginning to see a marked reduction in resettable RF cavity trips
Errant beam, magnet ps
SCL cavity trips
Warm linac cavity trips
Requires tech expert or repair (call-in)

## Slide 16: Excellent downtimes excluding IRP leak (353.6 hours)
Chart: FY17 & FY18-1 Downtime by System
| E-HVCM | Ion Source | RF | E-MagPS | CM/SRF | E-other | Controls | Cooling | Fac./Mech. Sys. | Prot. Sys. | Target | Vacuum | AP | Ops | BI | Misc./Mag/RS/ESH
FY17 | 100.8 | 67.3 | 45.5 | 45.4 | 40.9 | 25.7 | 27.7 | 10.9 | 6.8 | 6.2 | 3.3 | 1.6 | 1.2 | 1.2 | 0.4 | 0.3
FY18-1 | 16.3 | 0.8 | 13.8 | 6.4 | 6.9 | 18.1 | 3.1 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0

## Slide 17: Dreaming of how good it could be…..
Downtime hour level for
95% availability
Downtime hour level for
90% availability
Minimum runtime 16 days
Average runtime 27 days

## Slide 18: Summary
Execution of the target management plan has resulted in predictable operations
Excellent availability in FY17 (excluding IRP leak) and FY18-Q1
Long downtime events continue to be impactful
We continue to measure our performance and make system improvements as you will hear over the next two days