## Slide 1: SNS 2018 AAC/TAC Outbrief
Rod Gerig / John Haines Chairs
May 17, 2018

## Slide 2: 2018 AAC/TAC Close Out
All SNS accelerator and target-related activities over the next two years are aimed at two key objectives:
Objective A: By the end of FY 2018, achieve sustainable and predictable routine operation at or near 1.4 MW to the First Target Station (FTS) with availability against published schedule of ≥ 90% while using up to 3 target vessels per year
Objective B: Enable success of the Proton Power Upgrade project by providing key technical and management resources as required to meet project objectives

## Slide 3: Topic: Management
Since the last AAC meeting there has been a reorganization within NScD. There are minor organizational changes impacting accelerator and target systems, and new Division Directors in Research Accelerator Division (Fulvia Pilat) and Neutron Technologies Division (Graeme Murdoch).
The committee expresses its thanks and appreciation to the outgoing directors, Kevin Jones and Don Abercrombie for their support to this committee over the past years.

## Slide 4: Topic: Operations
Since the last meeting the SNS team has continued to achieve sustained operations with beam powers between 1.0 and 1.2 MW.
In FY17 6,079 operating hours were achieved, with 4,807 hours delivered to the user community (exceeding the target of 4,230 hours). Availability was 87.5, but would have been 94% excluding the IRP water leak. So far FY18 has continued with excellent performance (93.5%) for Q1.
Long duration events dominate overall downtime numbers. The aspiration is to eliminate events such as the MEBT water leak, IRP water leak and target failures, which would leave a residual downtime per month of ~45±25 hours – equivalent to ~94±3% availability (and easily sufficient to achieve the ≥90% availability required to meet Objective A).

## Slide 5: Topic: Operations (continued)
Progress is still being made in year-on-year reduction in the number of short trips and SCL cavity trips, supported by appropriate AIP and spares initiatives. This all appears to be in very good order.
The five month long outage (December 2017 – May 2018) was very effectively managed and has prepared SNS for 1.4 MW operations, with most issues identified at the last meeting having been addressed.
Recommendations:
Keep producing and analysing the high quality performance metrics that have proved so useful up to now.

## Slide 6: Charge Question 2: Do the capability and performance of the accelerator complex and neutron source support achieving Objective A?
Since the last meeting the work carried out in the long outage, alongside other technical developments, has produced a step-change in the present capability of the SNS accelerator. This is the most significant advance in recent years.
Prior to the five month long outage the accelerator was already capable of meeting Objective A, but with very little operational margin. However, improvements have now been made to remove the bottlenecks of poor RFQ efficiency and the SCL being operated below design energy, enabling accelerator capability of 1.7 MW, and therefore considerable margin for 1.4 MW operations.
The installation of the new RFQ is particularly significant (increasing transmission from ~75% to >90%) and meets a long-standing recommendation of the AAC. The AAC hopes that performance continues to be as good as the early measurements indicate. Whether spares provision for the RFQ is desirable or essential remains to be addressed.

## Slide 7: Charge Question 2: Do the capability and performance of the accelerator complex and neutron source support achieving Objective A?
As recommended last year there has been a review of key reliability issues, ageing components and single point vulnerabilities, and progress has been made in addressing many of these (e.g. HVCM upgrades, RF system upgrades, improvement in ion source performance, installation of a new LEBT gate valve, development of a spare medium beta cavity and improvement of the injection foils and electron catcher).
From the accelerator point of view the answer to the charge question regarding Objective A has moved on from a ‘yes, but…’ to a ‘yes!’
Recommendations:
Monitor RFQ performance for any deterioration at full operational parameters.
Give due consideration to RFQ spares provision.

## Slide 8: Charge Question 4: Is the scope of work identified for ongoing and future Accelerator Improvement Projects (AIP) appropriate and balanced between the competing interests of maintaining necessary margin for routine operation at 1.4 MW while addressing system obsolescence?
AIPs shifted from addressing design problems to ensuring reliable operations at 1.4MW. Obsolescence issues have started to impact reliable operations
Obsolescence can be a difficult issue to quantify. Want to be good stewards of the machine, but unless an old system is demonstrably causing problems it can be difficult to justify resources
The idea to quantify and model failure rates is a good
The balance between the competing interests of maintaining necessary margin for routine operation at 1.4 MW while addressing system obsolescence seems fair.
Prioritization formula attempts to balance competing factors
Recommend all projects go through prioritization process. Those that rise high enough and that fit AIP rules should use AIP funding
Annual rate of $4M - $5M for infrastructure investment seems reasonable

## Slide 9: Topic: Outage Planning
Since the last AAC meeting, SNS has undergone planning and execution of three outages: 2017B (summer of 2017), 2017C (October 2017), and 2018A (long outage starting December 2017).
SNS is continuing to use the prioritization and outage planning process which was developed and initially implemented in 2016. The intent was to have a process which is more quantitative and integrates overall facility activities. The process continues to be as described last year, but is clearly evolving from “this is what we’re developing as a tool” to “this is our tool”.
A high-level block schedule continues to be used effectively and anywhere from 300 to 1465 tasks have been tracked in an outage.
The outage planning tool is moving from MS Project to Primavera (P6) and a permanent planner has been put in place; further indications that this process is maturing into a robust tool that will be flexible and scalable to the length and scope of each outage.

## Slide 10: Topic: Outage Planning (continued)
The process continues to improve, with Lessons Learned from SNS’s first long outage having been identified:
  Distribute priority projects early to allow for proper identification of all needed resources
  Put in start-up tasks at the beginning for logic linking
  Evaluate logic as it is entered
  Attempt some amount of resource leveling at the beginning
  Continue to educate planners/task leaders/team leaders on scheduling techniques
The committee encourages implementation of identified improvements of the outage planning process.

## Slide 11: Charge Question 3: Is the Prioritization process and Project Planning strategy that has been developed and is in use for outage planning reasonable?
Yes, the prioritization process and planning strategy has clearly matured and been refined since the last AAC meeting.
Re-iterating comments from Operations: The five month long outage (December 2017 – May 2018) was very effectively managed and has prepared SNS for 1.4 MW operations, with most issues identified at the last meeting having been addressed.
Recommendations:
Continue to implement and refine the outage planning process as it was developed. This should include implementing lessons learned identified from the long winter outage.
Continue to review the effectiveness of the “three outages per year” operating strategy at regular intervals to ensure it remains optimal.

## Slide 12: Topic: BTF, Ion Source, and RFQ
Beam Test Facility
The beam test facility (BTF) has proven itself and its continue use should be encouraged. The BTF offers continued improvement to operations and beam physics.
The BTF played a critical role in verification and testing the new RFQ for operations. In addition, verification of external ion source beam performance, testing of injection diagnostics, controls and beam simulations has and will continue to benefit from the BTF. With the old RFQ being installed the test facility will be focused on beam physics and other upgrade ideas.
Planned BTF subjects include the high dimensionality beam dynamics (HDBD) and laser diagnostics. The novel and one of a kind HDBD deployment and extension planned for this summer offers long term beam physics options. Additionally, laser diagnostics testing and development in the controlled BTF environment is a good plan.

## Slide 13: Topic: BTF, Ion Source, and RFQ
Ion Source
This past year (FY17) has been very productive for both ion source development and operations.
The ion source has taken advantage of target and other outages to replace sources as to not incur downtime.
Development of the external RF antenna looks to be a viable replacement of the internal version. Shown lifetimes exceeding 100 days and currents capable of meeting PPU needs. The external RF antenna will eliminate a vulnerability and critical to the viability of SNS operations. The effort to make this the operational system should be a priority.
ISTS remains a critical part of operational reliability and supplements the BTF with flexibility of dedicated ion source work.

## Slide 14: Topic: BTF, Ion Source, and RFQ
RFQ
The committee again congratulates SNS for the successful installment and startup of the new RFQ! Operating time will now determine long stability. It is hoped that after a year or two should provide the needed data proving a successful RFQ design.
Recommendations:
Make room available to the BTF to fully utilize its potential. This BTF offers the possibility to expand SNS beam physics, collaboration and outside funding contributions.
Move SNS operations to the external antenna as soon as reasonably possible to benefit of longer lifetime and remove vulnerability. This new design will not only benefit SNS but the community.
Consider ordering an RFQ spare after verification of performance to guarantee long term operations..

## Slide 15: Topic: Linac Beam Dynamics: Measurement and Simulation
SNS has developed two simulation codes for the linac: “OpenXAL Online Model” and “PyORBIT”.
“Open XAL online model” is an envelope code and part of the Open XAL framework. The speed is faster and superior to Trace3D. The major specification is Open Source, and there are areas for improvement which SNS is addressing.
The OpenXAL model shows a great success for the SNS linac tuning up. The RF setup is automated and it takes 22 minute for 14 cavities linac, and 40 minutes for 81 superconducting cavities. It has flexible features, for example, if one SC cavity fails or changes the amplitude, the cavity is retuned without rescan.

## Slide 16: Topic: Linac Beam Dynamics: Measurement and Simulation
SNS has also developed a linac PIC code, PyORBIT, which is an extended Python interpreter. The source is open and extendable. It can be added new physics and new diagnostics, etc. It shows good benchmark results with conventional PARMILA code. It is used as an online model for the Beam Test Facility.
The committee appreciates the great success of the fast tuning by the Open XAL. The committee supports the continuous development of these codes. Further benchmark tests of PyORBIT are suggested for validation.

## Slide 17: Topic: Superconducting Linac / SRF
A 98% availability of the SCL during the past 7 years was reported. This proves a very high reliability of the cryomodules and its subsystems. The committee congratulates the SCL team to the very good operating performance.
The success of the plasma processing was reported already in the last ACC meeting. Since then, the performances of five additional high beta cryomodules have been improved. Plasma processing is the major contribution to the now possible 1GeV beam operation. The AAC supports the development of a new recipe for the use of this successful tool also for medium beta cavities.
Thanks to the availability of the spare high beta cryomodule, the leaky cryomodule in slot 17 could be replaced in January 2018. This supports the usefulness of spare cryomodules.

## Slide 18: Topic: Superconducting Linac / SRF
The construction of the spare medium beta cryomodule is progressing. We are happy to hear that the accelerating gradient and quality factor of the first fully equipped tested cavity is very high and exceeds already the PPU specification. The cold string assembly will start in summer this year. The development and construction of the spare cryomodule will not only support the future high performance and availability of the SCL, but will also function as an important development step for the future PPU.
The design improvements of the cavity and cryomodule for the PPU which have been reported in this meeting gain the full support of the AAC.
Besides the necessary R&D program goals for the PPU, the AAC supports the plans to investigate the ex-situ plasma processing and exploring innovative techniques to probe SRF surfaces.

## Slide 19: Topic: Superconducting Linac / SRF
Recommendations
In order to assure the full use of the SCL test facility during the PPU construction e.g. for power coupler testing and conditioning, the use of the RF power source independently from the beam test facility is necessary. We recommend a dedicated HVCM for the SCL test facility klystron.
To comply with the R&D goal to probe SRF surfaces, a clean chemistry bench for BCP and EP sample treatment is recommended.

## Slide 20: Topic: The R&D Plan
An impressive R&D program is being carried out by Beam Science and Technology group. Many of the topics are first in the accelerator community, like 6-d emittance, self consistence beam distribution, laser stripping injection, foil for high power injections, high power SRF (plasma cleaning), non-destructive high dynamics range beam diagnostics, laser for pulse muSR beam pulse shaping.
SNS is leveraging unique technological strengths to engage in these high impact R&D: like highest power beam in world, highest intensity proton ring, only hadron SCL, only 6D measurement system.
The committee encourages SNS to continue highly visible R&D program running. It will be a important and productive service to the accelerator community.

## Slide 21: Topic: Ring Stripper Foil R&D
Stripper foil development program is design to addressing issues with foil conditioning, predictability, and life time and is making a significant progress, CNMS foil#3073 ran for 2448 MW-Hr at 1.2 MW.
The Foil test stand uses pulsed rastered 30 keV, 5mA electron beam with 0.3 mm^2 spot size to simulate 2.8 MW equivalent heat loads to study different type foils.
A new removable electron catcher is designed with larger viewport and is movable and allows different electron catcher geometries. A tentative plan is to install it during winter 2018 outage. A method for verification of the final position of the electron catcher must be developed.
Recommendations
A figure of merit for charge exchange foil must developed for 2.8 MW beam power.

## Slide 22: Topic: Ring R&D: Laser Stripping
Laser stripping is a very promising basic research carried out by SNS. It will have significant impact on the accelerator community. Last year progress included a demonstration of a large mode optical cavity for enhancement of UV laser pulses in burst-mode and identification of technical challenges toward full-cycle (1.0-ms/60-Hz) green (nm 532nm) laser stripping. SNS is making significant progress to maintain this research. The committee views this as very important research for the accelerator community. We encourage the SNS to support this work at an appropriate level after the present grant runs out in July, 2018.

## Slide 23: Topic: Self Consistent Beam Distribution
The committee heard very promising progress about resolving several key issues like fringe field, bi-polar power supply and understanding of painting and injection kicker limitations, sensitivity of solenoids and, tunes. Specification of requirements to realize self-consistent beam is complete. Next step will be the design, fabrication and installation of solenoids, confirmation of the lattice settings, painting waveforms, and the measurement of the correlation coefficients between phase space variables. It will be interesting to check 4-D emittances for the rotating beams.

## Slide 24: Charge Question 5: Is the Accelerator R&D plan presented appropriately positioned to widen collaborations and to leverage external resource support?
The accelerator R&D plan is focused on areas of both facility need, and technological strengths at SNS: high power, high intensity, and SCLs.
The R&D program is experimentally focused and includes a number of novel technologies that are broadly applicable to the community and therefore are good candidates for external funding and for collaborations with other hadron accelerators (Fermilab, Los Alamos, BNL).
The SNS team has been aggressive and quite successful in pursuing external funding. However these resources are shrinking and the competition for these limited resources is fierce.

## Slide 25: Charge Question 5: Is the Accelerator R&D plan presented appropriately positioned to widen collaborations and to leverage external resource support?
It is therefore important that the NScD directorate support the R&D internally between external funding cycles, as it is not likely that projects will be funded on a continuous basis and it is important to maintain momentum.
As the only accelerator based directorate at ORNL it is important that NScD champion the important field of accelerator R&D as an ORNL strategic area, allowing and encouraging LDRD proposals. In addition to providing some needed money, it is vital to show laboratory support to to draw future external funding once the initial internal investment is made.
Recommendation:
The committee recommends that NScD advocate for a strategic ORNL initiative in Accelerator R&D.

## Slide 26: Topic: Target Status and Plans
The Target Management Plan (TMP) provides a roadmap for developing and implementing target improvements aimed at satisfying current operational goals (2 targets per year at 1.4 MW) as well as providing information critical to the development of 2.0 MW capable targets needed for PPU
  The team is commended for creating such a document and utilizing it to focus development as well as operational efforts
Successful replacement of the first IRP is a major achievement, but until IRP3 is delivered, failure of this complicated, inaccessible, highly stressed, and intensely irradiated system will represent a single-point-of-failure risk with a multi-year impact for the SNS science program
Recommendation:
The IRP design and associated manufacturing initiative should be given high priority by Directorate management to deliver IRP3 on a reasonable time scale

## Slide 27: Charge Question 7: Is the SNS Target Management Plan a reasonable approach to improving both performance and understanding of SNS mercury targets?
Yes, besides serving the purpose of focusing efforts on this area that is so critical to the success of SNS operations as well as the PPU Project, it integrates efforts across the Directorate, i.e. integrates and balances target development goals with machine operations (RAD) and science program goals.
Recommendation:
Continue to evaluate and revise the plan on a regular basis as new information is learned

## Slide 28: Charge Question 2: Do the capability and performance of the accelerator complex and neutron source support achieving Objective A?
Considerable progress is being made in developing targets and it appears that they are on track to meet Objective A (1.4 MW, > 90% availability, 3 target replacements/a) by the end of 2018

## Slide 29: Topic: Target Systems – IRP Operation, Fabrication and Development
A leak in IRP-1 complicated operations prior to the long shutdown. The engineering team developed a creative solution that allowed operations to continue until IRP-2 was ready. Kudos!
IRP-2 fabrication was completed by the vendor, the first time this has happened. However, fabricating the IRP continues to be a complicated and difficult task with little schedule predictability.
A new approach is proposed to manufacture and leak check the IRP in stages, completing components along the way, then assembling at the end, which allows for leak repair in a more efficient manner.
Steps were taken to lengthen the life of IRP-2, and to further lengthen the life of IRP-3.
Recommendations:
Look at all issues which may determine the lifetime of the IRP, not just the moderator poison thickness.

## Slide 30: Charge Question 8: Have lessons learned from the IRP-01 and IRP-02 experiences been adequately considered in the design and fabrication plan of the next-generation IRP (IRP-03)?
Yes. Numerous issues with IRP-1 operation and IRP-2 fabrication and installation have been identified and have been accounted for in the design and approach to IRP-3. These include moderator welding, alignment issues, cadmium spraying, pipe chases added back in from the IRP-1 design, elimination of right angles on the cryo moderator lines (mitre bends), etc. Most importantly, the approach to IRP-3 has identified the difficulty in fabrication and is addressing it by building components in stages and assembling at the end, either on site or at a vendor.

## Slide 31: Topic: Target Systems - Target Manufacturing and Procurement
SNS routinely makes targets, IRPs, and PBWs. These are part of the normal operation of the facility, but the targets are also part of a major deliverable for PPU.
The average annual cost for 3 targets/year, one IRP every 4 years, and one PBW every other year is approximately $7M. This is just the hardware cost.
  This funding level will be required to achieve operational goals
SNS currently has one original style spare target, with 8 on order in various stages.
Target delivery is slipping routinely, costs are rising, and vendors are less likely to bid on new targets.
SNS is starting a pilot target manufacturing program to improve the process and improve program control by breaking orders into components to widen the vendor pool and reduce risk.

## Slide 32: Charge Question 9: Is the major procurement planning sufficient for controlling long term cost and improving component manufacturing reliability?
SNS procurement planning is sufficient to ensure improvement of component manufacturing reliability. However, as only a very limited number of target suppliers with adequate manufacturing skills are available on the market, it is nearly impossible to control the long term target costs. A reasonable approach could be to seriously consider a production of the target in house or at least parts of it. Even if this means extra investment in the near-term, we are convinced that it will pay off over the longer term.
Another approach might be to award incentive-type contracts for the target vendor based on succeeding in delivering the required quality in due time.
Recommendations:
Ensure the target, IRP, and PBW manufacturing program is successful by providing the required resources
Consider ways to leverage ORNL expertise to support the success of SNS and PPU, such as leveraging advanced manufacturing for complicated target components

## Slide 33: Topic: Target Operations
The IRP leak was the major contributor to unavailability in 2017, while stable operation of the target at 1.2 MW was achieved without any major problems giving confidence for the planned power increase to 1.3 MW and 1.4 MW
The SDE team is extremely capable and has developed many new, highly effective improvements aimed at increasing the reliability of target operation at high power levels.
Because sometimes more than one improvement is introduced to a new target it is difficult to distinguish which improvement has had the biggest impact. Therefore, introducing fewer changes/improvements per target, especially as long as three targets are utilized per year, should be considered
The comprehensive PIE of spent targets is an extremely useful tool to determine the effectiveness of newly implemented design changes. By now it can be done on a nearly routine basis, which is very impressive. This is unparalleled among all major spallation neutron sources.

## Slide 34: Topic: Target Operations (continued)
The team has successfully developed a robotic-based laser scanning system for inspecting samples from spent targets
Blockage of the orifice openings in gas injection systems utilizing this concept has significantly reduced the capability to inject gas into the mercury
Recommendations:
A robot based laser scanner for determining the thickness of the walls of the target nose is very useful improvement and should be utilized in the service bay
The flowrate of the orifice gas injection system should be checked at the manufacturer prior to shipment to SNS in order to be corrected if some blockage has occurred

## Slide 35: Topic: Target Systems – Remote Handling
The team responsible for the remote handling system development and operations is working very professionally. All major steps of non-routine operations are practiced in mock-ups and optimized in order to ensure maximum safety to the workers and optimal results.
With successful completion of the first IRP replacement, they now have a proven record in all major planned remote handling operations
Photo-neutrons emitted by the beryllium reflector within the spent IRP led to excessive background on the detectors of a nearby instrument. Measures were expeditiously taken to minimize the impact using spare shielding materials
Recommendation:
A new exchange flask for the lower part of IRP should be designed in such a way that photo-neutrons coming from the reflector material are better shielded

## Slide 36: Topic: Target Systems – Mercury Target Engineering
7 of 18 targets have developed mercury leaks in service, necessitating unplanned replacement and facility down-time. It should be noted that three of these targets exceeded nominal lifetime expectations, but were intentionally run to end-of-life.
Leaks are caused by fatigue failure due to high-cycle pressure waves and low cycle thermal loading, which in some cases appeared to be aggravated by mercury cavitation erosion of surfaces
The Target Management Plan has provided reliable operation for SNS users, and key operational data on target performance. The mercury target engineering team still faces challenges, but is moving forward in a determined and deliberate fashion
Strain reduction was achieved with even low gas flow rate. Injection of more gas could lead to further strain mitigation. Consider the relationship between the bubbler position and the bubble distribution in the flowing mercury.
High radiation dose rates were observed at the mercury pump. Understand why, in particular, from the viewpoint of safety. Consider the effect of accumulated gas somewhere in the loop as well.

## Slide 37: Topic: Target Systems – Mercury Target Engineering (continued)
It is good news that gas injection also appears to have mitigated cavitation, and no cracks.
Collaboration with numerical simulation experts to understand the interaction between bubbles, pressure waves and elastic deformation of the vessel should be pursued.
The surprising erosion observed in the T16 jet-flow target suggests that locally high velocity led to unexpectedly high erosion. Understanding the erosion mechanism for this target would be very helpful in informing both incremental improvements needed to sustain reliable operations and to develop PPU targets
Recommendation:
Make effort to understand the mechanism of the erosion in the case of T16 jet-flow target

## Slide 38: Topic: Target Systems – Target Gas Injection
Very promising results were obtained with the Swirl Bubblers in off-line tests. Pressure drop is acceptable and bubble size generated is smaller than expected.
Collaborate with J-PARC team. They developed a 2-vane bubbler which indicates lower pressure drop as compared with a 4-vane bubbler.
Swirl bubbler is ready for operation and only fabrication details need to be set. Check the mechanical properties if 3D printing is used.
Experimental and numerical results for the gas wall layer show encouraging progress. Sustain these experimental and numerical analysis activities to explore more suitable conditions.
Pursue a ramp-up in the gas flow rate that is more rapid than the currently planned ramp-up schedule.
Consider flow erosion by the jet-flow with gas. Consider using the TTF loop to demonstrate no-effect.
Recommendation:
Continue to collaborate with the J-PARC team, particularly in the area of vane bubbler development

## Slide 39: Charge Question 10: Is the proposal for early use of the 2 MW PPU target in operations reasonable?
A qualified Yes:
  The PPU target design is moving from conceptual to preliminary design level. It is not clear which design features beyond those already identified in the TMP can be explored during early operation
  The preceding 1.4 MW target design iterations (chinstrap +) are unknown and may not converge with the chosen PPU target design. If PPU design presents a large departure, risk to operations may be greater and separate effects analysis may be complicated
With the above caveat, the cons presented appear to be manageable (so there is little down-side)
A strategy to make this decision should include documenting what design features and manufacturing prototyping questions can be explored (beyond the current TMP) with early operation versus what cannot be explored with early operation.
  E.g. Effect of tapered nose can be explored, but gas-wall cannot.

## Slide 40: Topic: Target Systems – PIE
The PIE team is commended for achieving impressive work over the past year. The results continue to be the best validation of target development efforts. Management has fully supported the PIE efforts.
8 activities performed on each target routinely now
After the Hg flow velocity was increased (T13 and on), no center baffle cracks have been found
T16 jet flow showed no pitting in corners. But higher vertical “striping” and greater erosion damage in center region of inner window
T17 had 1/3 thickness deep pits in corners. Conjecture: once a pit starts, it erodes at a faster rate.

## Slide 41: Topic: Target Systems – PIE (continued)
A robot arm added to scanning system which eliminates dose and may result in higher quality scans.
  This is very good application using newly available commercial technology
Inconel 718 PBW tensile testing with DIC shows 10% elongation after up to 10 DPA. Does not agree with other data. Is decay heat affecting properties?
Sampling Aluminum PBW is encouraged, especially with the results from the 718 testing
  Check for corrosion morphology (pitting versus surface)
Recommendations:
None

## Slide 42: Topic: Target Systems – Target Development Plan for 2.0 MW PPU
The general goals of the 2 MW PPU target design include applying the entire set of alternatives currently being explored to reduce fatigue stresses and combat cavitation erosion
  This seems appropriate because it is not yet clear that current results can be extrapolated to higher beam powers and/or higher gas flow rates
  However, it is also currently unknown how some of these mitigation techniques will interfere with each other (one should be cognizant of what features can be easily “turned off”, e.g. gas-injection can be turned off, but jet-flow cannot)
“Better is the enemy of Good Enough”, But what is “Good Enough”?
  Goals for small bubble gas or gas-wall injection are based on WNR testing
  Goals for jet-flow velocities are undetermined
PIE and gas injection studies have been, and continue to be, executed at an extremely high level of competence with promising results
  But, there is not much time for additional studies before PPU 2.0 MW target design finalization

## Slide 43: Topic: Target Systems – Target Development Plan for 2.0 MW PPU (continued)
Current plan for gas wall implementation requires jet-flow in the central nose region. This achieves about a 5 cm wide area for 60% coverage.
  If jet-flow velocity needed for good gas wall coverage is in a range that shows bad results during T16 – 17 operation, will it create increased damage in areas not covered by gas wall?
Recent design studies have confirmed several design features
  E.g. elimination of center baffle (dilatational mode suppression acceptable), pressure drop for swirl bubblers and side baffle holes
Ongoing design studies are aimed at increased nose taper, manufacturability, and alternative gas-wall injection scheme
Automated Design Exploration Activities have been successful in reducing the “minimum of maximum stresses” by 30% in a study of center baffle size and location dimensions
  This is impressive and is a good tool for exploration
  Obviously, once focusing on a particular configuration, be careful of sensitivity to other parameters held constant for the exploration study

## Slide 44: Topic: Target Systems – Target Development Plan for 2.0 MW PPU (continued)
As PIE results and operational experience with the next few iterations of 1.4 MW targets come in, the TMP should be updated considering the PPU 2 MW target final design configuration. The resulting TMP should balance:
  First establish operational robustness for 1.4+ MW operations
  Testing PPU 2 MW target design features and scaling effects
Ideally, the above ”balanced” TMP would result in a 1.4 MW operational target (chinstrap +) capable of running at higher powers as a back-up for the PPU 2MW target
Recommendations:
Continue pursuing all beneficial features in the PPU 2 MW target design, while keeping in mind the potential for interference between the techniques and considering methods to possibly mitigate interference.
After establishing 1.4+ MW reliable operation, proceed with plans for early operation of the PPU 2 MW target before the long shut-down, coordinating and integrating with 1.4 MW operations to achieve a balanced TMP

## Slide 45: Charge Question 11: Do the benefits proposed from the PPU 2 MW target design changes outweigh additional potential complexities?
It is too early to answer this question
  Benefits of the PPU 2 MW design features are not fully understood yet (scaling to higher beam power and higher gas flow rates; combined effects of jet-flow, gas bubbles, and gas wall)
  Consequences of potential complexities not quantifiable yet since early in design phase (cusp of preliminary design)
Should all pressure wave and cavitation damage mitigation techniques, identified thus far, be explored/included in the design of the PPU 2 MW target?
  Given the time constraints and unknowns, Yes.

## Slide 46: Topic: Pulsed Power and Electrical Systems
High Voltage Converter Modulator
HVCM downtime is trending down, ongoing system improvements are increasing operational reliability, demonstrating the efficacy of the evolution of the preventative maintenance activities, e.g. replacing booster caps, primary buss, voltage dividers, …
Full implementation of pulse flattening increases the RF overhead and also reduces the electrical stress, which should ultimately improve HVCM reliability.
Reliability and MTTR is improved by replacing the existing oil cooling system (AIP-36). Interim replacement of the pump motors (prior to upgrade) is improving operational reliability.
The FR3 dielectric fluid is reaching end-of-life and should be replaced in all HVCMs.
The planned upgrade of the IGBT gate drive circuits will have an added benefit of providing a pathway to replacement of discontinued IGBTs.

## Slide 47: Topic: Pulsed Power and Electrical Systems
High Voltage Converter Modulator
The TPC arrays are a promising replacement for the resonant boost capacitors. If successful, the team should consider this approach for SCL HVCMs and the selected PPU modulator topology.
The laminated buss to connect energy storage to the switch plates greatly reduces the parasitic effects of the original coaxial cables and should be introduced as an upgrade to the existing HVCMs.
Alternative Topology (AT-HVCM)
  Eliminates the voltage reversal on the resonant boost capacitor – should significantly increase boost capacitor lifetime.
  The turn-on oscillations have been eliminated with the addition of a by-pass diode.
  The HVCM team should continue to develop the AT-HVCM as the baseline design for the 3 new PPU modulators and select the best topology for the application at the beginning of CY2019 as proposed.

## Slide 48: Topic: Pulsed Power and Electrical Systems
High Voltage Converter Modulator
PPU
  Three additional HVCMs will be required.
  A new HVCM “tune” must be developed for the 3 MW DTL klystrons
  The SCL HVCMs have been demonstrated at the voltage/power required for PPU, data for CCL should be evaluated to determine if higher voltage qualification of this “tune” is required.
  We encourage management to fill the open position for the PPU Power Electronics engineer to alleviate concerns over the additional work load inherent in the PPU scope so the existing team doesn’t lose focus on operational improvements.

## Slide 49: Topic: Pulsed Power and Electrical Systems
RF Systems
On-going replacement of RF circulators is improving operational reliability of RF systems.
The Stewardship Program (ongoing review/revision of operational procedures to enhance component lifetime) (e.g. reducing cooling water flow rates) is improving operational reliability.
Commissioning of the new LLRF system for the ring should be a priority to provide operational experience, as this system will serve as the basis for the PPU LLRF.
On-going purchase of klystron spares is important to assure operational reliability.
Second source replacements for Thales klystrons should be developed, based on SNS operational experience.
PPU will require development of a vendor for 3 MW klystron for DTL.

## Slide 50: Topic: Pulsed Power and Electrical Systems
RF Systems
Recommendation: Operations funds should be provided ASAP to develop 2nd-source for 5 MW klystron.
Recommendation: PPU funds should be provided ASAP to develop source for 3 MW klystron

## Slide 51: Topic: Pulsed Power and Electrical Systems
AC Power Distribution Systems
There is a deficiency of long-lead spares (e.g. transformers) that could lead to extended operational interruption.
ORNL has migrated to a new communications standard for AC power systems (Schneider Electric ION) that is incompatible with much of the SNS infrastructure.
Recommendation: Work with ORNL management to identify funding sources to upgrade SNS infrastructure.
Recommendation: The priority for AC power system upgrades and obsolescence replacements should be evaluated using the project prioritization process to highlight the urgency.

## Slide 52: Topic: Controls
Work on CS-Studio (CSS) continues. Decision to proceed without the use of the Eclipse framework is notable, should remove many of the barriers to adoption. Good to see collaboration with other developers. We encourage continued development.
Much work completed since last year. The completion of the remediation program for the PPS grounding issue on the accelerator is notable.
From a facility-wide perspective, it is good to see Controls expertise being used to address some beamline improvements, for example standardization of vacuum controls.
Much work planned by the facility will involve, and be dependent, upon Controls. Prudent to assess the level of staffing for EPICS application and Software application required.

## Slide 53: Topic: Controls
Faster data rates from instrumentation will stress current network infrastructure. Most new devices are network attached, there will be many more devices on the network in the coming years.
Recommendation: Look at network requirements post PPU and start to invest in upgrade of capability. Skimping on network infrastructure will be a false economy.

## Slide 54: Topic: Diagnostics
The committee was pleased to hear progress for replacement of BPM and BLM electronics under AIP-37 due to obsolescence and encourage to continue for other diagnostics. The new BPM electronics is capable of data acquisition at rate of 60 Hz instead of 1 Hz. This will open up many new possibilities for diagnostics.
A foil temperature measurement system being developed. It is important to measure the stripper foil temperature at present operating currents and necessary to predict foil life time. Measurements using thermal imaging are promising and are encouraged.
The committee congratulates for pioneering work of 6D measurements of the beam at Beam Test Facility and encourage further refine the data taking process.
Group is over subscribed, consider ways of looking adding to this group approaching the PPU.

## Slide 55: Topic: Proton Power Upgrade
STS Project activities were suspended in June 2017 to focus on PPU
CD-1 was approved by DOE in March 2018 with $36M funding.
The project is pursuing long lead items.
The project has begun to identify key people for project positions. Given the early stage of the project (i.e., pre CD-2) the staff remains largely matrixed, but project and PPU management are discussing transitions and allocation of effort. Posting for project positions have been made. Effective matrixing of the SNS staff such that both operations and the project can effectively be done, but must be reevaluated annually as funding availability is made known. (Objective B)
The recent 2018A shutdown was a good step forward in using Primavera scheduling tools to manage work and help prepare the organization for PPU work.

## Slide 56: Topic: Proton Power Upgrade
It was reported that the PPU has a proposed KPP that requires achievement of “Target operational time without failure of 1,250 hours at 1.7 MW”
  Having such an operational goal required before project completion appears to unnecessarily impose a serious risk to success; any difficulties encountered in operation, even those unrelated to the target or even any of the equipment included in the PPU project, would lead to a delayed project completion and additional project costs.

## Slide 57: Charge Question 6: Are the PPU pre-CD-2 activities properly focused?
YES – development work is proceeding
  A number of the development items have been covered in the talks in those areas. This includes SRF, power systems, foil development, controls and targets.
The project has identified and is pursuing long lead procurement items.
Project is in process of contracting an AE firm to assist in planning the klystron gallery equipment layout (3D model).

## Slide 58: Charge Question 1: Are the SNS responses and ongoing actions to recommendations from the 2017 AAC meeting satisfactory?
The SNS has been very responsive to last year’s recommendations. The committee is pleased to see the progress that has been made. The one recommendation presented as “unclosed”, the spare medium beta cryomodule, has received funding and work has begun.