## Slide 1: Status and development in the Integrated Control System project at ESS
Henrik Carling
ESS/ICS
Date: 2016-09-20

## Slide 2: ESS is an European collaboration project
Host Countries of Sweden and Denmark
47,5% Construction 15% Operations
In-kind Deliverables ~3%
Cash Investment ~97%
Non Host Member Countries
52,5% Construction
85% Operations
In-kind Deliverables ~ 70%
Cash Investment ~ 30%

## Slide 3: ESS is a pulsed neutron source
Proton Accelerator
Energy: 2 GeV
Pulse rate: 14 Hz
Current: 62.5 mA
Neutron Instruments
16 instruments in c-budget
22 instruments by 2028
Target Station
Rotating W target
He-gas cooled
5 MW average power
42 beam ports
Control system
EPICS based
About 1.5 Mpv
MPS with fast BI-system

## Slide 4: ESS Timeline
4
2014
Construction work starts on the site
2009
Decision: ESS will be built in Lund
2025
ESS construction complete
2003
First European design effort of ESS completed
2012
ESS Design Update phase complete
2019
First beam on target
2023
ESS starts
user program
2067
Decommissioning

## Slide 5: ICS Project scope
Work package 01 Management and administration
Work package 02 Software Applications
Work package 03 Software core
Work package 04 Hardware core
Work package 05 Machine protection
Work package 06 Equipment
Work package 07 Control system infrastructure
Work package 08 Physics
Work package 09 Personnel safety systems
Work package 10 Integration - Accelerator
Work package 11 Integration - Target
Work package 12 Integration - Instruments
Work package 13 Integration - Conventional facilities
Work package 14 Test Stands
Work package 20 Installation
Software
Electronics
Infrastructure
Safety & protection

## Slide 6: ICS Organization 2016-09-01
Henrik Carling
Division head
Anna Gillberg
Team assistant
Annika Nordt Safety and protection
Daniel Piso
Hardware and integration
Hector Novella
Deputy project manager
Susanne Regnell
Control Software
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Karin Rathsman Senior scientist
Leandro Fernandez Senior software engineer
Ricardo Fernandes Senior software engineer
Claudio Rosati
Software engineer
Javier Cerejo PhD Student
Angel Monera
FPGA Engineer
Denis Paulic
PLC Engineer
Manuel Zaera-Sanz
PLC Engineer
Morteza Mansouri
Safety Engineer
Riccard Andersson PhD student
Stuart Birch Senior safety engineer
Ben Folsom
PhD student
Remy Mudingay Infrastructure engineer
Thilo Friedrich
PhD Student
Temporary employee
Employee
Consultant
Consultant off-site
Nick Levchenko
Integrator
Benedetto Gallese
Integrator
Yong Kian Sin IEC61508 engineer
François Bellorini
Integrator
David Brodrick
Integrator
?
IT/Infrastructure ?
(Vacant?)
Position under consideration
Alexander Söderqvist
Integrator
Niklas Claesson Integrator
Jeong Han Lee Integrator
Consultants
Julen Etxeberria
Intern
Open positions (4)
Open positions (2)
Open positions (2)
In-kind project manager
Simone Farina Embedded systems egineer
Technical Coordinator (6 months)

## Slide 7: ICS - construction phase value envelope (tentative)
The ICS value envelope for the construction phase shows the aggressive project schedule
A majority of the ICS value is labor based effort (i.e. not equipment)
The ICS estimated headcount envelope reveals large in-kind/supplier opportunities
2016 2017 2018 2019

## Slide 8: ESS In-kind contributions
A non-cash contribution by a Member Country to ESS
In the form of:
Technical components for the facility (also personnel needed to perform the testing, installation and/or integration)
R&D work (also personnel needed to perform the work)
Personnel made available for specific tasks during the construction phase
Other products and services relevant for the completion of the facility
A large portion of the ICS budget is allocated as In-kind contributions
The following statements define an In-kind contribution
The in-kind contribution model constitutes an enormous challenge for ESS in general and ICS in particular

## Slide 9: ICS In-kind partners
Agreement signed
Agreement waiting for signature
Early discussions
Collaboration agreement
Partner Institutes
Atomki, Hungary
CEA, France
CNRS, France
Elettra, Italy
ESS Bilbao, Spain
IFE, Norway
INFN Catania, Italy
INFN Legnaro, Italy
PSI, Switzerland
Tallinn Technical University, Estonia
ÚJV Řež, Czech Republic
University of Łódź , Poland
Uppsala University, Sweden
ZHAW, Switzerland

## Slide 10: ICS Software scope
Controls configuration tools
  Controls Configuration Database (CCDB)
  Naming Server for naming convention
  Cable Database (CDB)
  IOC Factory
  CS Entry
  Role Based Access Control (RBAC)
Clients
  Alarm Handling
  E-logbook
  Archiving System
  Save, Compare & Restore
  Scenario management
  GUI/HMI (Control System Studio)
Core controls software
  Development/contributions to core EPICS
  Timing applications
  Post-mortem diagnostics
Operation tools – Scripting frameworks
  iPython
  Scripting Execution Environment
  Macroserver
Software development environment
  Vagrant for virtualization
  Ansible for automation of deployment and configuration of our software infrastructure
  Jenkins for continuous integration support
Physics modelling
  Open XAL
  ESS Linac Simulator
  Beam Physics Applications

## Slide 11: ICS hardware strategy
ICS has adopted a three layer strategy for implementing the control system based on signal speed
  A custom made platform based on microTCA for applications with data acquisition exceeding 100 kHz
  The CPU will run EPICS and the FPGA will have a complete application development environment
  For slower signals, EtherCAT will be used as a real-time fieldbus with good price/performance ratio
  Synchronization and event information are key for applications where a full custom platform solution would be too costly
  Low speed signals are handled with commercially available PLC systems from Siemens
  This is a cost-effective solution that addresses ESS reliability and maintainability requirements
  The PLC:s will be connected to EPICS for further integration into the control system
Signal speed
10 Hz
1 Hz
0.1 Hz
100 Hz
1 kHz
10 kHz
100 kHz
1 MHz
10 MHz
Electronic front-end platform
EtherCAT
Industrial automation (PLC)
A custom made microTCA board with a powerful FPGA and a CPU. A FPGA framework constitutes the development environment. The CPU runs EPICS
EtherCAT I/O modules that are connected to commercial or open-source EtherCAT master controllers which are in turn connected to the EPICS based control system
Slower signals are handled by industrial automation (PLC) for reliability and cost reasons. The standardized platform for ESS applications comes from Siemens

## Slide 12: ICS vision and mission statements
ICS vision statement
ESS operated efficiently, reliably and safely, with a control system that everyone loves
ICS mission
The ICS division shall provide and maintain world-class and cost-efficient control, protection and safety systems and services for the ESS facility.
The division shall develop competence and innovative solutions that can be shared in the community through open processes

## Slide 13: ICS vision and mission statements
ICS vision statement
ESS operated efficiently, reliably and safely, with a control system that everyone loves
ICS mission
The ICS division shall provide and maintain world-class and cost-efficient control, protection and safety systems and services for the ESS facility.
The division shall develop competence and innovative solutions that can be shared in the community through open processes

## Slide 14: Project status - overview Integrated Control Systems
Achievements
  A new project plan in place and we are executing accordingly
    Start of execution has not been as easy as we thought
    More interrupts and staffing delays than expected
  The team is undergoing a period of rapid expansion
    Ten new recruitments are ongoing - technicians are starting to come in
    Call-offs to the new consultant framework agreement are also ongoing
  Substantial growth of the in-kind portfolio
    Ongoing and new projects in Estonia, Norway and Switzerland
    Increased activity in the in-kind activities together with Accelerator
Issues
  Slow procurement procedures, slow formal in-kind processes
  ESS In-kind goals hard to reach for ICS
  Budget and planning issues with installation
  Team and activity expansion growth pains - management

## Slide 15: Project status - highlights
The Personnel safety system test stand is being used for active evaluation and system development since some months
The commissioning of the SAS Access system in the Personnel safety lab has been finalized
The 3D-model for the PSS cabling has been
completed and can be used for estimating material and effort
The rack for Proton source and LEBT Vacuum Controls is operational and used for debugging and development This is the first full Vacuum control system powered on at ESS
  The proton source vacuum control system has been commissioned together with Accelerator division at INFN, Catania
Resources from the Hardware and Integration team performed installation together with colleagues during almost one week to enable the commissioning of the ion source vacuum control system

## Slide 16: Project status - highlights
  The full ICS configuration and production software tool chain has been integrated and used in real production cases for the first time
  ICS integrators have been using the Naming Service and the CCDB configuration tool to produce a model for the Proton source vacuum control system
  The data is then fed used by the IOC Factory software to automatically generate fully valid EPICS IOC:s for the modelled system
  A training material has also been produced to facilitate this automated configuration/generation methodology with in-kind stakeholders
  ICS/NSS integration have been making good progress with collaborative work on deploying a v4 EPICS IOC for a LS336 temperature controller to run in the NSS ESSIIP lab
  The ICS handbook, detailing ICS standards and best practices , has been released
  This is a critical document to facilitate wide-spread integration work with the ICS including in-kind and commercial partners’ work

## Slide 17: We are hiring!
We are looking for
  Controls system integrators
  Embedded system engineers
  Control system administrators
  Infrastructure software developers
  Control system software developers
  Safety and protection engineers
This year -> 6 - 8 positions
  Contact Annika Nordt, Daniel Piso Fernández, Susanne Regnell
  or https://europeanspallationsource.se/vacancies

## Slide 18: Thank you for your attention
Questions
Comments
henrik.carling@esss.se