## Slide 1: EPICS control system for ELI-NP Gamma Beam System (GBS)
Rok Šabjan on behalf of Cosylab team, ORNL, 2016-09-20

## Slide 2: Other ELI machines

## Slide 7: EuroGammaS Consortium
Amplitude
Alsyom
CNRS
COMEB
INFN – Consortium Leader
Sapienza
Scandinova
ALBA
Cosylab
Danfysik
Instrumentation Technologies
M+W
Menlo Systems
Research Instruments
STFC“

## Slide 8: Control System Scope
Control System Infrastructure (services, timing system, development environment, standards and templates)
Device level integration (EPICS)
HW Interfacing
Matlab Interface (labCA)
System level integration on-site (TBD)
Application and device specific functionality
Engineering GUI
Commissioning tools (Matlab / Middle Layer)

## Slide 9: Integrating different contributions

## Slide 10: Devices

## Slide 11: Control Room Layout
Design Direction for
  Room Dimensions: 16m x 10m
  Dry wall server room, space for 8 racks
  7 OPI workstations
    default 2x2 screens
    4x1 possible
  2 overheads
Optimal use of space
Extra middle work-desks
  Commissioning
  Central Control Option
Room foreseen for
  Meeting room corner
  Resting corner

## Slide 12: Vertical Column
A vertical column is an abstraction which describes how the concrete device type is integrated into the control system. It starts from the device sensors and progresses up to the GUI

## Slide 13: Parallelized Development Process
Requirements gathering
Development
Test procedures
FAT
Requirements gathering
Development
Test procedures
FAT
Requirements gathering
Development
Test procedures
FAT
VC1
VC2
VC3
Final FAT document is just a document with reference to all VC FATs.
After all VCs were FAT tested, actual IOC configuration was produced.

## Slide 14: Transparent Scope and Deliverables Management

## Slide 15: Scope by Subsystems
Control System Infrastructure
Diagnostic Devices
Laser Subsystem
RF System
Picosecond Timing Triggering System
Vacuum System and Magnet Power Supplies
IOC Health Monitoring
Laser Synchronization System
Conventional Facilities (Chiller)
Gamma Beam Characterization

## Slide 16: Integrated devices
Fast digitizers (4 GS/s) for current transformers
Basler GigE Vision Cameras
I-Tech Liberas
I-Tech LLRF
Scandinova RF Modulators
Simple motion controller, in/out (iPOS3604 HX-CAN)
Beckhoff modules for simple I/O
Siemens PLCs for Vacuum and Magnet PS
MRF Timing
…

## Slide 17: Controls Hardware
cPCI is the main form factor used:
MRF timing
Keystone digitizers
Ethernet devices
Pizza boxes for soft IOCs (Siemens PLC and Beckhoff, some Modbus/IP interfacing: Chiller, Vacuum, Magnets)

## Slide 18: Vacuum and Magnet Controls (STFC)

## Slide 19: Diag: Basler camera interfaced via areaDetector

## Slide 20: Diag: Libera BPMs

## Slide 21: Diag: Current Transformers
Time situation
Bergoz sensor elongates the pulse by factor of ~100 => 5ns
At 10 measurements per pulse (0.5 ns => 2 GS/s)
2-4 GS/s solution was chosen
  Not many cards in this range, additional complication is the platform (reduces possibilities) and desired voltage range (even further reduction)
Nominal Device Support was used

## Slide 22: Picosecond Timing Triggering System
Client Device | Count | Type | Comment
CCD Cameras | 23 | TTL | Assuming each camera needs one trigger [RD78]
Beam Position Monitor | 7 | TTL | Info obtained from A. Falone, April 24, 2015 11:11:53 AM, Subject: Re: System integration of Libera BPM; "…the Libera units (7) will be installed in two adjacent racks in GP08"
Current Transformer (FCT, ICT) | 4 | TTL | Assuming each Digitizer requires one trigger [RD78]
Laser subsystem (IP, LBTL) | 12 | TTL | system shown in [RD78] Figure 20: Interaction point components; trigger count and equipment location "GP-P-08" obtained from Kevin Cassou during skype meeting on 6 Mar 2015
RF Modulator | 15 | TTL | Assuming each modulator requires one trigger line, number of triggers is a sum of instances [RD78], Ch. 11.1.5. installed instances, HW is connected to ROOF level rack room
LLRF | 15 | LVPECL | Information on trigger count and type provided by I-Tech, 12 Mar 2015
HI efficiency camera | 2 | TTL | one per camera
Gamma | 8 | TTL | 4 in ACC bay 1, 4 in ACC bay 2
Experiment | 4 | TTL | 1 EVR board in experimental area, timing fiber optics is provided
Spare | 16 | TTL | one EVR with 4 TTL triggers per RACK room: 04, 06, 08 and ROOF

## Slide 23: RF: Scandinova Modulators
LLRF was implemented via Libera-LLRF (black box system)

## Slide 24: Development and testing

## Slide 25: Dealing with project delays

## Slide 26: February/March 2014

## Slide 27: Timeline for control system
May 5 2014 : Preliminary design review
  all data on devices, interfaces collected
  missing data marked with responsible stakeholders, clear action items and deadlines
15 intensive months of
Specifications, Architecture, Design, Prototyping,
Test procedures, Implementation (coding),
Documentation, Testing, Debugging, Acceptance
August 28 2015 : Acceptance test 1 at INFN
September 2015 : Installation and test at Magurele
October 2015 : Acceptance test 1 at Magurele
November 20 2015 : Acceptance test 2 at INFN
December 2015 : Installation and test at Magurele
December 2015 : Acceptance test 2 at Magurele

## Slide 28: May 2014

## Slide 29: Status
Plan from February meeting:
  May 5 2014 : Preliminary design review
    all data on devices, interfaces collected
    missing data marked with responsible stakeholders, clear action items and deadlines
Status
  Good progress on first set of deliverables (documents)
    Due to release draft/RFC documents in May
      Design and conventions
    Review meeting on May 6
  Alarmingly low information on CS interfaces and application requirements

## Slide 30: September 2014

## Slide 31: Overall Status
Plan from February meeting:
  May 5 2014 : Preliminary design review
    all data on devices, interfaces collected
    missing data marked with responsible stakeholders, clear action items and deadlines
Status
  Good progress during summer
  However lack of information on CS interfaces and application requirements are bringing our work to stand—still in September/October

## Slide 32: November 2014

## Slide 33: Overall Status
Plan from February meeting:
  May 5 2014 : Preliminary design review
    all data on devices, interfaces collected
    missing data marked with responsible stakeholders, clear action items and deadlines
Status
  Some dates on components requirements finalization are specified thanks to Antonio Falone
  Some are still not

## Slide 34: Building hand-over May (2015)

## Slide 35: September 2015

## Slide 37: Successful control system FAT

## Slide 38: Conclusion
EPICS once again proved as a robust and easy to use control system framework that provided no risks to the project
  Cosylab has a the world’s largest group of EPICS projects architects, developers and project managers with experience from dozens of projects worldwide
Transparent and disciplined project setup and management was required to cope with the complicated project setup
The final on-site part of the project is still ahead of us
Acknowledgement to members of EuroGammaS Consortium and Cosylab project team
  More details by slava.isaev@cosylab.com

## Slide 39: Thank you!

## Slide 42
Notes: GDR = Giant Dipole Resonance

## Slide 44: Online Timing Configuration

## Slide 45: Laser Subsystem (QT) – integrated as black box