## Slide 1: ESS Safety Readiness for Operations
Peter Jacobsson
Head of Environment, Safety & Health
Thomas Hansson
Senior Engineer, Radiation Safety
www.europeanspallationsource.se

## Slide 2: Outline
ESS project
ESS Licensing
The purpose of a Safety Readiness Review (SRR)
Lessons learned from SRR-1, July 2018
Improvements made for the SRR for Test Stand 2 (TS2), August 2019
Ideal approach for gradual commissioning
Set of documents reviewed during the SRR for TS2
Outcome of the SRR for TS2 and the next step

## Slide 3: ESS basic design principle
Ion Source
High Power Accelerator:
Energy: 2 GeV
Rep. Rate: 14 Hz
Current: 62.5 mA
16 Instruments in Construction budget
Committed to deliver 22 instruments by 2028
~30-100 higher performance than at ILL
Total cost: 1843 MEuros 2013
Target Station:
- He-gas cooled rotating W-target (5MW average power)
- 42 beam ports

## Slide 4: ESS Schedule
Ground break
Beam on Target
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
Jun 2014
Sep 2016
Dec 2019
July 2022
Dec 2025
Beam on Temporary Dump
First instrument ready for hot commissioning
Oct 2017
First installations on-site (Accelerator)
First installations on-site (Target & NSS)
Beam on Dump
Jan 2021
Last Construction Phase
Instrument handover
to Operations
Start of user program
SOAP

## Slide 5: Licensing timeline for trial operations
projections Aug 2019
2019
2021
ESS
SSM
Intentional neutron production trial operation review
2022
2020
RBoT
RFQ Beam
BoD
Conditional permit
SRR5
SRR4
Submission 2021-08-01
SC LINAC trial operation review
Conditional permit
Submission 2020-11-15
SRR2
Submission 2019-07-15
Conditional permit
Warm LINAC trial operation review
BoT
Ref Doc 2019-03-18
Ref Doc 2020-06-15
Ref Doc 2021-02-28
RFQ – Radio Frequency Quadropole
BoD – Beam on Dump
BoT - Beam on Target
RBoT - Ready for Beam on Target
PSAR – Preliminary Safety Analysis Report
SRR - Safety Readiness Review
SSM – Swedish Radiation Safety Authority
IoS Beam
SRR1
TS2b
Klystron test
RF cond
IoS
permit
2019
2021
2022
2020
2018
2023
DTL4 Beam
SRR3

## Slide 6: Safety Readiness Review (SRR)
The purpose is to review readiness to safely commission/operate.
The SRR is primarily intended for activities involving the proton beam, but could in specific cases also be applied for other systems.
The SRR is an independent review of the safety aspects, performed after the Test Readiness Review (TRR) or corresponding activity.
It is a process by which HARDWARE, PERSONNEL and PROCEDURES associated with commissioning/operation are verified.
The scope is safety, both conventional safety and ionizing radiation.
The ownership of the process lies within ESH division.

## Slide 7: Inputs
Design descriptions
Architecture description
Concept of Operations
Requirements Specification
Interface descriptions
Integration Plan
Operation and maintenance documents
Verification Plan
Risk assessment
CE marking/Declaration of Conformity

## Slide 8: History
First SRR (SRR1), was for the Ion Source and LEBT, July 2018
  SRR-1 Committee report
First beam from the Ion Source, roughly 6 weeks later..
Decision to do a SRR for our Test stand performing test of klystrons (Test Stand 2)
Together with internally gained experiences, lessons learned meetings and also discussions working our way through received recommendations from ESHAC and the SRR reports.
The SRR for the test stand was conducted 30 and 31 of August 2019, chaired by John Anderson leading a committee of in total 6 persons (2 internal staff)

## Slide 9: Improvements made for SRR TS2 (Test Stand 2)
Clarifications in the governing documents; ESS-0123091 rev 2 and ESS-0177837 rev 3
Identify involved systems and the breakdown structure 6 months in advance.
Necessary to daily and more clearly state and implement work according to ESS-0016468 (Classification) and ESS-0041755 (Hazard analysis).
Identify needed SRR committee competencies 3 months in advance.
Start weekly SRR in-house preparations at the latest 3 months before SRR-2.
Review documents available for the SRR committee 2 weeks in advance.

## Slide 10: Ideal approach for gradual commissioning
Integrate A+B
(install)
Integrate C+D = Complete system
(install)
Verify D
(testing)
Verify A+B
(testing)
Installation
proton beam commissioning
TRR
SRR
Verify C+D = Complete system
Commissioning
TRR
B
TRR
A
TRR
C
TRR
D
TRR
SRR
System owner responsible.
Scope: Performance and safety
ESH coordinates independent review
Scope: Safety
Verify B
(testing)
Verify A
(testing)
Integrate = install
Verify = test/commision

## Slide 11: Ideal approach for gradual commissioning
Integrate
Power cabling
+ Medium temp circuit
Integrate
Shielding + PSS
Integrate
PSS + LLRF + Modulator + Medium temp circuit
TRR
TS2
Integrate
Klystron + Medium temp circuit
Verify
Klystron
Verify
LLRF
Verify
Modulator
Integrate
ICS controls + LLRF
Verify
LCW
substation
Verify
Electrical
substation
Verify
Power cabling
Verify
Medium temp circuit
Verify
Cryoplant
Verify
Transfer Line
Verify
Shielding
Verify
PSS
Verify
RF
distribution
Verify
Signal
cabling
Verify
CDS
Valve box
Verify
Bunker
Integrate Bunker + CDS valve box + Signal cabling + LLRF + RF distribution + Medium temp circuit = Cryomodule with insulation vacuum and beam vacuum
Installation
Commissioning
SRR
Integrate = install
Verify = test/commision
Verify Cryomodule, including
insulation vacuum and
beam vacuum
TRR RF distribution
TRR Electrical substation
TRR Power cabling
TRR Klystron
TRR Modulator
TRR
Bunker
TRR
PSS
TRR
CDS valve
box
TRR
Transfer Line
TRR
Cryoplant
TRR
Signal cabling
TRR ICS controls
TRR LLRF
TRR LCW substation
TRR Medium temp
circuit
TRR
Shielding
Verify
ICS controls
Draft
Understanding
December 2018
Documents required | Bunker | Shielding | PSS
Design descriptions |  |  | 
Architecture description |  |  | 
Concept of Operations |  |  | 
Req. Spec, incl. Hazard identification |  |  | 
Classification doc (rad safety) |  |  | 
Interface descriptions |  |  | 
Integration Plan |  |  | 
Operation & maintenance documents |  |  | 
Verification Plan |  |  | 
Verification Report |  |  | 
Validation Report |  |  | 
CE marking / Declaration of conformity |  |  | 
Other documents |  |  | 
Example

## Slide 12: TS2 and involved sub-systems

## Slide 13: Set of documents to be reviewed, 1(2) TS2 Document Matrix at Confluence

## Slide 14: Set of documents to be reviewed, 2(2) TS2 presentations and belonging references at Indico
Identified safety measures

## Slide 15: Outcome of the SRR for TS2
SRR report with:
  Pre-start items
  Post-start items
SRR committee report conclude that the Test Stand 2 would be ready for commissioning if the pre-start items are done.
ESS follow-up meetings after the SRR for TS2 are already scheduled. ESS to start the commissioning by the end of September.
ESS start-up meetings for SRR-2 for the Normal Conducting Linac (NCL) to be scheduled asap, with the ambition to start in early September.
First dialogue held with NCL Machine Section Coordinator April 2019.

## Slide 16: Reflections from our TSS committee chair
System documentation has improved since the first SRR
  Typical minor document inconsistencies
    Nothing that was of a significant concern
Roles and Responsibilities better defined for TS2 SRR
  Electrical coordination
  Test stand commissioning coordination
System installation continues to be of the highest calibre
  Quality of work is excellent
  Housekeeping looked very good
Delays in component deliverables causing schedule pressures
  Need to resist temptations to operate with compromised systems to the extent possible
    If system changes are required, changes need to be fully reviewed, accepted and approved
Additional effort is needed to better establish commissioning plans and procedures necessary to support commissioning activities
  Work toward process driven vs expert driven systems
  Promotes a common direction and understanding
  Fosters reduced unwanted outcome

## Slide 17: ESS – Aerial photographs