## Slide 1: Target Module Fabrication Status
Drew Winder Target Systems
Don Abercrombie
Mike Atherton
Bernie Riemer
Mark Wendel

## Slide 2: Outline
Spares status
Ongoing Fabrication Status
  Upgraded original flow targets
  Jet-flow targets
FY16 Planned Fabrication
  Water shroud
  Updated original flow mercury vessels
Future Fabrication

## Slide 3: Terminology

## Slide 4: Spares Status
2 ready spare targets
ORTE-003 – Original design
  Sister unit to both ORTE-001 (>4100 MW∙hr) and ORTE-002 (166 MW∙hr)
  Includes trapezoidal cover plate
  Water shroud not removable
  Does not include newer material and processing improvements to increase cavitation damage resistance

## Slide 5: Spares Status
MTX-010 – Upgraded original design
  Does not have trapezoidal cover plate
  Removable water shroud
  Includes improvements to materials and processing to increase cavitation damage resistance
  Includes modifications to increase fatigue life at front body to transition weld
  Includes strain and temperature sensors

## Slide 6: Ongoing Fabrication Status
Reduce partial penetration welds
Original flow targets,
1 delivered without weld changes,
1 delivered with changes,
1 to be delivered with changes
Gas injection
Jet-flow targets,
1 delivered and developed leak
2 to be delivered with changes,
1 on hold (was welded before 2014 failures, has thin outer window)
Target fabrication is ongoing at Metalex
3 targets of 7 target contract delivered

## Slide 7: Reduce Partial Penetration Welds
Designed Weld Penetration
Unwelded portions
Weaknesses
  Partial penetration weld,
  Lack of inspectability,
  Stress concentration from change in geometry, and
  Stress singularity at weld root is bad for fatigue and impossible to resolve with linear FE analysis

## Slide 8: Reduce Partial Penetration Welds
Un-modified
Modified

## Slide 9: Reduce Partial Penetration Welds
Un-modified
Modified

## Slide 10: Reduce Partial Penetration Welds
Machined features leave ½ inch by ¼ inch (12 mm x 6mm) passages between bulk inlets and return passage.
Size intended to allow radiograph film to be inserted.
Mercury flow through holes not significant.
Front Body
Transition

## Slide 11: Ongoing Fabrication Status
MTX-013
  Updated original type, identical to current MTX-010 spare
  Sensors will be improved over MTX-010.
  Projected delivery June 2016.

## Slide 12: Gas Injection
New gas supply port
Modified vent
New hardware in mercury passages
(one on each side)

## Slide 13: Gas Injection
Bubbler
Bubbler weldment fits in new holes in transition piece.
Single bent tube supplies gas. Will be in the mercury flow.
Penetration passes gas from the back of the target to inside the flow passages.

## Slide 14: Gas Injection
Gas vent changed
  Moved towards elbow.
  Collection pocket added.
Old Vent Location
(will be capped)
New Vent Location
Added gas collection pocket

## Slide 15: Ongoing Fabrication Status
MTX-011
  Jet-flow type target
  Includes modifications to increase fatigue life at front body and transition weld
  Includes orifice bubbler gas injection hardware.
  Will include strain sensors
  Projected delivery August 2016
MTX-012
  Jet-flow type
  Same as MTX-011
  Projected delivery September 2016

## Slide 16: Ongoing Fabrication Status
MTX-008
  Jet-flow type target
  Construction on hold
    At time of T10 leak, was already fabricated past the weld of the T10 leak location
    Has 25% reduction in thickness at T12 leak location
  Projected delivery not before January 2017

## Slide 17: FY16 Fabrication
Fabrication plans are based on projected target consumption.
  Consumption rates are based on planned target removals in the near term, followed by a 2 target a year pace in future years.
  Goal is to maintain at least 3 ready spares

## Slide 18: FY16 Target Fabrication
Projected target inventory
Winter 15/16 Shutdown | Early 16 | Summer 16 Shutdown | Late 16 | Winter 16/17 Shutdown (IRP) | Early 17 | Summer 17 Shutdown | Late 17 | Winter 17/18 Shutdown | Early 18 | Summer 18 Shutdown | Late 18 | Winter 18/19 Shutdown | Early 19
 | MTX-009 |  | MTX-010 |  | MTX-011 |  | MTX-011 |  | MTX-013 |  | MTX-012 |  | MTX-008
 | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003
 | MTX-010 |  | MTX-013 |  | MTX-013 |  | MTX-013 |  | MTX-012 |  | MTX-008 |  | 
 |  |  | MTX-011 |  | MTX-012 |  | MTX-012 |  | MTX-008 |  |  |  | 
 |  |  | MTX-012 |  | MTX-008 |  | MTX-008 |  |  |  |  |  | 
Installed
Ready Spares
Arriving Spares

## Slide 19: FY16 Target Fabrication
Goal was to develop an improved original flow type target design to begin fabrication in mid-2016
Analysis has shown proposed target designs have vulnerabilities
  More details in next presentation
Continue to pursue improved target designs, but will fabricate more original flow type targets in the interim

## Slide 20: FY16 Target Fabrication
Target fabrication requires ~66 weeks
Water shroud and mercury vessel components are independent until 41st week.
Water shroud fabrication requires ~16 week lead
Water Shroud Fabrication
Mercury Vessel Fabrication
Final Target Assembly
16 weeks
66 weeks

## Slide 21: FY16 Target Fabrication
Will start fabrication of two water shrouds by summer 2016
  Will incorporate lessons learned into drawings and fabrication specifications
Will follow with order of at least one original type mercury vessel within 16 weeks
  Will incorporate lessons learned into drawings and fabrication specifications
  No major changes past current original type targets under fabrication

## Slide 22: Future Target Fabrication
Winter 15/16 Shutdown | Early 16 | Summer 16 Shutdown | Late 16 | Winter 16/17 Shutdown (IRP) | Early 17 | Summer 17 Shutdown | Late 17 | Winter 17/18 Shutdown | Early 18 | Summer 18 Shutdown | Late 18 | Winter 18/19 Shutdown | Early 19
 | MTX-009 |  | MTX-010 |  | MTX-013 |  | MTX-013 |  | MTX-011 |  | MTX-012 |  | MTX-008
 | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003 |  | ORTE-003
 | MTX-010 |  | MTX-013 |  | MTX-011 |  | MTX-011 |  | MTX-012 |  | MTX-008 |  | 
 |  |  | MTX-011 |  | MTX-012 |  | MTX-012 |  | MTX-008 |  |  |  | 
 |  |  | MTX-012 |  | MTX-008 |  | MTX-008 |  |  |  |  |  | 
Installed
Ready Spares
Arriving Spares
Updated target mercury vessel designs will be procured when designs are complete
Will keep the target fabrication pipeline flowing

## Slide 24: Backup

## Slide 25: Backup
Benefits
  Full penetration weld all around.
    Area near racetrack will be machined before welding to allow full penetration, then filled back with GTAW.
  Radiographs possible all around weld.
  Compatible with analysis.
  Removes contact ambiguity on abutting faces.
Front Body
Transition

## Slide 26: Proposed Changes – Elimination of Partial Penetration Weld Areas
Mercury Vessel Weldment before Modification, Drawing A222, Rev. 7
Mercury Vessel Weldment after Modification, Drawing A222, Proposed Rev. 8