## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
David E. Anderson
Level 3 Manager
September 14-17, 2021
P.03.6 New Linac Modulators

## Slide 2: Outline
Scope
Organization
Progress since CD-2/3
Challenges
Final design status
Installation plans
Cost and schedule
Labor profile
Risk register
Responses to recommendations
ESH&Q and COVID-19 impacts
12-month look-ahead
Summary

## Slide 3: Scope P.3.6 – New Linac Modulators
Final design of, procure, install, test and commission three new Alternative Topology High Voltage Converter Modulators (AT-HVCM) to power twenty-eight 700 kW klystrons
  Procure modulators under P.10.3.6
  Procure modulator spares to support operation of new AT-HVCM modulators
  Procure transformer and SCR Controller
  Upgrade & procure controller to address obsolescence issues
SCL-Mod25
SCR and modulator (9)
SCL-Mod28
SCR and modulator (9)
SCL-Mod30
SCR and modulator (10)
SCL-Mod25
transformer
SCL-Mod28
transformer
SCL-Mod30
transformer
Charge: 1

## Slide 4: Procurement Strategy
Step-down AC transformer1
SCR Controller
AC-DC Conversion1
Modulator System2
Modulator Controller
SCL-Mod25 | Sole source DPI | Sole source DPI | Build-to-print AOPT | Rack/chassis DCS3 Remainder ORNL
SCL-Mod28 | Sole source DPI | Sole source DPI | Build-to-print AOPT | Rack/chassis DCS3 Remainder ORNL
SCL-Mod30 | Sole source DPI3,4 | Sole source DPI4 | Build-to-print AOPT | Rack/chassis DCS3,4 Remainder ORNL
Spare | N/A | N/A | Build-to-print AOPT | N/A
1identical to existing equipment
2excludes ORNL-provided CO2, temp. monitor, oil circulation systems and oil
3currently at ORNL
4ship to AOPT as GFE for vendor FAT
Long lead CD-3B procurement (P.10.3.6)
Standard CD-3 procurement
Charge: 2

## Slide 5: Organization
P.3 – RF Systems
John Moss
P.3.7 Utilities
Greg Norman
P.3.3 NCL HPRF
John Moss
P.3.2 SCL HPRF
John Moss
P.3.8 RF Controls Karen White
P.3.6 New Linac
Modulators
David Anderson
P.3.4 LLRF
Mark Crofford
P.3.1
Management and System Integration John Moss
P.3.9 Global Controls Karen White
P.3.5 Existing Linac
Modulators
Chris Pappas
P.3.1.1
Management and System Integration
John Moss
P.3.2.5 Circulators
John Moss
P.3.2.3 Klystrons
John Moss
P.3.2.6 Water Loads
John Moss
P.3.2.2
Transmitters
John Moss
P.3.2.1
Management and System Integration
John Moss
P.3.3.3 Klystrons
John Moss
P.3.3.4 Circulators
Sung-Woo Lee
P.3.3.2
Transmitters
John Moss
P.3.3.5 Glycol/ Water Loads Sung-Woo Lee
P.3.3.1
Management and System Integration
John Moss
P.3.4.2 LLRF System
Mark Crofford
P.3.4.3 Arc Detectors
Mark Crofford
P.3.4.1
Management and System Integration
Mark Crofford
P.3.4.4 Reference Line
Chip Piller
P.3.5.2 Modulator System
Chris Pappas
P.3.5.3 Modulator Control System Mark Wezensky
P.3.5.1
Management and System Integration
David Anderson
P.3.5.4 Modulator SystemTest
Article
David Anderson
P.3.6.3 SCR System
David Anderson
P.3.6.4 Modulator System
David Anderson
P.3.6.2
Transformer
David Anderson
P.3.6.5 Modulator Control System Mark Wezensky
P.3.6.1
Management and System Integration
David Anderson
P.3.6.6 Integrated System
David Anderson
P.3.7.3 Water Utilites, Modify
Existing RFQ/DTL
Greg Norman
P.3.7.2 Water Utilities, New Cold
Linac SCL RF
Greg Norman
P.3.7.7 Electrical
Wm Barnett
P.3.7.1
Management and System Integration
Greg Norman
P.3.8.2 Linac RF Controls Doug Curry
P.3.8.3 Linac Water System
Controls
Derrick Williams
P.3.8.1
Management and System Integration
Doug Curry
P.3.9.2 Linac/SCL Timing/MPS Doug Curry
P.3.9.3 Linac/SCL Protection System
Kelly Mahoney
P.3.9.1
Management and System Integration
Doug Curry
P.3.9.4 Linac/SCL Networking and
Computing
Doug Curry
P.3.5.5 Warm Linac Test HVCM David Anderson
P.3.5.6 Upgrade RFQ-Mod1 Chris Pappas
P.3.6 Team
David E. Anderson – work package manager, lead engineer
Mark Wezensky – controls engineer
Kerry Ewald –mechanical designer
Jim Hicks – electrical technician
Joshua Singleton – electrical technician
Austin Bullman – electrical technician
Charge: 5

## Slide 6: Progress since CD-2/3
At CD-2/3, the following items were proposed for the previous year
  Execute build-to-print contract and perform 1st article FAT and SAT
  Award optional spares for build-to-print contract
  Procure 2 additional power transformers and SCR units
  Finalize modulator control system design
Charges: 1,2,4

## Slide 7: Progress since CD-2/3
Execute build-to-print contract and perform 1st article FAT and SAT and award spares
  Awarded to Alpha Omega Power Technologies (AOPT) in April 2020 with option for spares exercised after CD2/3 approval
  1st article FAT scheduled for September 2021; SAT will be eliminated since vendor is capable of full average power testing at FAT
  Supported vendor on assembly and switch plate testing
Single phase test stand set up at vendor for switch plate qualification
ORNL personnel training AOPT personnel on switch plate assembly
Capacitor rack assemblies at AOPT

## Slide 8: Progress since CD-2/3
Procure 2 additional power transformers and SCR units
  Awarded to Dynapower to insure interchangeability with existing equipment in December 2020
  Deliver SCR units by September 2021, transformers by September 2021
    2nd unit presently at AOPT for modulator FAT
    Minor delay due to regulator circuit configuration issue
SCR unit under factory acceptance testing at DPI, July 15, 2021

## Slide 9: Progress since CD-2/3
Finalize modulator control system design
  Custom hardware, new PXI equipment and controller programming complete and mostly tested
  90+% of equipment in house and assembled/tested
  First article PPU controller rack at AOPT to be used for FAT
Custom chassis and modules for PPU new modulator controllers
Updated controller HMI with new Aux I/O screen

## Slide 10: Challenges
Discovery of heating on boost transformer gap components
  Redesigned to reduce losses to 5.2%, DT to 11.2% of original value
Manufacturing delays, primarily due to component suppliers
  Worked with vendor to optimize schedule, captured unrecoverable delays with project PCRs
Failure of SCR unit on RFAX modulator
  Sent to DPI to determine root cause (SCR failure and vacuum contactor failure, improper protection circuit configuration)
  PCR to procure additional unit from contingency
FEA of boost capacitor pole face redesign to minimize losses
Damage in HV section to SCR enclosure
Charges: 1,4

## Slide 11: Final Design Status
Final Design Review held on May 26, 2019
Recommendations addressed
  Vendor test plan & QA plan with RFQ
  ORNL on-site presence during critical manufacturing stages
  ORNL procure long-lead items for build-to-print
Charge: 6

## Slide 12: Installation Plans
Transformers installed on pads upon arrival starting Sept. 2021
  Switch gear and cabling already in place
SCRs installed according to installation schedule, except 1st unit which ships to AOPT for modulator FAT, starting Sept. 2021
Modulators and control racks installed according to installation schedule starting September 2021
  CO2 system provided by external vendor due to certification requirements
  Oil circulation and temperature monitoring system installed by ORNL after equipment arrival
Integrated testing readiness dates1:
SCL-Mod30: Mar. 2022
SCL-Mod28: Jul. 2022
SCL-Mod25: May 2023
1latest dates based on approved June PCR
Charges: 4,5

## Slide 13: Schedule
Fabrication on schedule with installation to begin late FY21
Charge: 4
long outage
FY18
FY19
FY20
FY21
FY22
FY23
FY24
FY25
FY26
CD-4
(E)
CD-4
(L)
42 months contingency
FY27
FY28
CD
3B
CD
2/3
CD
1
CD
3A
RF Systems Preliminary Design Complete
RF Systems FD (Excl. LLRF & RFQ-DTL HVCM)
RF Systems FD Complete (LLRF & RFQ-DTL HVCM)
Procure/Fab RF Systems Controls
Transmitter Design & Fab First Article
Procure/Fab Transmitters
Procure/Fab SCL Klystrons
First High-Power Test for XMTR 30 & 31 (8/2022), 27 & 28 (11/2022), and 25 (11/2023) Complete
Procure/Fab WG, Circs and Loads
Procure/Fab Transformers & SCR
Procure/Fab New Modulator Systems
Proc/Fab LLRF
Proc/Fab Upg. Linac Modulators
Procure/Fab 3MW Klystrons
3MW Klystron Design & Fab First Article
Procure/Fab Utilities/Electrical
Existing Linac – Test HVCM w. Dual 3.0 MW Klystrons
RF SCL Installation

## Slide 14: PPU Changes since CD-2/3
Major increases
  Additional SCR unit and temperature monitoring $300k
  ORNL-provided cooling system with other modulators’ AIP-36 upgrades $227k
  AT-HVCM GFE shipping/preparation for vendor FAT $54k
Charge: 4

## Slide 15: Estimate to Complete
P.03.06.02 (SCR System) merged into P.03.06.02 (Transformer) in FY21
P.03.06.02 and P.03.06.04 primarily vendor subcontracts
Charge: 4

## Slide 16: Estimate to complete
Completion of manufacturing subcontracts main contributor to materials costs in FY21 and FY22
Labor primarily to support system installation and testing through FY23
Charge: 4
Chart: P.03.06 New Linac Modulators
| FY2021 | FY2022 | FY2023 | FY2024 | FY2025
Actual Cost Oct - May FY21 | 954.2808
Labor | 245.4916 | 476.4802 | 90.5505 | 14.4636 | 0
Material | 1319.1822 | 624.662 | 0 | 0 | 0

## Slide 17: Labor Profile
Heavy technician / RM labor remaining in FY21/FY22 to support installation
Labor ramps down quickly after installation complete
Heavy technician labor support is a challenge for new Electrical Power Conversion Group
Charge: 4

## Slide 18: Project Change Requests post CD-2/3
Charge: 4
PCR # | Title | Impact (k$) | Motivation
LL-2020-42 | Awarded AT-HVCMs & Error Corrections | 472 | Correct error for historical actuals, incorporate vendor costs and impacts
LL-2020-50 | AT-HVCM Vendor Inspection Consultant | 14 | Consultant for vendor oversight during COVID
LL-2020-53 | AT-HVCM Vendor Testing GFE | 54 | Prep and ship ORNL equipment to vendor for full power testing
RF-2021-01 | AT-HVCM Oil Cooling System | 227 | Provide ORNL-furnished oil cooling systems compatible with AIP-36
RF-2021-03 | Award of Remaining Transformers and SCRs | 11 | Cost increase to incorporate new design features
RF-2021-07 | Award of AT-HVCM Spare Parts | (37) | Vendor schedule improvements and removal of vendor oversight
RF-2021-12 | Added SCR Unit and Associated Hardware | 228 | Added SCR after failure of RFAX SCR unit
RF-2021-13 | AT-HVCM Temperature Monitoring and Other Diagnostics | 79 | Added temp. monitoring so modulator consistent with others
LL-2021-02 | AT-HVCM Vendor Schedule Update | 4 | Capture vendor schedule slippages
LL-2021-15 | Modulator Oil Award and de-scope test equipment | (24) | Reduced cost of modulator oil

## Slide 19: Risk Register
No active risks identified
  Three risks retired
High Risks
  No high risks identified
Key risk categories analyzed
  Equipment requirements
Risks are reviewed on a regular basis
Charge: 5

## Slide 20: Responses to Recommendations
No recommendations from CD-2/3 DOE review
Recommendations from prior reviews are closed
Charge: 6

## Slide 21: ESH&Q and COVID-19 Impacts
SCR vendor non-conformance to ORNL implemented changes
  Vendor improved internal QA procedures to address
  ORNL to perform more thorough incoming inspections
Modulator vendor has done a good job capturing ECOs with ORNL approval
COVID-19 has impacted manufacturing
  Vendor supply chain delays impacting manufacturing by ≤3 months
  Inability to travel required ORNL to hire local NM consultant to monitor modulator fabrication and assembly
  Overall, vendors and ORNL personnel have done an outstanding job responding to COVID-19 issues
Charge: 3,5

## Slide 22: 12-Month Look-Ahead
Complete FAT of modulator systems
  SCL-Mod30: Sept. 2021
  SCL-Mod28: Sept. 2021
  SCL-Mod25: Nov. 2021
Complete delivery of power transformers and SCR units by end of FY2021
Installation of first two systems initiated by summer of 2022
Charge: 4,5

## Slide 23: Summary
Technical challenges mostly in the past
Project is on schedule
  Vendor subcontracts are on track with deliveries on schedule
  Installation scheduled to begin late FY21
Using PCRs, costs have been well managed
Labor ramp-up for installation will tax EPC group resources