## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
Alan Justice
Level 4 Manager for RF and Global Controls
September 14-17, 2021
P.3.8 Linac RF Controls
P.3.9 Linac Global Controls

## Slide 2: Outline
Scope
Organization
Progress since CD-2/3
Challenges
Final design status
Installation plans
Cost and schedule
Labor profile
Risk register
Responses to recommendations
ESH&Q and COVID-19 impacts
12-month look-ahead
Summary

## Slide 3: Scope
P.3.8/P.10.3.8 RF Controls
  Integrate new HPRF and LLRF into existing SNS EPICS based Control System to support 7 additional Cryomodules
  P.3.8.2 Linac HPRF Controls
    Controls support for 3 new Modulators and 5 new Transmitters
  P.3.8.2 Linac LLRF Controls
    Controls support for 28 LLRF MicroTCA Systems
Charge: 1, 2
SNS Controls EPICS environment
B3-3 Crofford

## Slide 4: Scope
P.3.9/P.10.3.9 RF/SCL Global Controls
  P.3.9.2 Linac/SCL Timing/Machine Protection System(MPS)
    Extension of SNS Timing and MPS to devices added for PPU
    Total of 17 Timing Receiver Cards, 4 Timing Fanouts and 3 MPS Nodes
Charge: 1, 4
MPS Fast Protect Nodes
Timing Fanouts
VME Timing Receiver
MicroTCA Timing Receiver

## Slide 5: Scope
P.3.9 RF/SCL Global Controls
  P.3.9.3 Linac/SCL Personnel Protection
    Extension of SNS Accelerator PPS to devices added for PPU
  P.3.9.4 Linac/SCL Networking and Computing Infrastructure
    Extension of network and computing infrastructure to devices added for PPU
Charge: 1, 4
PPS KL Cab04
Network switches
Klystron Gallery User Terminal

## Slide 6: Organization
Charge: 5
P.3 – RF Systems
John Moss
P.3.7 Utilities
Greg Norman
P.3.3 NCL HPRF
John Moss
P.3.2 SCL HPRF
John Moss
P.3.8 RF Controls Karen White
P.3.6 New Linac
Modulators
David Anderson
P.3.4 LLRF
Mark Crofford
P.3.1
Management and System Integration John Moss
P.3.9 Global Controls Karen White
P.3.5 Existing Linac
Modulators
Chris Pappas
P.3.1.1
Management and System Integration
John Moss
P.3.2.5 Circulators
John Moss
P.3.2.3 Klystrons
John Moss
P.3.2.2
Transmitters
John Moss
P.3.2.1
Management and System Integration
John Moss
P.3.3.3 Klystrons
John Moss
P.3.3.4 Circulators
Sung-Woo Lee
P.3.3.2
Transmitters
John Moss
P.3.3.5 Glycol/ Water Loads Sung-Woo Lee
P.3.3.1
Management and System Integration
John Moss
P.3.4.2 LLRF System
Mark Crofford
P.3.4.3 Arc Detectors
Mark Crofford
P.3.4.1
Management and System Integration
Mark Crofford
P.3.4.4 Reference Line
Chip Piller
P.3.5.2 Modulator System
Chris Pappas
P.3.5.3 Modulator Control System Mark Wezensky
P.3.5.1
Management and System Integration
Chris Pappas
P.3.5.4 Modulator SystemTest
Article
Chris Pappas
P.3.6.3 SCR System
David Anderson
P.3.6.4 Modulator System
David Anderson
P.3.6.2
Transformer
David Anderson
P.3.6.5 Modulator Control System Mark Wezensky
P.3.6.1
Management and System Integration
David Anderson
P.3.6.6 Integrated System
David Anderson
P.3.7.3 Water Utilites, Modify
Existing RFQ/DTL
Greg Norman
P.3.7.2 Water Utilities, New Cold
Linac SCL RF
Greg Norman
P.3.7.7 Electrical
Wm Barnett
P.3.7.1
Management and System Integration
Greg Norman
P.3.8.2 Linac RF Controls
Alan Justice
P.3.8.3 Linac Water System
Controls
Derrick Williams
P.3.8.1
Management and System Integration
Alan Justice
P.3.9.2 Linac/SCL Timing/MPS Alan Justice
P.3.9.3 Linac/SCL Protection System
Kelly Mahoney
P.3.9.1
Management and System Integration
Alan Justice
P.3.9.4 Linac/SCL Networking and
Computing
Alan Justice
P.3.5.5 Warm Linac Test HVCM
Chris Pappas
P.3.5.6 Upgrade RFQ-Mod1 Chris Pappas

## Slide 7: Progress since CD-2/3
12 Month Look ahead from CD-2/3 Review
  P.3.8.2 HPRF
    Document the software configuration information
    Define software interlocks used by other systems
  P.3.8.2 LLRF
    Continue software support for the firmware development of the FCM and HPM
    Document the software configuration information
    Define software interlocks used by other systems
    Support cavity testing in the Linac
Charge: 1, 4

## Slide 8: Progress since CD-2/3
12 Month Look ahead from CD-2/3 Review
  P.3.9.2 Linac/SCL Timing/MPS
    Document the software configuration information
    Define software interlocks used by other systems
  P.3.9.3 Linac/SCL Protection System
    Complete CD-3B procurements
  P.3.9.4 Linac/SCL networking and computing infrastructure
    Review installation documentation
Charge: 1,2,4

## Slide 9: Progress since CD-2/3
Accomplishments
  P.3.8.2/P.10.3.8.2 HPRF
    Reviewed existing HPRF Transmitter PLC code
    Developed plan to extend PLC and EPICS software support for factory acceptance testing and production deployment.
  P.3.8.2 LLRF
    Continued software support for LLRF platform updates
    Designed and completed procurement for LLRF Timing Interface cards
    Completed procurement for LLRF MicroTCA Processors
Charge: 1,2,4
PPU LLRF MicroTCA platform
B3-3 Crofford

## Slide 10: Progress since CD-2/3
Accomplishments
  P.3.9.2 Linac/SCL Timing/MPS
    Completed Procurement and Received all Hardware and Cabling
    Received, Inspected and Accepted Controls Racks
    Finalized Installation Plans and Drawings
    Tested all Timing Fanouts, Timing Receivers, and MPS Hardware
Charge: 1,2,4
Controls Rack 50-S-03
Rack UL Inspection

## Slide 11: Progress since CD-2/3
Accomplishments
  P.3.9.3 Linac/SCL Protection System
    Procured, received, tested, and installed KLCab04
    Procured, received and tested RF Transmitter and Modulators interfaces
    Procured all cabling and connectors for Interfaces
  P.3.9.4 Linac/SCL networking and computing infrastructure
    Completed Procurement of all Hardware and Cabling
Charge: 1,2,4
PPS Interface chassis

## Slide 12: Challenges
Long Lead Times
  Issue
    Global shortage of Integrated Circuits (ICs) and bare printed circuit board(PCB) materials
  Mitigation
    Moved procurements up on the schedule
Personnel Resources
  Issue
    In the Last 12 months lost a field engineer and technician
  Mitigations
    Posting the technician job and hiring someone as soon as possible
    ORNL Reimagining provided access to a second technician that is being trained and will be utilized for PPU installation
Charge: 2,4,5

## Slide 13: Final Design Status – P.3.8.2
HPRF design is final
  Hardware and software are already in use for production systems
LLRF is a new platform but has received final design review approval
  Software supports basic functionality and progress is ongoing for advanced functionality
  Support for production cavity field testing has been successful
Charge: 1, 2
Charge: 2
B3-3 Crofford

## Slide 14: Final Design Status – P.3.9.2, P.3.9.3, P.3.9.4
Timing, Networking and PPS designs are final
  Designs are complete and already utilized for production
MPS Fast Protect System(FPS) is based on a new design that is being completed through an Accelerator Improvement Project
  The final design has been approved and the hardware is finalized
  Firmware and Software are in final stages of development
  Firmware and software will be completed in the next 4 months
Concerns
  New MPS FPS will not be ready for PPU Deployment
  Mitigation will be to use existing Legacy MPS FPS hardware
Charge: 1, 2

## Slide 15: Installation Plans
Racks
  Controls Racks will be installed by construction contractors and oversight by SNS Electrical engineers
Cabling
  Cabling will be pulled by contractors or SNS craft
  Cabling will be terminated by SNS Craft or Controls technicians
  PPS Cabling will be terminated by PPS technicians
MPS, Timing and Network Hardware
  MPS, Timing and Network Hardware will be installed by Controls technicians
PPS Interface
  PPS Interfaces will be installed by PPS technicians
Charge: 2
Charge: 2

## Slide 16: Installation Plans
Charge: 2,5
Install Controls Racks
Install Timing and Network
Install MPS

## Slide 17: Schedule
Charge: 2

## Slide 18: Cost and Schedule
Changes Since CD – 2/3
P03.08 at 57%
P03.09 at 57%
Charge: 2

## Slide 19: Cost and Schedule
Charge: 2
ETC is well understood and achievable for all 3 WBS

## Slide 20: Estimate to Complete by FY
Charge: 2
Chart: P.03.08 RF Controls
| FY2021 | FY2022 | FY2023 | FY2024 | FY2025
Actual Cost Oct - May FY21 | 106.0883
Labor | 87.9248 | 210.5213 | 45.0564 | 24.7349 | 0
Material | 59.3372 | 0 | 0 | 0 | 0

## Slide 21: Estimate to Complete by FY
Charge: 2
Chart: P.03.09 RF/SCL Global Controls
| FY2021 | FY2022 | FY2023 | FY2024 | FY2025
Actual Cost Oct - May FY21 | 166.7989
Labor | 108.3701 | 138.5007 | 17.8289 | 10.05 | 0
Material | 17.0534 | 22.9911 | 0 | 0 | 0

## Slide 22: Labor Profile
RF Controls is composed of Software, Hardware and Process Control Engineer for the duration of remaining work.
Charge: 5

## Slide 23: Labor Profile
Charge: 5
FY2021 is divided between subcontract, Technician/RM and Engineer support.
FY2022, FY2023, and FY2024 is split between Technician/RM and Engineer Support

## Slide 24: Risk Register
One active risk identified
  One retired risk
  Pre-mitigated ranking: 1 Medium
  Post-mitigated ranking: 1 Low
High Risks
  No high risks identified
Key risk categories analyzed
  Requirements
  Staff availability
Risks are reviewed on a regular basis
Risk ID | L3 WBS | Risk Title | Expiration Date | Mitigation | Pre-Mitigation Rank | Post Mitigation Rank
T-P.3-012 | P.03.08 | Controls Software Requirements | 7/31/2021 | Carefully monitor development of requirements to push completion prior to software development. Perform requirements reviews for complex areas. | 12 | 4
Charge: 2, 5

## Slide 25: Responses to Recommendations
No Recommendations from CD-2/3 Review
Charge: 6

## Slide 26: ESH&Q and COVID-19 Impacts
ESH&Q
  No issues or concerns
  Racks and PPS Chassis are already UL certified
Covid-19 impacts
  No major impacts to the PPU schedule
  Delay from MicroTCA Vendor
    MicroTCA Processor Cards delayed 4 months
    Still can achieve installation schedule
  Quarantine issues
    Working remotely has allowed the team to stay on track despite several quarantines at all levels
Charge: 3

## Slide 27: 12-month look ahead
P.3.8.2 HPRF
  Support Factory Acceptance Testing of Transmitters
  Integrate controls for Transmitter 30 and 31
  Integrate controls for Modulator 30
P.3.8.2 LLRF
  Support final software development for new LLRF platform
  Integrate new Timing Receiver card
  Support continued production cavity testing
Charge: 1,4
B3-3 Crofford

## Slide 28: 12-month look ahead
P.3.9.2 Linac/SCL Timing/MPS
  Complete Rack installation in the Klystron Gallery Buildout
  Install Timing infrastructure and fanouts in Klystron Communication Room 6 and new LLRF and Controls Racks
  Install fiber patch panels and fiber for Timing, MPS and Network
P.3.9.3 Linac/SCL Protection System
  Prepare PPU KL-Cab04 software modifications
P.3.9.4 Linac/SCL networking and computing infrastructure
  Install networking hardware in Klystron Communication Room 6 and PPU racks
  Install wall mounted PC in the Klystron Gallery Buildout
Charge: 1,4

## Slide 29: Summary
All RF and Global Controls are on schedule
Controls hardware designs are well established
  Timing, Network and PPS hardware is already in production use
  MPS hardware has final design approval
Firmware and Software designs are in final stages
  HPRF PLC code and Software are well defined and extensions of existing systems
  LLRF Software has made good progress and is a high priority
  MPS firmware and software are in final stages and targeted to be completed before being needed for PPU