## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
Angel Berrocal
FTS Controls Integration
September 14-17, 2021
P.5.10.3 First Target Station Controls

## Slide 2: P.5.10.3 Scope
Control System is based on existing EPICS architecture
Architecture remains the same for PPU
EPICS architecture is scalable and extensible
Adding more network nodes, IOCs, PLCs
Modifying systems to support additional hardware for Target controls integration

## Slide 3: P.5.10.3 Design Phases
Control Integration design are managed in Phases
  Phase 1 (Conceptual)
  Phase 2 (Preliminary)
  Phase 3 (Final)

## Slide 4: P.5.10.3 Scope
Ethernet IP Star Configuration
Ethernet IP Multiple Ring Configuration
Ethernet IP Ring Configuration
Diverse types of signals will be provided as deemed necessary to ensure reliability of the system
Signals critical to beam production will be redundant to ensure reliability and ensure uptime is maximized
Target Controls will be distributed to SNS standard PLCs/IOC pairs for each target subsystem to facilitate maintenance
PPU FTS control integration scope includes controls integration up to connectivity to instrumentations, Allen Bradley Control/Compact Logix PLC, Ethernet IP Ring topology architecture for redundancy, and operator interface (EPICS)
Charge: 1,4

## Slide 5: P.5.10.3 Scope
Hydrogen Refill System (HRS)
  New PLC enclosure to control
  Monitor CMS Hydrogen supply
  Control cabinet will be in building 8760 compressor room
Mercury Off-Gas Treatment System (MOTS)
  New PLC enclosure to control
  Monitor Tritium and Xenon removal systems
  Control Cabinet will be in building 8700 baseman
Gas Recirculation (GR)
  New PLC enclosure to control and monitor Target Gas Injection
  Include a Molecular Sieve as a subsystem.
  Control Cabinet will be in building 8700 baseman
Charge: 1,4
Hydrogen Refill System
Mercury of Treatment System
Gas Recirculation

## Slide 6: P.5.10.3 Scope
Gas Panel 10
Gas Panel 10 (GP10)
  Control cabinet 8780 upgrade
  Additional PLC in the Mercury Loop Recovery
Catalyst
  Adding six Pressure Transmitters and six Temperature Transmitters in existing CMS circulator system
  Drawings will be upgraded
Mercury Process System (MPS)
  Adding Level Sensor for the Mercury Pump Overflow Tank
  Cabinet 8530 drawings will be upgraded
  The preferred design concept is to make use of the existing Rocket GLS penetration and junction boxes
Charge: 1,4
Catalyst
Mercury Process System

## Slide 7: P.5.10.3 Organization
Charge: 5
P.5 First Target Systems
Bernie Riemer
P.5.3 Mercury Process Systems Makayla Edwards
P.5.8 MOTS
Greg Stephens
P.5.7
Instrument System
Oscar Martinez
P.5.4
Moderator
Cryogenic Systems Bernie Riemer
P.5.2
Neutronics
Franz Gallmeier
P.5.9 2 MW Target
Kevin Johns
P.5.6 Target Utility Systems
Erica Ahlschwede
P.5.5 Vessel and Shielding
System
Oscar Martinez
P.5.1
Management
and System Integration Bernie Riemer
P.5.10 Safety, Controls and Operations
Charlotte Barbier
P.5.1.1
Management and System Integration Bernie Riemer
P.5.6.3 Upgrades for 1.3 GeV Systems
Erica Ahlschwede
P.5.6.4 Upgrades for Gas Injection Erica Ahlschwede
P.5.6.2
Evaluations at 1.3 GeV
Erica Ahlschwede
P.5.6.1
Management and System Integration
Erica Ahlschwede
P.5.2.3 System Design Support Franz Gallmeier
P.5.2.4 FTS Source
Performance
Franz Gallmeier
P.5.2.2 Evaluation at 1.3 GeV
Franz Gallmeier
P.5.2.5 FTS Facility Support Franz Gallmeier
P.5.2.1
Management and System Integration
Franz Gallmeier
P.5.3.3 Hg Pump Tank Overflow Makayla Edwards
P.5.3.4 Hg Return GLS
Makayla Edwards
P.5.3.2
Evaluations at 1.3 GeV
Makayla Edwards
P.5.3.5 In-Cell Target Gas Supply
Hardware
Makayla Edwards
P.5.3.1
Management and System Integration Makayla Edwards
P.5.5.1
Management and System Integration
Oscar Martinez
P.5.5.2
Evaluations at 1.3 GeV
Oscar Martinez
P.5.7.1
Management and System Integration
Oscar Martinez
P.5.7.2
Evaluations at 1.3 GeV
Oscar Martinez
P.5.8.2 Additional MOTS delay bed Greg Stephens
P.5.8.3 Upgrades for Gas Injection Greg Stephens
P.5.8.1
Management and System Integration
Greg Stephens
P.5.9.2 Target Module
Kevin Johns
P.5.9.3 Supporting Hardware Kevin Johns
P.5.9.1
Management and System Integration
Kevin Johns
P.5.10.2 System Integration for
Safety
Jacob Platfoot
P.5.10.3 Controls Integration Karen White
P.5.10.1
Management and System Integration Charlotte Barbier
P.5.10.4 Operating Procedures and
Training
Greg Stephens
P.5.8.4 MOTS Cold Trap and Shielding
Greg Stephens
P.5.9.4 PPU Test Target
Drew Winder
P.5.4.1
Management and System Integration Bernie Riemer
P.5.4.2 Ortho-Para Hydrogen Converters Bernie Riemer
P.5.4.3 Ortho-Para Hydrogen
Converter Diag.
Bernie Riemer
P.5.4.4 Hydrogen Refill System Bernie Riemer
P.5.11
Gas Injection Development
Charlotte Barbier
P.5.11.1
Management and System Integration Charlotte Barbier
P.5.11.2
Gas Injection
Charlotte Barbier
Supporting contributors
P.5.10.3 (Controls Integration): Doug Campbell, Terry Kennedy, and Tony Dao

## Slide 8: P.5.10.3 Progress since CD-2/3
HRS
  Phase 2 Schematic Design 100% completed
  Phase 3 Schematic Design 98% completed
  FDR Completed
MOTS
  Phase 1 Design 100% Completed
GR
  Phase 2 Schematic Design GR 100% completed
  Phase 2 Schematic Design Mol Sieve 100% completed
  Phase 3 Schematic Design 10% completed
Charge: 1,3,4
Current HRS location (at capacity)
New inventory location
Hydrogen Refill System
Mercury of Treatment System & Gas Recirculation
Gas Recirculation
Mercury of Treatment System

## Slide 9: P.5.10.3 Progress since CD-2/3
GP10
  Phase 2 Schematic Design 100% completed
  FCSR document completed
  Phase 3 Schematic Design 100% completed
  FDR Completed
Catalyst
  Phase 1 & Phase 2 Design 100% completed
MPS
  Phase 1 Design 64% completed
Charge: 1,3,4
Gas Panel 10
Catalyst
Mercury Process System

## Slide 10: P.5.10.3 Challenges
HRS
  Waiting on vendor BOM to complete Phase 3 schematics
  Instrumentation to be rated for Class 1 Div. 2 Group B using nonincendive fields wiring methods or equivalent
  Will need to work with new ME to finalized design and installation efforts
MOTS
  Phase 2 delayed due to changes in design
  Molecular Sieve P&ID and PCD are not finalized at this time
GR
  P&ID & PCD were not finalized which impacted revisions and rework on design
Charge: 1,3,4,5

## Slide 11: P.5.10.3 Challenges
GP10
  Resources working on other WBS
Catalyst
  Resources working on other WBS
Target Control Systems progress has been delayed because predecessors have been delayed
  Additional resources are working to recover schedule
PCR was approved for Gas Recirculation and MOTS due to mechanical design changes
  This increased the controls scope
Charge: 1,3,4,5

## Slide 12: P.5.10.3 Final Design Status
HRS and GP10 Final Design Review(FDR) completed
  Tracking recommendations, procurement in progress
Catalyst design in progress. MPS is delayed due to resources
  Additional resources can be hire for design
GR and MOTS design currently ongoing
  PCD & P&ID finalized
PLC programming and configuration is getting pushed and will overlap with other activities
  Additional resources can be hire for PLC programming and configuration
Charge: 1,3,4

## Slide 13: P.5.10.3 Installation Plans
Equipment will be procured from external suppliers and control hardware will be assembled by external panel fabricators
Installation of Target Controls hardware will be performed primarily by craft labor with supervision/oversite from FTS Engineers
Testing and commissioning will be performed by FTS engineers and technicians
Work will be performed consistent with QA & Safety requirements
Charge: 1,2,3

## Slide 14: P.5.10.3 Installation Plans
HRS Fabrication
HRS Installation and Programming
HRS Installation and Programming
GP10 Installation & Programming
Gas Recirculation PLC Cabinet & Cable Placement
MPS PLC Cabinet Update, Cable Placement, Programming
MOTS PLC Cabinet & Cable Placement
Catalyst PLC Cabinet Update, Cable Placement, Programming
HRS
GP10
GR
MOTS
CAT
MPS
GP10 Programming
Gas Recirculation Procurement
MOTS Procurement
Catalyst Procurement
MPS Procurement
Gas Recirculation Programming
MOTS Programming
GP10 Procurement,
Charge: 1,2,3

## Slide 15: P.5.10 Cost and Schedule
Charge: 4
P.5.10 is dominated by Control Integration
March PCR resulted in $716K increase
Overall progress in 26% completed

## Slide 16: P.5.10 Cost and Schedule
Charge: 4
Cost are dominated by labor
Chart: P.05.10 Safety, Controls and Operations
| FY2021 | FY2022 | FY2023 | FY2024 | FY2025
Actual Cost Oct - May FY21 | 418.3136
Labor | 552.2683 | 741.5076 | 862.0931 | 0 | 0
Material | 22.3435 | 177.148 | 0 | 0 | 0

## Slide 17: P.5.10 Labor Profile
Charge: 5

## Slide 18: P.05.10 Safety, Controls and Operations Risk Register
Two active risks identified
  One risk retired
  Pre-mitigated ranking: 2 Medium
  Post-mitigated ranking: 1 Low, 1 Medium
High Risks
  No high risks identified
Key risk categories analyzed
  Controls requirements
  Safety
Risks are reviewed on a regular basis
Risk ID | L3 WBS | Risk Title | Expiration Date | Mitigation | Pre-Mitigation Rank | Post Mitigation Rank
T-P.5-024 | P.05.10 | Analysis reveals additional controls and/or protection system requirements for 2 MW target. | 11/1/2022 | Ensure analysis is completed well in advance of CD-2 so proper estimates for target control and protection systems can be developed and included in the project baseline. | 12 | 6
T-P.5-016 | P.05.10 | Failed certification for safety or controls during last outage | 12/1/2023 | Leverage the lessons learned in GI3 to develop a reasonable schedule and make sure some time is in the planning to address any potential failure in any certification. | 12 | 4
B2-10 Platfoot

## Slide 19: P.05.10 Responses to Recommendations
No recommendations from the CD-2/3 review
Charge: 6

## Slide 20: P.05.10.3 ESH&Q and COVID-19 Impacts
Hydrogen Refill System
  Compliant with fire protection engineer
  Compliant with Class 1 Div.2 Group B
COVID-19 impacts
  Due to quarantines, meetings and schedules were delayed
  Project interaction was a challenge with requirements and design, progress move at slower pace
  Despite COVID-19 challenges, project aimed for milestones
Charge: 3

## Slide 21: P.05.10.3 12-Month Look-Ahead
Hydrogen Refill System
  Procurement and cabinet fabrication
  Phase 2 & 3 for PLC and HMI configuration and programming
MOTS
  Phase 2 & 3 schematics design
  Phase 2 & 3 for PLC configuration and programming
  Procurement and cabinet fabrication
Gas Recirculation
  Phase 3 GR schematics design
  Phase 2 & 3 for PLC configuration and programming
  Procurement and cabinet fabrication
Charge: 1-5

## Slide 22: P.05.10.3 12-Month Look-Ahead
Gas Panel 10
  Procurement and cabinet upgrade
  Phase 2 & 3 for PLC configuration and programming
Catalyst
  Phase 3 for schematics design
  Phase 2 & 3 for PLC configuration and programming
  Procurement and cabinet upgrade
Mercury Process System
  Phase 2, & 3 for schematic design & PLC configuration and programming
  Procurement and cabinet upgrade
Charge: 1-5

## Slide 23: Summary
Target Control Systems has progress well to further develop the design
Scope is understood and meets FTS performance requirements
Interfaces for Target Controls are well defined for this stage of the project
Activities and cost are well developed and will be refined as the Target Systems design evolves
Schedule is integrated with Target Systems design schedule to support project completion dates
Thank you for your time!
Questions?