## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
Mandy Greenwood
Risk Manager
September 14-17, 2021
Risk Analysis

## Slide 2: PPU Risk Management System
Risk management has been implemented on the project since prior to CD-1
PPU has utilized the services of Dr. Keith Molenaar (Professor, University of Colorado) to assist the project in better understanding and identifying associated risks
Project has a pro-active approach to risk management that focuses on continual evaluation and monitoring
Risk manager is responsible for working closely with project CAMs to review the risks and uncertainty to ensure a complete contingency needs analysis

## Slide 3: Contingency Development

## Slide 4: Templates guide the Monte Carlo analysis
Suggested ranges are provided to assist the project team in determining appropriate 3-point ranges for their work scope

## Slide 5: Monte Carlo Cost Uncertainty at P80
Cost Uncertainty and Risk Exposure - Mitigated
80% confidence remain cost will not exceed $142M
100% confidence remain cost will not exceed $149M

## Slide 6: Cost Risk Exposure Decreases with Mitigation
Charge: 5c
Mitigations cost ~$900K and reduce cost risk exposure by $5M

## Slide 7: Monte Carlo Schedule Uncertainty at P80
Duration Uncertainty and Risk Exposure - Mitigated
80% confidence: schedule EF will not exceed 6/27/25
100% confidence: schedule EF will not exceed 7/14/26
Baseline EF: 2/12/25 Baseline LF: 7/31/28

## Slide 8: Schedule Risk Exposure Decreases with Mitigation
Charge: 5c
Mitigations cost ~$900K and reduce schedule risk exposure by 5 months

## Slide 9: Risks are identified and understood
Risk register populated by PPU team members (CAMs, SMEs, technical staff and L2 Managers)
All risks are approved by the Risk Advisory Board
Includes project and operations risks
Mitigation costs associated with the event risks are included in the baseline estimate, as needed
Risks are continually evaluated and monitored
Charges: 5c, 5d

## Slide 10: Risk Register
Forty-nine risks
  80 Threats and 16 Opportunities have been retired. 6 Threats and 3 Opportunities have been realized
  Pre-Mitigated Ranking: 11 Low, 34 Medium, 4 High
  Post-Mitigated Ranking: 24 Low, 23 Medium, 2 High
High Risks
  COVID-19 Impacts Project Cost or Schedule
    Mitigation: Frequent vendor communication, use of alternate vendors if needed, vendor oversight by local experts, vaccinations, masking, social distancing, and work-from-home
  Fermilab has competing projects or resource issues
    Mitigation: Maintain good communication between PPU and Fermilab so that schedule challenges can be discovered early and mitigated. Engage project management and Fermilab management as needed to ensure this work receives adequate priority. Perform periodic visits to Fermilab to assess progress
Key risk categories analyzed
  Vendor delivery delays
  Budget cycle
  Resource availability
8 New Risks identified since CD-2/3
Charges: 4b, 5c

## Slide 11: Risk Identification
Risks are reviewed monthly in Metrics Meetings
Charge: 4b

## Slide 12: Cost Risk Drivers at P80
Cost Uncertainty and Risk Exposure - Mitigated
Risk drivers for cost risk exposure are reasonable and appropriate
Cost risk drivers are risk events contributing significantly to cost risk exposure

## Slide 13: Cost Activity Drivers at P80
Cost Uncertainty and Risk Exposure - Mitigated
Activity drivers for cost risk exposure are reasonable and appropriate
Cost activity drivers are activities contributing significantly to cost risk exposure

## Slide 14: Schedule Risk Drivers at P80
Duration Uncertainty and Risk Exposure - Mitigated
Risk drivers for schedule risk exposure are reasonable and appropriate
Schedule risk drivers are risk events contributing significantly to schedule risk exposure

## Slide 15: Schedule Activity Drivers at P80
Duration Uncertainty and Risk Exposure - Mitigated
Activity drivers for schedule risk exposure are reasonable and appropriate
Schedule activity drivers are activities contributing significantly to schedule risk exposure

## Slide 16: Contingency development by WBS
Schedule Contingency:
~ 4.5 months per Monte Carlo analysis
~ 12 months by Management Assessment due to COVID-19
~ 22 months by Management Assessment due to 1250hr Target KPP
Charge: 4b
Baseline Values:
~ $53M Contingency
~ 42 months schedule contingency

## Slide 17: Monte Carlo Simulation Compared to Expected Value

## Slide 18: Risk Burn-down
Chart: 
| 43952 | 43983 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166 | 44197 | 44228 | 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692 | 46722 | 46753 | 46784 | 46813 | 46844 | 46874 | 46905 | 46935
Base | 63258000 | 62036500 | 60815000 | 59593500 | 58372000 | 57150500 | 55929000 | 54707500 | 53486000 | 52264500 | 51043000 | 49821500 | 48600000
Contingency Surplus | -888000 | 333500 | 1555000 | 2776500 | 3998000 | 5429278 | 6993312 | 8455988.9596 | 9152776.1296 | 9113472.4896 | 8589274.2396 | 6002520.8496 | 4738000
Actual Risk Expiration | 63258000 | 62036500 | 60815000 | 59593500 | 58372000 | 57150500 | 55929000 | 54707500 | 53486000 | 52264500 | 51043000 | 49821500 | 48600000
Risk Realization
Project Contingency | 62370000 | 62370000 | 62370000 | 62370000 | 62370000 | 62579778 | 62922312 | 63163488.9596 | 62638776.1296 | 61377972.4896 | 59632274.2396 | 55824020.8496 | 53338000
Contingency is adequate to cover remaining risks based on risk analysis

## Slide 19: Contingency is sufficient for the project
Monte Carlo analysis, using cost & schedule uncertainty with event risks, was performed to define the project contingency needs
Acumen Risk P80 analysis showed an overall contingency need of ~30%
After assessment by management, the value was increased to 47%, providing a high confidence level
Contingency based on:
“Bottom-up“ cost and schedule uncertainty analyses and identified risk events by the CAMs
Management Assessment contingency included to address unidentified project impacts.
Charge: 4b

## Slide 20: Summary
  Project is pro-active in risk management and has been actively performing risk analysis since prior to CD-1
  Project is 53% complete with an ETC of ~$103M and an available contingency of ~$53M
  52% contingency on work to go
  PPU has a Contingency Spend Plan that the project will utilize for making contingency usage decisions per the PEP.
B8-7 - Champion
Charge: 5d

## Slide 21: End

## Slide 22: Backup
3 Realized Opportunities
  O-P.1-001 PPU is considered LI project
  O-P.1-003 On-site ORNL provided storage becomes available
  O-P.4-001 Extraction kicker system does not need new magnets
6 Realized Threats
  T-P.2-005 Cavity Delivery Is Late
  T-P.2-018 End Can Delivery Is Late
  T-P.2-021 Vacuum Vessel Delivery Is Late
  T-P.6-010 Construction competition for Klystron Gallery
  T-P.6-008 Delay in Tie-Ins to Klystron Gallery Utilities
  T-P.6-009 Schedule pressure requires Klystron Gallery installation to be concurrent with CF Construction