## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
John Galambos
Director
September 14–17, 2021
PPU Project Overview

## Slide 2: Agenda: focus on break-out / executive sessions
Plenary
Sub-committee breakout sessions
Executive sessions

## Slide 3: PPU overview
PPU doubles Spallation Neutron Source (SNS) power capability from 1.4 MW to 2.8 MW
  30% beam energy increase, 50% beam current increase
2 MW to First Target Station
Linac
Accumulator Ring
First Target Station (FTS)
Future
Second Target Station (STS)
PPU scope is in blue areas

## Slide 4: Proton Power Upgrade project scope
Radio Frequency (RF) system upgrades
Additions for new cryomodules
Upgrades for existing systems
LINAC
Front-End
Upgrade
Extraction
Collimators
7 new superconducting linac cryomodules
Conventional facility upgrades
Target system upgrades
Ring system upgrades
Primarily injection and extraction
Includes scope across much of the neutron source
Charge: 2

## Slide 5: PPU has been busy the past 3 years: LLPs + CD-2/3
FY 19: Tailored strategy leveraging use of proven designs
  CD-3A: ~$10 M for superconducting RF cavities
  CD-3B: ~ $53 M for superconducting cryomodules, RF and klystron gallery buildout
FY 20: Combined CD-2/3 review
  Final design was > 90% complete mid 2020
FY 21: Execute LLPs + CD-3 scope
Jan
2018
Jan
2019
CD-1 approved
$36M FY18 enacted
$60M FY19 enacted
CD-3A approved
Jan
2020
CD-3B approved
Jan
2021
$60M FY20 enacted
CD-2/3 approval
$55M FY21 enacted

## Slide 6: Project baseline parameters
Key Performance Parameter | Thresholds | Objectives
Beam power on target | 1.7 MW at 1.25 GeV | 2.0 MW at 1.3 GeV
Beam energy | 1.25 GeV | 1.3 GeV
Target operational time without failure | 1,250 hours at 1.7 MW | 1,250 hours at 2 MW
Stored beam intensity in ring | > 1.6x1014 protons at 1.25 GeV | > 2.24x1014 protons at 1.3 GeV
KPPs require upgrades to be fully functional
Baseline TPC is $272M
CD-4 is Q4 FY2028

## Slide 7: The past year we made good progress
 | 1 year ago (July 2020) | Now (July 2021)
% complete (earned value) | 33% | 57%
Contingency relative to ETC | 45% | 59%
Early finish* | 1/24/2025 | 2/12/2025
Dodged bullet for initial COVID impact
Generally maintained overall schedule
  Procurements
  Component fabrication
  Construction
Close to predicted cost estimate
* CD-4 (late finish) is July 31 FY2028
B8-2 Steffey

## Slide 8: Integrated Project Team has new members
Harriet Kung
Kurt Fisher
Linda Horton
Linda Horton
Johnny Moore
Wendy Cain
(James Barnard previously)
John Galambos
Mark Champion
Sang-Ho Kim
Wayne Steffey
Hannibal Joma
(Ed Stevens previously)
Thomas Zacharia

## Slide 9: PPU project organization is largely stable
Ken Andersen replaced Paul Langan
Currently being reconstituted
Nick Evans replaced Charlotte Barbier

## Slide 10: Partner lab coordination is going well
We have resumed in person visits to JLab
  COVID prevented travel until May 2021
Regular video conference updates, weekly/monthly status reports
  Longstanding positive relationship between JLab and SNS
B8-6 Daly

## Slide 11: Cost contingency is healthy at > 50% on Estimate to Complete
Have a contingency spend plan and process for allocating contingency
+ and – cost changes balance
Net negative draws on contingency (COVID ?)
A2 - Champion
B8-1 - Galambos

## Slide 12: Gradual power ramp-up over 2023-2024 drives schedule
Incorporates new equipment as it arrives – red shaded areas indicate downtimes
One 10 month extended outage in 2023
B8-8 Johns
B8-7 Champion
B8-9 Peters

## Slide 13: PPU plans are integrated in the “5-year” NScD directorate plan
See https://neutrons.ornl.gov/hfir/hfir-sns-5-year-working-schedule
Tradeoffs communicated with our BES sponsor

## Slide 14: SCL systems: cryomodule production ramping up
Cavities received in good shape
Cryomodule production proceeding well at JLab
  84 of 93 procurements at JLab
  2 string assemblies complete
  Spare cryomodule added
Cryomodule vacuum vessel
String assembly
Cold mass assembly

## Slide 15: RF Systems: Procurements on track for power ramp-up
Transmitter cooling cart at vendor
HVCM fabrication at vendor
1st article circulator received
LLRF test operation on SNS
Klystrons being received on site (working too!)

## Slide 16: Ring systems: magnet final designs complete, focus on fabrication
Current pickups in tunnel for beam power limiting system
Injection dump imaging system: on track for install in FY22
FNAL is fabricating new injection magnets

## Slide 17: Target systems: target manufacture and sub-system component fabrication going well
Test target 1 assembly
Delay bed carbon cartridge and vessel
Mercury pump overflow tank mockup test

## Slide 18: Conventional facilities: klystron gallery buildout is complete: BIM helped
See: https://neutrons.ornl.gov/klystron-virtual-tour
Complicated piping sections are fabricated offsite
And lifted / positioned into place:
easier than fabricating in place
(BIM = Building Information Modeling)
B5-2 Santee

## Slide 19: BIM transformation from virtual to reality

## Slide 20: Klystron gallery activity videos
Under Project Information - Klystron gallery construction video
February 2020
Under Project Information - Klystron gallery Installation Video
August 2021

## Slide 21: ESH&Q
COVID: impacted on on-site activities (e.g. klystron gallery construction)
QA: heavy involvement in procurement activities and acceptance
PPU is using the same work control practices as operations
Safety: continuous presence on CF and installation activities
B8-4 McKenzie

## Slide 22: COVID impacts have not been severe … so far
Critical PPU staff were permitted on site throughout COVID
  E.g. klystron gallery construction
  There was a schedule impact – but we worked around this
ORNL return to full onsite presence on hold
  (84% staff vaccinated)
JLab site access has been more restrictive than ORNL
  Onsite presence has permitted equipment acceptance and cryomodule fabrication
Vendor performance
  Initially not many direct COVID related delays, but over the past months we are starting to get more delay requests
But there are some indications of potential issues
  Recent trend of change requests: cost increases
  Issues finding resources
B8-6 Daly

## Slide 23: Installation has begun and outage planning is refined
PPU Installation is ongoing
  Klystron gallery equipment is being installed
  Electrical tie-ins are occurring in outages
Outage plans include more refined estimates
  ARR execution durations are increased
Coordination with operations
  E.g. RFQ swap delayed to after the long outage
B8-7 Champion
B8-8 Johns

## Slide 24: What worries me (1 year ago at CD-2/3)
COVID impact on vendor deliveries
  Survived initial impact, but still have concerns
CD-3B activities, moving beyond procurements
  The project mentality has switched to “fabrication/construction”
Targets: manufacturing / schedule for power ramp-up
  Target manufacturing is going well
  Power ramp-up schedule is maintained
Long outage: coordinating activities
  More realism is now included
  Better coordination / communication with operations and sponsor

## Slide 25: What worries me (looking forward)
Maintaining equipment delivery schedules
COVID secondary impacts
  Cost/schedule, resource availability, staff returning to campus
Target stub planning

## Slide 26: Summary
PPU has transitioned from “design” to “construction” mode
We survived COVID in relatively good shape
Now concerns are shifted to equipment delivery, installation and outage coordination

## Slide 27: Backup