## Slide 1
DOE/SC Independent Project Review of the Proton Power Upgrade Project
Jacob Harris
JLab Quality Assurance Representative
September 14 – 17, 2021
P.2.3 Cryomodules Integration

## Slide 2: Outline
Scope
Organization & WBS
Three Keys to JLab QA Success
  SNS PPU and JLab QA
  Lessons Learned vs Lessons Applied
  JLab’s Data-Driven Approach
12-month look-ahead
Summary
Charge: 3
SNS PPU and JLab QA
Lessons Learned / Lessons Applied
Data- Driven Approach

## Slide 3: Scope – P.2.3 Cryomodules Integration
Original procurement scope was included in CD-3B
Scope changed to include an additional 8th cryomodule
Design high-beta cryomodule and associated tooling
  Includes assembly and shipping tooling
Procure components
  Entire cryomodule bill of materials except for cavities and couplers
Receive and inspect components
Qualify (32) cavities; install helium vessels
Assemble (8) cavity strings
Assemble and test (8) cryomodules
Ship (8) cryomodules from JLab to ORNL / SNS
Charge: 5

## Slide 4: Work Breakdown Structure
Charge: 5
P.2 – SCL
Matt Howell
P.2.4
Cryogenics
Brian DeGraff
P.2.3
Cryomodules Integration Ed Daly
P.2.5 Utility Systems Chris Stone
P.2.2 Cavities
John Mammosser
P.2.6 System Integration
John Mammosser
P.2.1
Management and System Integration Matt Howell
P.2.7 SCL Controls Karen White
P.2.1.1
Management and System Integration
Matt Howell
P.2.2.4 Cavity Reprocessing
John Mammosser
P.2.2.5 Coupler Acquisition Yoon Kang
P.2.2.2 Cavity Procurement
John Mammosser
P.2.2.7 HTA Testing
Brian Degraff
P.2.2.1
Management and System Integration
John Mammosser
P.2.5.2 Beamline Vacuum
Chris Stone
P.2.5.3 Insulating Vacuum System
Chris Stone
P.2.5.1
Management and System Integration
Chris Stone
P.2.5.4 Water Systems Klent Pope
P.2.7.2 Linac Beamline Vacuum
Controls
Derrick Williams
P.2.7.3 Linac Insulating Vacuum System Controls
Derrick Williams
P.2.7.1
Management and System Integration
Aaron Coleman
P.2.7.4
Cryomodule Controls Aaron Coleman
P.2.2.8 Coupler Waveguide Transition Yoon Kang
Partner Lab
P.2.4.1
Management and System Integration
Brian Degraff
P.2.4.2 Cryogenic Components Brian Degraff
P.2.4.3 Cryogenics System Testing
Brian Degraff
P.2.6.1
Management and System Integration
John Mammosser
P.2.6.2 Completed Cryomodule
Testing
John Mammosser
P.2.6.3
Cryomodule in Tunnel
John Mammosser
P.2.6.4
Cryomodule Testing in Tunnel John Mammosser
P.2.6.5 Plasma Process MB Cryo. John Mammosser

## Slide 5: Organization @ Jefferson Lab – SNS PPU Project Team
Charge: 5
JLab Project Team in place since August 2018
J. Harris joined as Quality Assurance Representative

## Slide 6: Jefferson Lab Quality Assurance
Charge: 3
Quality is our commitment to deliver world-class SRF products and services that are worthy of our customers trust by
  Enabling and empowering our people to build safety, reliability, quality, and compliance into our products, technologies, and services
  Delivering products to plan that support system reliability, availability, and that yield a great customer experience
  Measuring our quality objectives and driving systemic continual improvement
  Proactively and transparently engaging our customers
SRF Operations Quality Policy

## Slide 7: Jefferson Lab Quality Assurance
Charge: 3
Satisfies SNS PPU QA and JLab QA requirements
Approved by SNS PPU Project Team
Describes unique SNS PPU QA requirements
  e.g. standard vs non-standard NCRs
SNS PPU Quality Assurance Plan
JLab Quality Assurance Plan
JLab SNS PPU SQAP
JLab Supplemental Quality Assurance Plan

## Slide 8: SNS PPU and JLAB QA Interface
Standard NCR. Nonconformance Reports resolved through standard practices such as high-pressure rinse, lapping, or product replacement, and the final disposition results in an acceptable product.
Non-Standard NCR. Failure to meet PPU High Beta Cavity and Cryomodule Performance Requirements and Minimum Acceptance Criteria documents. Other conditions which are likely to lead to a critical failure in fit, form, or function, or which require non-routine repairs.
Example of a recent Non-Standard NCR
Vendor #1 fabricated heat exchangers (HX) and sent them to Vendor #2 for installation into end cans.
Vendor #2 inspected HXs under JLab contract, and informed JLab of defects to the HXs.
JLab investigated and proposed a solution to SNS PPU in a written report.
SNS PPU approved the written report.
JLab generates NCRs and includes the report.
Charge: 3

## Slide 9: Lessons Learned vs Lessons Applied
Receiving
Inventory
Issuance
Cavity Processing
Vertical Test
Cavity String Assembly
Cold Mass Assembly
He Tanking
Space Frame
Thermal Shield
Vacuum Vessel
Final Assembly
Cryomodule Test
Cryomodule Shipping
PFMEA Methodology
Facilitated by JLab Performance Assurance.
Work Center Leads and technicians provide input based on traveler steps and experience.
RPN calculated. Focus is on scores >100.
Current Status
27 Failure Modes with an RPN >100
21 Recommended Actions identified
Changes made to work control documents
Process Function | Failure Mode | Potential Effects | Causal Mechanism | Current Process Control(s) | S | O | D | RPN | Recommended Action
Previous Travelers completed | Components not checked for NCR status | Dependent on nature of NCR, use of non-cleared part could have impacts on performance or downstream assembly | Physical tag falls off and database not checked | Canned NCR report available | 7 | 6 | 4 | 168 | Potential use of personnel verification that no NCRs are open
Adjust FPC head and tack weld to cavity end dish | Improperly clocked head | Additional work/issues installing piping | Drawing interpretation, not following procedures | Reference drwg's contained in Traveler/Proc | 5 | 5 | 6 | 150 | Devise engineered solution (tooling)
Hold point to ensure cavity is secure (cleared only by SMEs) | Clearance step missed or disregarded | Dependent on what is wrong | Distraction, complacency | Traveler contains instructions for SME to reference | 8 | 3 | 5 | 120 | Further detail the traveler list (itemize)
Remove coupler lollipop | Inspection of cavity in prior step not conducted correctly or thoroughly | Fallen cavity | Inattention, or perhaps lack of sufficient training | Tooling has an engineered control to allow visual load release | 8 | 3 | 3 | 72 | SME to remain and witness lollipop removal
Cavity Helium Tanking
Charge: 3

## Slide 10: Jefferson Lab’s Data-Driven Approach
Charge: 3
Inventory Travelers
Inspection Travelers
Production Travelers
Components Delivered
Parts Received
Shipping data
Inspection and test results
Vendor data
  Part Assembly
  In-progress testing
Serialization
NCR/D3 Travelers
  Digital segregation
Calibration Tracking Module
PRIMeS system for Inventory Travelers
Pansophy system for other Travelers and work control documents.

## Slide 11: Jefferson Lab’s Data-Driven Approach
Age of Open NCRs
Monitored regularly.
Timeliness discussed in SRF project meetings.
Charge: 3
Histogram of NCR Categories
Monitored regularly.
Outliers quickly identified and evaluated.
Quality Reports

## Slide 12: Jefferson Lab’s Data-Driven Approach
Cavity Status Board
Status of key travelers, including NCRs, for each cavity.
Charge: 3
Cavity Performance
Quality Reports

## Slide 13: 12-Month Look-Ahead
Complete the PFMEA and implement risk mitigation steps into work control documents.
Continue to develop QA Reports and make them available to SNS PPU.
Finalize the data packet to be delivered with each Cryomodule.
Continually improve the JLab Quality Management System
Charge: 3

## Slide 14: Summary
Jefferson Lab’s SQAP is aligned to SNS PPU QA Plan, resulting in effective interaction and mutually agreed upon results.
Lessons learned are applied through a PFMEA which results in improved travelers and lower risk.
A data-driven process approach is pervasive through all aspects of work performed at Jefferson Lab. This rich dataset allows for critical self-inspection and transparency to SNS PPU.
Charge: 3