## QIKR Motion WBS Components
FMEA
Process/Product Name: |  | QIKR Detector |  |  |  | Quality Level: |  |  | 2
Responsible: |  | Danielle Wilson |  |  |  | FMEA Date (Orig.): |  |  | 2024-12-04 | (Rev.): | 0
[6 empty] | Prepared By: |  |  | Danielle Wilson
Process Step/Input/System | Potential Failure Mode | Potential Failure Effects | SEVERITY (1 - 10) | Potential Causes | OCCURRENCE (1 - 10) | Current Controls | DETECTION (1 - 10) | RPN | Potential Action Recommended | Resp. | Actions Taken | SEVERITY (1 - 10) | OCCURRENCE (1 - 10) | DETECTION (1 - 10) | RPN
What is the process step, change or feature under investigation? | In what ways could the step, change or feature go wrong? | What is the impact on the customer if this failure is not prevented or corrected? |  | What causes the step, change or feature to go wrong? (how could it occur?) |  | What controls exist that either prevent or detect the failure? |  |  | What are the recommended actions for reducing the occurrence of the cause or improving detection? | Who is responsible for making sure the actions are completed? | What actions were completed (and when) with respect to the RPN?
Detector | Can't change the camera focus | Not expected to be something the user will routinely do, but could impact data collection if the focus can't be changed when needed | 3 | Motor, motor cable, leadscrew, guide rails, or motor controller fails | 2 | 1) Cable routing chosen to be out of the user's way 2) Components are protected beneath radiation shielding | 5 | 30 | Have a scheduled maintenance (lubrication) for the lead screw and guide rails
Detector | Aperture cannot be adjusted | Calibration and normalization takes much longer | 4 | If the aperture is motorized, motor could fail | 2 | 1) Will select an aperture that can also be adjusted manually 2) Components are protected beneath radiation shielding | 1 | 8 | None
Detector | Camera fails | User cannot perform their experiment | 10 | Radiation damages the camera, internal camera failure | 2 | Radiation shielding is placed around the camera. No controls exist for internal camera failure. | 2 | 40 | Should have a spare on hand
Detector | Intensifier fails | User cannot perform their experiment | 10 | high voltage unit burns out | 3 | There are no controls to prevent the intensifier itself from failing | 2 | 60 | Should have a spare on hand
Detector | Intensifier fails | Intensifier has a permanent after-image burned into the microchannel plate (MCP) | 7 | Excessive light input to the intensifier, perhaps from the user opening the detector box without unplugging the intensifier first | 7 | No controls except the detector output… intensifier damage will be visible in the data | 3 | 147 | 1) Could modify the detector box to prevent removing the lid without unplugging the intensifier 2) Add a sticker to the box to notifiy the user to unplug the intensifier before opening the box lid 3) Have a spare on hand
Detector | Scintillator layer is damaged | Damage can be seen in the data | 4 | Opening the detector box lid to change lenses (for example) & accidentally scratching the scintillator surface | 2 | None | 5 | 40 | Propose a check on the data before and after opening the box lid
Detector | Mirror is damaged | Damage can be seen in the data | 7 | Opening the detector box lid to change lenses (foe example) & accidentally scratching the mirror surface or shifting the mirror | 3 | None | 2 | 42 | Propose a check on the data before and after opening the box lid
Detector | Background shielding is not sufficient to block extraneous radiation | Data would be of lower quality, signal to noise ratio would be higher | 6 | Background shielding is not thick enough, or not of an optimal composition | 1 | 1) Thickness is significantly larger than we think we'll need, consists of borated polyethylene lined with boron carbide, which should be the correct materials to stop the spectrum of neutrons we expect to see. 2) The shielding is removable/replaceable should the need arise. | 1 | 6 | None
Detector | Cables are damaged | User cannot perform their experiment | 10 | Cables are placed where the user can accidently catch them, cable routing runs through motion component pinch points or has insufficient servive loop length to allow full movement of motion components | 3 | Cables are routed away from the user, no loose sections of cable exist except where some amount of service loop is required | 1 | 30 | 1) Ensure during installation that the cable routing and loop allow full motion range of the motion components 2) Have spare cables on hand
Detector | Detector is badly misaligned to the sample & beam and cannot be corrected | For very bad misalignments, there could be missing data | 5 | Incorrect assembly of the detector | 1 | The detector is fairly insensitive to misalignment. Also, the detector assembly will be placed such that it is within an inch of its desired location (other placements are not possible). Current adjustments for the detector allow movement within that range to bring it into the proper alignment. | 1 | 5 | None
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on F14: Wilson, Danielle: Very unlikely that there would be damage to any of these componente… they're not very accessible to the user. The most likely failure cause would be damaged motor cable or connector
Note on H14: Wilson, Danielle: The focus would not normally be changed, so it would not be detected until a change is needed
Note on B15: Wilson, Danielle: For direct beam measurements
Note on H15: Wilson, Danielle: Will be able to tell right away during a direct beam measurement that the aperture is not adjustable
Note on B16: Wilson, Danielle: This assumes we have a single camera. It's possible that the design will have 2 cameras eventually.
Note on D16: Wilson, Danielle: This would change to a 5 if there end up being two cameras in the design. The second camera could still be used even if the first fails. There would be a loss in data quality, but data could still be collected… perhaps with longer run times.
Note on F16: Wilson, Danielle: Have not seen any failures on the camera in testing so far. There is no high voltage to cause potential electrical failures.
Note on H16: Wilson, Danielle: May spend a few minutes determining if the problem is in the camera or the intensifier, but a problem would be immediately obvious
Note on B17: Wilson, Danielle: This assumes we have a single camera. It's possible that the design will have 2 cameras (with two intensifiers) eventually.
Note on D17: Wilson, Danielle: This would change to a 5 if there end up being two cameras in the design. The second camera could still be used even if the first fails. There would be a loss in data quality, but data could still be collected… perhaps with longer run times.
Note on F17: Wilson, Danielle: There has been one that died in testing already. Not expecting that to be a normal occurrence, though.
Note on B18: Wilson, Danielle: This assumes we have a single camera. It's possible that the design will have 2 cameras (with two intensifiers) eventually.
Note on F18: Wilson, Danielle: This is a fairly easy mistake to make
Note on H18: Wilson, Danielle: You'll see the problem immediately in the detector output
Note on H19: Wilson, Danielle: Minor damage would be difficult to see
Note on F20: Wilson, Danielle: More likely to damage the mirror than the scintillator because it is closer to the lens
Note on H20: Wilson, Danielle: Damage to the mirror would be more obvious than scintillator layer damage
Note on F21: Wilson, Danielle: It is very unlikely that the shielding design as it currently stands would not be sufficient.
Note on H21: Wilson, Danielle: Excessive background noise would be immediately seen in the detector output
Note on F22: Wilson, Danielle: No matter how carefully routed, the cables are still exposed and could potentially be damaged
Note on H22: Wilson, Danielle: A cable failure would be immediately detected… depending on which cable were damaged, there would either be no data from the camera, or data that was obviously wrong
Note on F23: Wilson, Danielle: Extreme misalignment that cannot be corrected would be impossibly to do in this design
Note on H23: Wilson, Danielle: Extreme misalignment would be immediately seen in the data

## Severity Scale
Severity Scale
Adapt as appropriate
| Effect | Criteria: Severity of Effect | Ranking
| Very Extreme | User cannot run their experiment within their alloted time window | 10
| Extreme | User might only be able to run <50% of their experiment within their alloted time window, and may only be able to collect <50% of the desired data | 9
| Very High | User may only be able to run >50%, <100% of their experiment within their alloted time window, and may only be able to collect <50% of the desired data | 8
| High | User may only be able to run >50%, <100% of their experiment within their alloted time window, but is able to collect >50% of the desired data | 7
| Moderate | User is able to run all of their experiment and collect >80% of the desired data | 6
| Low | User is able to run all of their experiment and collect 100% of the desired data with <6 hours required to effect repairs or devise a workaround to the failure | 5
| Very Low | User is able to run all of their experiment and collect 100% of the desired data with <4 hours required to effect repairs or devise a workaround to the failure | 4
| Minor | User is able to run all of their experiment and collect 100% of the desired data with <2 hours required to effect repairs or devise a workaround to the failure | 3
| Very Minor | User is able to run all of their experiment and collect 100% of the desired data with <1 hour required to effect repairs or devise a workaround to the failure | 2
| None | No Effect | 1

## Occurrence Scale
Occurrence Scale
| Probability of Failure | Time Period | Per Item Failure Rates | Ranking | Event Frequency Level | Estimated Annual Likelihood of Occurrence | [7 empty] | Description
| Very High | <100% of usage | >= 1 in 2 | 10 |  | Exp | Base | Exp | Exp | Annual |  | Occurs once per
|  | <80% of usage | 1 in 3 | 9 | Anticipated (A) | 10–1 > p > 10-2 | 10 | -1 | -2 | 0.1 | 0.01 | 10 years | 100 years | Incidents that may occur several times during the lifetime of the facility. (Incidents that commonly occur) | SIL 1
| High | <60% of usage | 1 in 8 | 8 | Unlikely (U) | 10-2 > p > 10-4 |  | -2 | -4 | 0.01 | 0.0001 | 100 years | 10,000 years | Events that are not anticipated to occur during the lifetime of the facility. | SIL 2 ~ 4
|  | <50% of usage | 1in 20 | 7 | Extremely Unlikely (EU) | 10-4 > p > 10-6 |  | -4 | -6 | 0.0001 | 1e-06 | 10,000 years | 1,000,000 years | Events that will probably not occur during the life cycle of the facility.
| Moderate | <40% of usage | 1 in 80 | 6 | Beyond Extremely Unlikely (BEU) | 10-6 > p |  | -6 | ∞ | 1e-06 | ∞ | 1,000,000 years | ∞ | Events that are unlikely to occur during the life cycle of the facility.
|  | <30% of usage | 1 in 400 | 5
|  | <20% of usage | 1 in 800 | 4
| Low: | <10% of usage | 1 in 1,500 | 3 | Reference
| Very Low | <5% of usage | 1 in 3,000 | 2
| Remote | 0-2% of usage | 1 in 6000+ | 1

## Detection Scale
Detection Scale
| Detection | Criteria: Likelihood the existence of a defect will be detected by process controls before next or subsequent process, -OR- before exposure to a client | Ranking
| Almost Impossible | No known controls available to detect failure mode | 10
| Very Remote | Very remote likelihood current controls will detect failure mode | 9
| Remote | Remote likelihood current controls will detect failure mode | 8
| Very Low | Very low likelihood current controls will detect failure mode | 7
| Low | Low likelihood current controls will detect failure mode | 6
| Moderate | Moderate likelihood current controls will detect failure mode | 5
| Moderately High | Moderately high likelihood current controls will detect failure mode | 4
| High | High likelihood current controls will detect failure mode | 3
| Very High | Very high likelihood current controls will detect failure mode | 2
| Almost Certain | Current controls almost certain to detect the failure mode. Reliable detection controls are known with similar processes. | 1

## SxO Visualization
Optional Visualization
Severity | 10
9
8
7
6
5
4
3
2
1
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Occurrence