## Slide 1: Overview of Proton Power Upgrade (PPU) and Second Target Station (STS) Projects
Presented to the SNS Accelerator Advisory Committee
John Galambos
PPU Project Director
March 8, 2017

## Slide 2: SNS-PPU to SNS-STS
SNS-PPU upgrades the existing accelerator structure
  Increases neutron flux to existing beam lines
  Provides a platform for SNS-STS
SNS-STS constructs a second target station with an initial suite of 8 beam lines
CD-0 for SNS-PPU and SNS-STS are the same

## Slide 3: PPU impact on first target station science
FTS instruments were designed to operate at 2 MW of proton beam power on target
  Adequate choppers, shielding and detectors
  Higher data rates need evaluation on NOMAD and VISION
Higher neutron flux is useful
  Higher capacity means more experiments, more publications, science impact
    E.g. “mail-in” programs
    More complete parametric studies
  Increased opportunity for method and technology development
  Higher emphasis on rapid sample environment changes
  Grows the user community and enables more programmatic studies
    All instruments are over-subscribed
Big bang for the buck:
~ 10% of the SNS TPC: doubles the accelerator capability

## Slide 4: PPU high level parameters
 | Current SNS 1.4 MW | Full accelerator upgrade capability | FTS 60 Hz operation
Proton beam power capability (MW) | 1.4 | 2.8 | 2.0
Beam energy (GeV) | 0.97 | 1.3 | 1.3
RFQ output peak beam current (mA) | 33 | 46 | 46
Average linac chopping fraction (%) | 22 | 18 | 41
Average macropulse beam current (mA) | 25 | 38 | 27
Energy per pulse (kJ) | 23 | 47 | 33
Pulse repetition rate (Hz) | 60 | 60 | 60
Macro-pulse length (ms) | 1 | 1 | 1
PPU delivers 2.8 MW capable accelerator
Prior to STS, accelerator will run at 2 MW to FTS
50% current increase
33% energy increase
No change

## Slide 5: Accelerator built with upgrade provisions
Tunnel: Fill 7 empty drift sections with cryomodules (space available for 9)
Klystron gallery: empty area for new SRF
LINAC
Front-End
Upgrade
Extraction
Collimators
Ring + transport lines: 96% magnets are 1.3 GeV ready

## Slide 6: Operational improvements ensure technical basis
Spare RFQ :
Improved transmission
Ion source test stand: demonstrated PPU required current
Spare SRF cryomodule: operational since 2012 with PPU gradient
Spare RFQ: tested and provides required PPU transmission
In situ plasma processing: demonstrated cavity gradient improvement
Ring damper system: operational, insurance against instabilities

## Slide 7: PPU: Front-end capability demonstrated
Ion source output
  Operation production source has demonstrated required output
RFQ output
  Measured beam transmitted through new RFQ meets STS requirement
STS Requirement
STS Requirement
Notes: STS – new facility

## Slide 8: SCL systems scope
Increase beam energy from 1.0 GeV to 1.3 GeV
Procure, fabricate, test, install, and commission seven new high beta cryomodules
  Bids solicited from JLab, FNAL and FRIB
Prototype = spare cryomodule in production since 2012 with PPU gradient

## Slide 9: RF systems scope
Additional SCL RF systems to support 7 new cryomodules
  3 modulators, 28 klystrons
Upgrade some existing RF infrastructure
  Using beam based measurements to refine plan
Klystron Gallery
New pump room

## Slide 10: Ring systems scope
Injection and extraction ring upgrades
  Injection area is the primary scope – bids from FNAL,BNL for magnets
Utilities, accelerator physics, injection dump
Ring injection area

## Slide 11: FTS scope: Builds on current FTS target activities
PPU Scope:
2 MW target structure
Evaluate systems for 2 MW, 1.3 GeV operation
High gas rate He injection development
Flow reduces cavitation
Instrumentation provides confidence
2017
2019
2021
2023
PPU target fabrication start
High flow He injection
PPU complete
PPU
Hg target
CD-3
2018
2020
2022
2024
2016
1.4 MW reliable operations
FTS reliability improvements
Hg flow
Initial gas injection
Structural & fabrication
Operations input to design evolution
J-PARC data
Gas injection reduces strain
Jet flow
Std.
Notes: 2017 – 2018 targets will inform PPU target design (current target management plan draft)
  Low flow gas injection (GI3), jet-flow and thickened outer beam window … we will assess pressure wave (strain measurements) and cavitation mitigation (PIE)
Beyond 2018:
  Last 1.4 MW target that can influence PPU target design must be taken out of service in early 2019, i.e., the 1st “Blue” target (flow improvement at sides of outer window)
  Needs time for PIE, analysis and interpretation, concept development to CD-2 level
  Perhaps one more target beyond current target management plan could be operated
    Strain measurements; time for informative PIE is questionable under current operating plan (2/y)
After CD-2b, must allow time for final design & analysis, target fabrication, installation and commissioning
“Chinstrap” target potential features for 2018-19 operation
  Swirl bubblers and / or modest increase in gas flow: smaller bubbles in greater volume fraction
  Further flow modifications for cavitation mitigation
  Incorporate improve pulse simulation techniques if available

## Slide 12: Conventional facilities scope
Build a tunnel stub to facilitate future STS tie in
  New “simpler” approach recently adopted
Klystron gallery build-out, new pump room
“RTBT Stub”

## Slide 13: Major project risks
SCL: partner lab - costs, schedule
RF: RF power margin
FTS: target reliability
Schedule: long outage impacted by operations issue

## Slide 14: CD-1 document preparation
  Acquisition Strategy - ✔
    Alternative selection
  Preliminary Project Execution Plan - ✔
    Key Performance Parameters
  CDR - ✔
  Assumptions / NScD MOU - ✔
Status
✔ Signed / complete
Drafted
  Risk Management Plan - ✔
  PHAR - ✔
  Parameter List - ✔
  QA (use SNS plan) - ✔
  Security Vulnerability - ✔
  NEPA agreement - ✔
  Project Management Plan - ✔
    Staffing, procurement, configuration management

## Slide 15: PPU Key Performance Parameters: negotiated with BES
1 Corresponds to 2.0 MW @ 1.3 GeV and 60 Hz
2 Corresponds to 2.8 MW @ 1.3 GeV and 60 Hz
Key Performance Parameter | Thresholds (Performance Deliverable) | Objectives
Beam Power | 1.7 MW | 2.0 MW
Beam energy | 1.25 GeV | 1.3 GeV
Stored beam intensity in ring | 1.60x1014 protons1 | 2.24x1014 protons2
Number of additional installed cryomodules | 6 | 7

## Slide 16: PPU cost and summary schedule
TPC point cost: $212M
  Range is included , roughly + $20M
  Contingency is 35% (being scrubbed)

## Slide 17: PPU planning
Fall 2016 system reviews
  Technical focus
Dec. 2016 – present
  Focus on cost, schedule, project agenda
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
Long Term
CD-1
CD-2
CD-4
Short Term
Ring, SRF reviews
Director’s review
CD-1
Oct
Nov
Dec
Jan
Feb
March
April
May
June
July
Aug
OPA
IPR
RF, CF reviews
Target review
PM
ICR

## Slide 18: February Director’s Review
Technical scope and basis of cost estimate is generally sound
Cost contingency and risk analysis need development
PPU needs independent mission need (from STS)
  Present CD-0 is with STS (2009)
  Consider removing STS specific scope

## Slide 19: STS status
Firming up technical design basis
High level parameter choice to be finalized in a review April 19-21
  Response to 2016 BESAC panel report
    Frequency: 10-20 Hz
    Long pulse short pulse
Target technical approaches
  Rotating target
  No hot cell

## Slide 20: Rotating target: potential operating advantages but needs manufacturing validation
STS: rotating target test stand with a full-scale proof-of-principle mockup
[6000+ hr test]
25 cm deep x 5 cm high Ta clad W blocks (16 ea)
Target fabrication program underway to address possible issues related to large target segments

## Slide 21: Target hall bunkers: Instrument line maintenance approach
Bunkers extend from a neutron beam distance of ~5.5 meter to 11.5 meter
The open space is required to accommodate relatively large and complex neutron beam line components
Maintenance Shutter
Guide Alignment Mechanism
To Chopper
Moderator
Section view through beam lines 6 and 20

## Slide 22: Beamline layout
Short beamlines one side, long beamlines on the other
“No hot cell” opens up space for other purposes

## Slide 23: STS conventional facilities
From 30,000 ft, STS looks like another FTS – with long beam-lines
Some scope reduction: Gross sq. ft: 380,000 (TDR) to ~290,000 (now)

## Slide 24: STS conventional facilities
Elevation: STS and FTS same elevation
  Sloped proton beam-line is complicated
Instrument layout: short / long segregation
Instrument elevation: tunnel, above, trench
Space needs requirements: initial scrub

## Slide 25: High level schedule
Notional – funding dependent
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
CD-1
CD-2
CD-4
CD-4
CD-1
CD-2
STS
PPU

## Slide 26: Summary
PPU efforts are in full swing
  Preparing for CD-1 in FY2017
  Solid technical basis
  Schedule, cost, supporting documents in progress
STS technical concept is being refined
  Decision on repetition rate soon
  Target system designs are maturing
  Aiming for well defined requirements for conventional facilities