## Slide 1: Status of Linac High Voltage Converter Modulators Upgrades
Presented to the SNS Accelerator Advisory Committee
David E. Anderson
Team Lead, High Voltage & Pulsed Power Systems
March 9, 2017

## Slide 2: Outline
System Introduction
Calendar year 2016 Performance Statistics
Upgrade Installation Status
Development Activities and Progress
PPU Activities and Plans
Conclusion

## Slide 3: Modulators provide pulsed power to high power RF klystrons using 20 kHz switching with IGBTs
Provides up to 135 kV, 1.35 ms pulses at 60 Hz to amplify RF up to 5 MW
3 phases employed to increase output ripple frequency
  Minimizes output filter requirements
  Minimizes fault energy available to klystron
Powers multiple klystrons up to 11 MW peak power
OR

## Slide 4
15 Modulators in 3 different configurations power 92 klystrons to support operation of the Linac
15 modulators, 11 currently with new controllers
Approx. 1.1×106 combined operational hours on all modulators
115 kV
<125 kV
≤135 kV
71 kV
<75 kV
DTL (8.5-10.6 MW peak)
CCL (8.4-9.1 MW peak)
SCL (8.0-8.8 MW peak)

## Slide 5: HVCM downtime summary CY2016 – 18% of total
System | Total Hours | Major (>4 hrs.)
RFQ-Mod* | 6.2 | 1
DTL-Mod3* | 7.5 | -
DTL-Mod5* | 10.1 | -
CCL-Mod1* | 2.7 | -
CCL-Mod2* | 10.9 | 1
CCL-Mod3* | 9.4 | -
CCL-Mod4* | 14.8 | -
SCL-Mod1* | 11.2 | -
SCL-Mod5* | 3.9 | -
SCL-Mod9 | 27.1 | 2
SCL-Mod12 | 0 | -
SCL-Mod14* | 3.5 | -
SCL-Mod15 | 4.4 | -
SCL-Mod18* | 1.3 | -
SCL-Mod21 | 2 | -
TOTAL | 118.6 | 4
3 of 4 major system outages due to arcing of primary bus work
  Both SCL-Mod9 failures from same root cause (arcing of primary bus work)
  CCL-Mod2 failure also arcing of primary bus work
  Polymerized oil and aging Dacron/Mylar/Dacron insulation likely the cause
  In SCL-Mod1 through Mod14 bus work replaced in January, warm linac HVCMs bus work replaced 2015
IGBT gate drivers have gone through several modifications (noise mitigation, permit pulse flattening, disabling features, etc.)
  Not all modifications implemented at same time
  Redesign in process
Multiple oil pump bearing failures, replacing with new thrust bearings
New controller channel access / network / timing issues, majority resolved with updates
*new controller installed

## Slide 6: New controller installation nearing completion
Currently installed in 11/15 production HVCMs and on both test stands with 92,000 combined run hours
Plan to install remaining units during summer 2017 outage
Features in place to support:
  New oil cooling system AIP upgrade
  Remote monitoring and warning/faulting on IGBT gate signals
  Remote access to operating screens
  Remote waveform access with executable LabView interface
  Spare analog channels available for additional HPRF / other monitoring and fault capture

## Slide 7: Other upgrade installation status
All snubber networks installed on all operational, spare and test stand IGBT switch plates
  Permits pulse flattening
  Permits higher DC bus voltage operation
  Mitigates IGBT failures
All gate drivers installed but subsequently modified:
  Increased filter capacitance for reduced gate voltage droop
  Bypassed features that created problems with frequency modulation
  Changed several trip thresholds
  Modified VCE,sat circuitry to Vgate monitor feedback for remote gate monitoring with new controller
  All these changes, combined with some obsolescence issues, require a PCB redesign
New thrust bearings installed in ~33% of operational modulator pump motors
Remote Vgate monitor feedback fibers installed in 4 systems and enabled on 2 systems
New primary bus work and voltage dividers installed in 12/15 operational modulators

## Slide 8: Pulse flattening demonstrated on all new controller HVCMs and currently enabled on several
All 11 installed new controller HVCMs have pulse flattening demonstrated
Pulse flattening current enabled on entire warm linac and SCL-Mod14
Chart: SCL-Mod18 Output Voltage
Chart: CCL-Mod4 Output Voltage

## Slide 9: Obsolete IGBT evaluation ongoing
FZ1200R33KL2C discontinued Nov. 2016
Sufficient spares on-hand for a few years
Evaluating most manufacturers’ compatible modules
  Performed at ±1000 V and ±1200 V on SPTS
  ABB, Dynex, Mitsubishi and Infineon devices
  First test for peak power performance, subsequent tests at full average power
Device | VCES, V | IC, A | Rgate, W | Eon, mJ | Eoff, J
FZ1200R33KL2C | 3300 | 1200 | 0.5 | 144 | 2.5
5SNA1200E330100 | 3300 | 1200 | 0.4 | 71 | 2.84
FZ1200R33HE3 | 3300 | 1200 | pending |  | 
5SNA1500E330300 | 3300 | 1500 | 0.5 | 68 | 2.89
DIM1500ESM33-TS000 | 3300 | 1500 | 0.25 | 32 | 3.64
CM1500HC-66R | 3300 | 1500 | 0.35 | 78 | 3.2
FZ1500R33HE3 | 3300 | 1500 | 0.14/0.25 | 75 | 2.32
5SNA1200G450300 | 4500 | 1200 | 0.5 | 100 | 4.1

## Slide 10: Progress continuing on HVCM boost capacitors
Condenser Products currently utilized in all systems but have exhibited some problems
  New set installed in 2015 on NCL HVCMs
  New set installed during summer 2016 on SCL HVCMs
NWL capacitors currently under evaluation in CCL-Mod1 (~10,000 hrs. operation)
Identical NWL delivered a thermally-instrumented unit in March but had problems. Installed in RFTF in February.
TPC solution shown is metallized poly, also permits tuning of resonant circuit

## Slide 11: Progress continuing on HVCM boost capacitors
TPC solution shown is metallized poly film, also permits tuning of resonant circuit
  Tested in RFTF for 1 year (began 2/11/16, removed 2/16/17
  >3800 operational hours at ≥80% CCL operating voltage levels
  Temperature <120°F (vs. 135-140 on prior film/foil caps)
  New capacitors C = 331.2 nF, s = 0.7 nF
  After 3800 hrs., C = 327.7 nF, s = 1.0 nF, a 1.0% degradation
  No positional-dependent variations
  Need to run an additional ≥4k hours to fit projected lifetime
New RFG86Y0334J capacitors
RFG86Y0334J capacitors after 3800 operational hours

## Slide 12: Switch Plate high current feed rail clamping assembly prototyped and progressing towards installation approval
Damage from non-uniform / inadequate pressure leads to downtime
Prototype clamp system built and tested in HEBT for 100’s of hours
Design review conducted and design will be slightly modified
Damage from a improperly gapped set of bus bars

## Slide 13: Enhanced reliability and reduced MTTR is improved by replacing the existing oil cooling system (AIP-36)
Filter can be swapped during operation Pump/motor assembly can be changed without removing the tank
Internal surface temperatures have dropped by at least 45 ° F
Oil turnover and filtering has improved more than 3X and flow does not decrease during operation
The Barron’s Oil system can be used during operation
Added dissolved gas analyzer (H2, CO, C2H2, & C2H4 (ethylene))
Build in FY17 AIP budget, pending DOE approval
Spray Nozzles
Balancing Valves
Eductors

## Slide 14: The laminated bus promises lower ripple and reduced MTTR for switch plates
Inductance of header cables creates DC bus ripple. This ringing also appears at the output pulse
Removal of most bypass capacitors possible but complete elimination places excessive stress on IGBT snubbers
Ripple significantly reduced with laminated bus as shown below
2nd laminated bus received to be installed in RFTF - still need to design tank alignment fixture
Chart: Bus and snubber ripple with 10 uF per H-bridge, laminated bus, 75 kV output
Chart: Bus and snubber ripple with standard HVCM configuration, cable bus, 75 kV output

## Slide 15: Modulator test stands to support modulator development and testing activities
RFTF HVCM
NCL variant of HVCM
Primarily to support RF- testing & BTF
Secondary mission is NCL HVCM work, PPU
HEBT HVCM
SCL variant of HVCM, PPU-rated beam stick load
Dedicated mission is to support HVCM testing and reliability runs
Most development work is protyped here
Open frame test stand
Prototype efforts
  Alternate topology
  Laminated bus
Affords flexibility and more extensive instrumentation @ limited power levels
Single Phase Test Stand (not shown)
Useful to test IGBT assemblies and pre-qualification of spares
Useful to quantify IGBT and resonant tank element changes
Evolving into a test stand and area for new controller “ready” spares

## Slide 16: The PPU Project requires some development but should achieve comparable reliability
Perform extended reliability testing of warm and cold linac modulators at elevated operating voltages
  Started in HEBT for SCL HVCMs at ±1220 V DC (78 kV 10 klystron load equivalent)
  Scheduled for late March for warm linac CCL configuration
Modify boost transformers and capacitors in warm linac to achieve required higher output voltages, esp. for dual 3.0 MW klystrons
Chart: DC Capacitor Voltage, ±V
| 1135 | 1150 | 1065 | 1130 | 1150 | 1160 | 1170 | 1140
Output Voltage | 71.8 | 74.4 | 69.7 | 73.2 | 74.4 | 74.4 | 75.3 | 73.6
SCL-Mod1
SCL-Mod5
SCL-Mod9
SCL-Mod12
SCL-Mod14
SCL-Mod15
SCL-Mod18
SCL-Mod21
Limit for reliable
operation
10:1
11:1
PPU Operating Levels for
Existing SCL HVCMs w/ 15% margin
HEBT oper.
level

## Slide 17: The Alternate Topology Modulator (AT-HVCM) baseline for 3 new PPU modulators
Tested in HEBT test stand.
Delivering 1.2ms 70kV 100A pulse at 60 Hz
92% efficient ZVS/ZCS power conversion
Thermal run completed
Redesigning production capable rectifiers and boost transformers
Need to run 30 day test at PPU parameters to characterize reliability
Variable frequency operation: 24kHz-19kHz sweep illustrating pulse flattening capability
AØ,BØ,CØ XFMR Primary Currents
Mod Vout ripple (~1.3%)
1.2ms pulse

## Slide 18: The JEMA modulator performed 30-day non-continuous test, returned to Spain
Operated at peak available output power (90 kV, 38 A, 340 kW peak) at extended pulse width (3.5 ms) to achieve ~750 kW average power operation
Completed unattended 24/7 30-day test non-continuous April – November 2016
Resolved technical issues with HV Modules (breakdown issues, failed IGBT), Inverter (gate driver failure) and controls (FPGA and DSP modules)
Reliability acceptable at end of testing period

## Slide 19: Summary
Over 1 million combined operational hours on all HVCM systems to-date
Performance during the last year resulted in more downtime than in recent history
  Equipment is aging
  Need to place a higher priority on preventative maintenance activities
  Major contributors to this downtime is understood and mitigation has been applied or is under development
Major upgrades have been installed in most locations
New HVCM cooling upgrade AIP is ready for installation and awaiting DOE approval
Work continues to address other reliability and performance issues with HVCM systems
PPU work has begun and viable conceptual designs exist for all affected HVCM systems
The JEMA testing effort has been completed