## Slide 1: Fabrication of Major Neutron Source Components
Presented to the SNS Accelerator Advisory Committee
Peter Rosenblad
Manufacturing Team Leader for Source Development and Engineering Group
March 9, 2017

## Slide 2: Outline
What are Major Neutron Source Components?
Manufacturing goals, strategies, internal roles
Present and future inventory status
Present challenges
Summary

## Slide 3: Major neutron source components?
Perishable Components:
  Target Modules
    Inflatable seals, leak detectors, instrumentation, bubblers
  Proton Beam Windows (PBW)
  Inner Reflector Plugs (IRP)
    Moderators, shielding, piping, etc.
  Cryogenic Moderator System (CMS) components
Non-perishable components (all major spares on hand):
  Heat exchanger
  Hg transfer valve
  Hg pump – will require modification / rebuild to comply with gas injection
New Installations
  Gas Injection Components
  PPU equipment

## Slide 4: There is now a dedicated manufacturing team within ISD’s Source Design and Engineering Group

## Slide 5: Manufacturing team goals are established to support operation and design
Confidence in product
On time delivery
Repeatable, conveyable processes
In depth understanding of manufacturing processes and challenges
  Feedback provided to design and manufacturing
Cost control, competition, non-singular supply chain
Traceable (audit strong) processes
Efficient use of budget – planning appropriate spending spread amongst critical components
Successful relationships –more profit for suppliers is good

## Slide 6: The present realities surrounding source component manufacturing offer room for improvement
Today:
  High visibility
  History includes delays and some flawed product
  Limited spares (1 target, 1 PBW, 0 IRPs)
  Little room to accommodate the unexpected
Future:
  Healthy spares, which allows for:
    more aggressive design improvement
    Manufacturing difficulties without large consequences
  Become transparent to management / sponsor
  Regain leverage with suppliers

## Slide 7: SNS personnel roles are now clearly defined
Design Engineer (DE):
  Holds complete design and technical authority over the product configuration
  Responsible for all requirement changes
  Contributes to process related requirements
Manufacturing Engineer (ME) and Technical Project Officer (TPO):
  Fulcrum for success
  Contributes to process related requirements
  Reviews design requirements for manufacturability
  Ensures execution of process and technical requirements
  Establishes productive relationship with suppliers
  Primary contact between Company and Seller
  Tracks and ensures schedule performance
  Witnesses and/or performs inspections of product or processes
Quality Assurance Representative
  Verifies performance of contractual requirements via audit (data package)
  Witnesses and/or performs inspections of product or processes

## Slide 8: Target Module inventory has been affected by reactions to end of life events, manufacturing delays, and operational changes
Current operating model calls for 3 scheduled target module changes per year – thus we need to produce 3/year at steady state
Goal is to reach a steady state level of 5 spare target modules, which represents ~1.5+ years of operation
  The cycle time for implementing improvements is approximately 2 years - 0.5 for design, 1.5 for manufacturing, and 0.5 for operation and PIE
Chart: 
| 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525 | 43556 | 43586 | 43617 | 43647 | 43678 | 43709 | 43739 | 43770 | 43800 | 43831 | 43862 | 43891 | 43922 | 43952 | 43983 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166
Spares | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4

## Slide 9: One spare proton beam window (PBW) is on hand and one is in early procurement stage
New aluminum PBW installed during the recent winter 2016/2017 outage
  This PBW will require replacement no sooner than the winter of 2018/2019
Spare Inconel PBW is on hand
An additional aluminum PBW is presently in the solicitation phases of procurement, delivery is expected around January, 2018
Plan is to retain the Inconel window as a spare and continue to install aluminum PBWs

## Slide 10: Currently installed IRP is past due for replacement and has a leak – replacement IRP is delayed due to a leak
Lower and intermediate IRP sections were complete and assembled
All piping was installed above Intermediate IRP (water cooled stainless steel shielding)
All three transfer lines were assembled to level above eventual carbon steel shielding (top of IRP)
Status prior to leak
Complete IRP
Upper IRP, carbon steel shielding
Intermediate IRP, stainless steel shielding
Lower IRP, moderators, reflector, and shielding

## Slide 11: Leak location
Cross section through top moderator centers
Top upstream moderator
Top downstream moderator
Protons
Top upstream helium lid
Target

## Slide 12: Leak is likely caused by 2 weld induced stresses
1. Water lid weld shrinkage pushes down on the helium lid locally where rib contacts the top of the helium lid
Water lid weld
Water lid
Water lid ribs
Helium lid
2. Helium line piping welds pull up on helium line and lid do to tight clearance in piping
Small clearance between helium and vacuum lines

## Slide 13: Disassembly step 1, remove 3 upper transfer line spools – completed
Requires cutting 3x6 layers of transfer line spools

## Slide 14: Disassembly step 2, remove intermediate IRP – complete
Leak is in second outermost layer of TUM line (helium layer)

## Slide 15: Disassembly step 3, remove piping above lower IRP– complete
Water layer (blue) removed

## Slide 16: Disassembly step 4, mill circumference of lower IRP and water lid welds to open the structure – complete
Ribs cut by hand grinder
Spacers

## Slide 17: Disassembly step 5, separate lower IRP and remove stainless steel shielding and beryllium reflector – complete
Be ready for removal
Stainless shielding ready for removal

## Slide 18: Disassembly step 6, mill away combined water lid in order to access leak location on helium lid – complete
Milling of combined water lid
Exposed top upstream helium lid

## Slide 19: Disassembly step 7, remove top upstream moderator helium lid – in progress
The leak in the helium lid was confirmed, but could not be isolated for repair
Removal of leaking lid is risky due to proximity to the vacuum vessel and cadmium coating below
Replacement helium lid is nearly complete, ready for installation

## Slide 20: Reassembly steps will follow proven processes with adjustments and risk mitigation based on lessons learned
Install helium lid
  Helium lid will be made thicker to lesson thickness disparity and increase leak tightness – this also will reduce any stresses imparted post weld
Re-install Be reflector and stainless shielding – no changes to these components
Re-install lower IRP plenum after refurbishment (spacer added to account for milling during removal)
Install intermediate IRP and piping as done previously
Transfer line piping modified to bring water away from lines before the first 90 degree bends
  This eliminates the chance of weld induced axial stress on the helium line

## Slide 21: The impact of the leak and recovery operations is significant – present delivery date is August, 2017 – risk mitigation planned on multiple fronts
Fabrication schedule risk mitigation
  Fabrication of several parts not necessarily required by repair path
    These parts may be repurposed for next IRP if not needed
Pursuing direct ORNL support of fabrication activities
  Welding, inspection, leak testing
Design changes for rebuild to reduce / eliminate the understood failure modes
  Changing pipe routing configuration
  Changing weld joint designs
  Increasing thickness of helium lid

## Slide 22: The replacement IRP will last until summer 2024 – replaced with 2nd Generation IRP
Lessons learned from recent IRP-1 and IRP-2 leaks will be valuable for design and manufacturing of the 2nd Generation IRP
See J. Janney presentation for detailed changes employed in 2nd generation IRP
Goal is robust design for manufacturing and operations balanced by minimal performance impacts
First 2 IRPs have awful track record with regard to manufacturing schedule – sufficient time is currently available, but there is no spare and history says we must proceed deliberately

## Slide 23: Summary
A dedicated team is in place responsible for producing major neutron source components
Personnel roles are clearly defined – feedback between design and manufacturing is well established
Vendor relationships are strong and the selection of vendors is constantly being updated – supply chains are being diversified
Target module inventory is presently low, but a plan is in place to address the issue
IRP supply is high risk for the facility, but current situations provide opportunity
  The replacement IRP will benefit from limited lessons learned during its rebuild
  The 2nd generation IRP will fully benefit from all lessons learned